## SUB CONTRACTOR IR (hidden)
Project Name: Project Code Num: | [9 empty] | Date: | 2023-10-09
Inspection Request (IR) LOG
IR No. | Title | Rev. | Discipline | Sub-Discipline | Sub-System | Building / Zone | Floor Level | Space No. | Scope | Date Issued | Planned Response Dates | Actual Response Dates | Elapsed in Days | Status | Last Ref. | Root Cause | Remarks
P0010-ATR-SIR-HAM-00001 | Dry Wall Partition - First Fix (Stage B) | 0A | Architectural | Internal Finishing | Gypsum Board | D2 | First | KT1-1 / KT1-2 / KT1-3 | Arabco | 2020-01-01 | 2020-01-02 | 2020-01-01 | -1 | C
P0010-ATR-SIR-HAM-00001 | Dry Wall Partition - First Fix (Stage B) | 0B | Architectural | Internal Finishing | Gypsum Board | D2 | First | KT1-1 / KT1-2 / KT1-3 | Arabco | 2020-01-02 | 2020-01-03 | 2020-01-03 | 0 | C
P0010-ATR-SIR-HAM-00001 | Dry Wall Partition - First Fix (Stage B) | 0C | Architectural | Internal Finishing | Gypsum Board | D2 | First | KT1-1 / KT1-2 / KT1-3 | Arabco | 2020-01-04 | 2020-01-05 | 2020-01-04 | -1 | C
P0010-ATR-SIR-HAM-00001 | Dry Wall Partition - First Fix (Stage B) | 0D | Architectural | Internal Finishing | Gypsum Board | D2 | First | KT1-1 / KT1-2 / KT1-3 | Arabco | 2020-01-07 | 2020-01-08 | 2020-01-08 | 0 | A | L
P0010-ATR-SIR-HAM-00002 | Installation of 1st fix for Lighting system at Wet Area | 00 | Electrical | Lighting | Second Fix | D1 | First | 1B-2 | El Sarah | 2020-01-11 | 2020-01-12 |  | 1366 |  | L
P0010-ATR-SIR-HAM-00003 | Installation of 2nd Fix for GRMS System | 00 | Electrical | GRMS | Second Fix | D1 | First | 1B-2 | El Sarah | 2020-01-11 | 2020-01-12 | 2020-01-11 | -1 | A | L
P0010-ATR-SIR-HAM-00004 | Installation of 2nd Fix for GRMS System | 00 | Electrical | GRMS | Second Fix | D1 | First | 1B-1 | In House | 2020-01-11 | 2020-01-12 | 2020-01-12 | 0 | B | L
P0010-ATR-SIR-HAM-00005 | Installation of 1st fix for Lighting system at Wet Area | 00 | Electrical | Lighting | Second Fix | D1 | First | 1B-1 | In House | 2020-01-11 | 2020-01-12 | 2020-01-14 | 2 | C | L
Formulas:
Planned Response Dates = [Date Issued]+1
Elapsed in Days = IFERROR(IF([Actual Response Dates]="",TODAY(),[Actual Response Dates])-[Planned Response Dates],"")

## MAIN CONTRACTOR IR (hidden)
Project Name: Project Code Num: | [9 empty] | Date: | 2023-10-09
Inspection Request (IR) LOG
IR No. | Title | Rev. | Discipline | Sub-Discipline | Sub-System | Building / Zone | Floor Level | Space No. | Scope | Date Issued | Planned Response Dates | Actual Response Dates | Elapsed in Days | Status | Last Ref. | Root Cause | Remarks
P0010-ATR-SIR-HAM-00001 | Dry Wall Partition - First Fix (Stage B) | 00 | Architectural | Internal Finishing | Gypsum Board | D2 | First | KT1-1 / KT1-2 / KT1-3 | Arabco | 2020-01-12 | 2020-01-13 |  | 1365 |  | L
P0010-ATR-SIR-HAM-00002 | Installation of 1st fix for Lighting system at Wet Area | 00 | Electrical | Lighting | Second Fix | D1 | First | 1B-2 | El Sarah | 2020-01-11 | 2020-01-12 |  | 1366 |  | L
P0010-ATR-SIR-HAM-00003 | Installation of 2nd Fix for GRMS System | 00 | Electrical | GRMS | Second Fix | D1 | First | 1B-2 | El Sarah | 2020-01-11 | 2020-01-12 | 2020-01-11 | -1 | A | L
P0010-ATR-SIR-HAM-00004 | Installation of 2nd Fix for GRMS System | 00 | Electrical | GRMS | Second Fix | D1 | First | 1B-1 | In House | 2020-01-11 | 2020-01-12 | 2020-01-12 | 0 | B | L
P0010-ATR-SIR-HAM-00005 | Installation of 1st fix for Lighting system at Wet Area | 00 | Electrical | Lighting | Second Fix | D1 | First | 1B-1 | In House | 2020-01-11 | 2020-01-12 | 2020-01-14 | 2 | C | L
Formulas:
Planned Response Dates = [Date Issued]+1
Elapsed in Days = IFERROR(IF([Actual Response Dates]="",TODAY(),[Actual Response Dates])-[Planned Response Dates],"")

## MAIN CONTRACTOR IR LOG (2)
Project Name: Four Seasons Hotel - Luxor | Owner : |  | Project Management : Hill International |  |  |  |  | Main Consultant : | [5 empty] | Main Contractor : Atrium Quality Contractor
Contractor Inspection Request (CIR) LOG | [11 empty] | Date: | 2023-10-09
IR No. | Description | Rev. | Discipline | Sub-Discipline | System | Sub-System | Zone | Part/Building | Grid Line | Level | Space No. | Space Func. | Issued Date | Inspection Date | Actual Response Dates | Date limit to issue response | Overdue | Status | Last Ref. | Root Cause | Remarks | SUB | Status
P0020-ATR-SIR-IET-00001 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 4 & 5 & 13 & 14 | N/A | 14 to 20/J to Qx | FDN | N/A | N/A | 2022-01-21 | 2022-01-22 | 2022-01-21 | 2022-01-23 | DONE | B | L
P0020-ATR-SIR-IET-00002 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-24 | 2022-01-25 | 2022-01-24 | 2022-01-26 | DONE | B | L
P0020-ATR-SIR-IET-00003 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-25 | 2022-01-26 | 2022-01-25 | 2022-01-27 | DONE | B | L
P0020-ATR-SIR-IET-00004 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-26 | 2022-01-27 | 2022-01-26 | 2022-01-28 | DONE | B | L
P0020-ATR-SIR-IET-00005 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-26 | 2022-01-27 | 2022-01-26 | 2022-01-28 | DONE | B | L
P0020-ATR-SIR-IET-00006 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place |  | N/A |  | FDN | N/A | N/A | 2022-01-27 | 2022-01-28 | 2022-01-27 | 2022-01-29 | DONE | B | L
P0020-ATR-SIR-IET-00007 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | N/A | 20 to 26/M to Qx | FDN | N/A | N/A | 2022-02-06 | 2022-02-07 | 2022-02-06 | 2022-02-08 | DONE | B | L
P0020-ATR-SIR-IET-00008 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 6 & 14 & 15 | N/A | 20 to 32x/G to R | FDN | N/A | N/A | 2022-02-06 | 2022-02-07 | 2022-02-06 | 2022-02-08 | DONE | B | L
P0020-ATR-SIR-IET-00009 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00010 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00011 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-10 | DONE | B | L
P0020-ATR-SIR-IET-00012 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-09 | 2022-02-10 | 2022-02-09 | 2022-02-11 | DONE | B | L
P0020-ATR-SIR-IET-00013 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-10 | 2022-02-12 | DONE | B | L
P0020-ATR-SIR-IET-00014 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-10 | 2022-02-12 | DONE | B | L
P0020-ATR-SIR-IET-00015 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00016 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00017 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-12 | 2022-02-13 | 2022-02-12 | 2022-02-14 | DONE | B | L
P0020-ATR-SIR-IET-00018 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-13 | 2022-02-14 | 2022-02-13 | 2022-02-15 | DONE | B | L
P0020-ATR-SIR-IET-00019 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-14 | 2022-02-15 | 2022-02-14 | 2022-02-16 | DONE | B | L
P0020-ATR-SIR-IET-00020 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-17 | 2022-02-18 | 2022-02-17 | 2022-02-19 | DONE | B | L
P0020-ATR-SIR-IET-00021 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place |  | N/A |  | FDN | N/A | N/A | 2022-01-21 | 2022-01-22 | 2022-01-22 | 2022-01-23 | DONE | A | L
P0020-ATR-SIR-IET-00022 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place |  | N/A |  | FDN | N/A | N/A | 2022-02-22 | 2022-02-23 | 2022-02-23 | 2022-02-24 | DONE | A | L
P0020-ATR-SIR-IET-00023 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A | 18 to 32x/G to Qz | FDN | N/A | N/A | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-02-25 | DONE | B | L
P0020-ATR-SIR-IET-00024 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A |  | FDN | N/A | N/A | 2022-02-24 | 2022-02-25 | 2022-02-25 | 2022-02-26 | DONE | B | L
P0020-ATR-SIR-IET-00025 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 2 & 3 | A3 / A4 | H To S / 13 To 9Y | FDN | N/A | N/A | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-10 | DONE | C |  | Not following approved SD |  | Al-Abrar | open
P0020-ATR-SIR-IET-00025 | Excavation for Bottom level & Coordinate | 01 | Civil | Civil | Earthwork | Excavation | Zone 2 & 3 | A3 / A4 | H To S / 13 To 9Y | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-28 | DONE | B | L |  |  | Al-Abrar
P0020-ATR-SIR-IET-00026 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 6 & 7 & 8 | N/A | 32x to 38/G to Qx | FDN | N/A | N/A | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-10 | DONE | B | L
P0020-ATR-SIR-IET-00027 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 & 8 | N/A | 32x to 38/G to Qx | FDN | N/A | N/A | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-10 | DONE | B | L
P0020-ATR-SIR-IET-00028 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | N/A | 23 to 27/N to QX | FDN | N/A | N/A | 2022-03-12 | 2022-03-13 | 2022-03-12 | 2022-03-14 | DONE | A | L
P0020-ATR-SIR-IET-00029 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | N/A | 23 to 27/N to QX | FDN | N/A | N/A | 2022-03-12 | 2022-03-13 | 2022-03-12 | 2022-03-14 | DONE | B | L
P0020-ATR-SIR-IET-00030 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 8 | N/A | Z/46 to 47X | FDN | N/A | N/A | 2022-03-13 | 2022-03-14 | 2022-03-13 | 2022-03-15 | DONE | B | L
P0020-ATR-SIR-IET-00031 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 8 | N/A | Z/46 to 47X | FDN | N/A | N/A | 2022-03-13 | 2022-03-14 | 2022-03-13 | 2022-03-15 | DONE | B | L
P0020-ATR-SIR-IET-00032 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-16 | DONE | B | L
P0020-ATR-SIR-IET-00033 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-16 | DONE | B | L
P0020-ATR-SIR-IET-00034 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-17 | 2022-03-18 | 2022-03-17 | 2022-03-19 | DONE | B | L
P0020-ATR-SIR-IET-00035 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-17 | 2022-03-18 | 2022-03-17 | 2022-03-19 | DONE | B | L
P0020-ATR-SIR-IET-00036 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-18 | 2022-03-19 | 2022-03-18 | 2022-03-20 | DONE | B | L
P0020-ATR-SIR-IET-00037 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-18 | 2022-03-19 | 2022-03-18 | 2022-03-20 | DONE | A | L
P0020-ATR-SIR-IET-00038 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-19 | 2022-03-20 | 2022-03-19 | 2022-03-21 | DONE | A | L
P0020-ATR-SIR-IET-00039 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-19 | 2022-03-20 | 2022-03-19 | 2022-03-21 | DONE | B | L
P0020-ATR-SIR-IET-00040 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | (U-Z)(40:47) | FDN | N/A | N/A | 2022-03-21 | 2022-03-22 | 2022-03-21 | 2022-03-23 | DONE | A | L
P0020-ATR-SIR-IET-00041 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | (U-Z)(40:47) | FDN | N/A | N/A | 2022-03-21 | 2022-03-22 | 2022-03-21 | 2022-03-23 | DONE | A | L
P0020-ATR-SIR-IET-00042 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 13 & 14 | N/A | AXJ/A16 to 22X | FDN | N/A | N/A | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-03-26 | DONE | B | L
P0020-ATR-SIR-IET-00043 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 13 & 14 | N/A | AXJ/A16 to 22X | FDN | N/A | N/A | 2022-03-25 | 2022-03-26 | 2022-03-25 | 2022-03-27 | DONE | A | L
P0020-ATR-SIR-IET-00044 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-25 | 2022-03-26 | 2022-03-25 | 2022-03-27 | DONE | A | L
P0020-ATR-SIR-IET-00045 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-26 | 2022-03-27 | 2022-03-26 | 2022-03-28 | DONE | B | L
P0020-ATR-SIR-IET-00046 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | B | L
P0020-ATR-SIR-IET-00047 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-03-26 | 2022-03-27 | 2022-03-26 | 2022-03-28 | DONE | A | L
P0020-ATR-SIR-IET-00048 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 & 12 | N/A | 32x to 38/J to Rx | FDN | N/A | N/A | 2022-03-26 | 2022-03-27 | 2022-03-26 | 2022-03-28 | DONE | C |  | Not following approved SD
P0020-ATR-SIR-IET-00048 | Excavation for Bottom level & Coordinate | 01 | Civil | Civil | Earthwork | Excavation | Zone 7 & 12 | N/A | 32x to 38/J to Rx | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00049 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 & 12 | N/A | 32x to 38/J to Rx | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | B | L
P0020-ATR-SIR-IET-00050 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | B | L
P0020-ATR-SIR-IET-00051 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | 44 & 41 | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | A | L
P0020-ATR-SIR-IET-00052 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | X/QY 46X /49X | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | B | L
P0020-ATR-SIR-IET-00053 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | A | L
P0020-ATR-SIR-IET-00054 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | X/Z & 41/46X | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | A | L
P0020-ATR-SIR-IET-00055 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | X/Z & 41/46X | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | A | L
P0020-ATR-SIR-IET-00056 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 | N/A | 39 to 41/W to Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00057 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 | N/A | 39 to 41/W to Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00058 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | X/QY 46X /49X | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00059 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | WY/ZY & 44/40 | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | A | L
P0020-ATR-SIR-IET-00060 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | 46X/39 & VX/Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | A | L
P0020-ATR-SIR-IET-00061 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | 46X/39 & VX/Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00062 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | W9/Z9 & 44/40 | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00063 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 13 & 14 | N/A | 16-23 / J-K | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | A | L
P0020-ATR-SIR-IET-00064 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | W/Z & 41-39 | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | A | L
P0020-ATR-SIR-IET-00065 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | W/Z & 39-46 | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | A | L
P0020-ATR-SIR-IET-00066 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A | 16/23 & J/K | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | B | L
P0020-ATR-SIR-IET-00067 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | U/Z &39-46 | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | B | L
P0020-ATR-SIR-IET-00068 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | W/Z & 41-39 | FDN | N/A | N/A | 2022-04-01 | 2022-04-02 | 2022-04-01 | 2022-04-03 | DONE | B | L
P0020-ATR-SIR-IET-00069 | Plain concrete top level & Coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 13 & 14 | N/A | J/K & 18/22X | FDN | N/A | N/A | 2022-04-06 | 2022-04-07 | 2022-04-06 | 2022-04-08 | DONE | B | L
P0020-ATR-SIR-IET-00070 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | N/A | 18 to 32x G to Qz | FDN | N/A | N/A | 2022-04-06 | 2022-04-07 | 2022-04-06 | 2022-04-08 | DONE | B | L
P0020-ATR-SIR-IET-00071 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-11 | 2022-04-12 | 2022-04-11 | 2022-04-13 | DONE | A | L
P0020-ATR-SIR-IET-00072 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-11 | 2022-04-12 | 2022-04-11 | 2022-04-13 | DONE | B | L
P0020-ATR-SIR-IET-00073 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-12 | 2022-04-13 | 2022-04-12 | 2022-04-14 | DONE | A | L
P0020-ATR-SIR-IET-00074 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-12 | 2022-04-13 | 2022-04-12 | 2022-04-14 | DONE | B | L
P0020-ATR-SIR-IET-00075 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | 1v/1z & 46/39 | FDN | N/A | N/A | 2022-04-19 | 2022-04-20 | 2022-04-19 | 2022-04-21 | DONE | B | L
P0020-ATR-SIR-IET-00076 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | WY/ZY & 44/41 | FDN | N/A | N/A | 2022-04-19 | 2022-04-20 | 2022-04-19 | 2022-04-21 | DONE | B | L
P0020-ATR-SIR-IET-00077 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | V to Y/40 to 46 | FDN | N/A | N/A | 2022-04-20 | 2022-04-21 | 2022-04-20 | 2022-04-22 | DONE | B | L
P0020-ATR-SIR-IET-00078 | Plain concete top level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A |  | FDN | N/A | N/A | 2022-04-20 | 2022-04-21 | 2022-04-20 | 2022-04-22 | DONE | B | L
P0020-ATR-SIR-IET-00079 | Soil Replacement level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A |  | FDN | N/A | N/A | 2022-04-24 | 2022-04-25 | 2022-04-24 | 2022-04-26 | DONE | A | L
P0020-ATR-SIR-IET-00080 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A |  | FDN | N/A | N/A | 2022-04-25 | 2022-04-26 | 2022-04-26 | 2022-04-27 | DONE | B | L
P0020-ATR-SIR-IET-00081 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | Z to Y/46 to 42 | FDN | N/A | N/A | 2022-04-25 | 2022-04-26 | 2022-04-25 | 2022-04-27 | DONE | A | L
P0020-ATR-SIR-IET-00082 | Plain concete top level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | Z/Y &46/42 | FDN | N/A | N/A | 2022-04-25 | 2022-04-26 | 2022-04-25 | 2022-04-27 | DONE | A | L
P0020-ATR-SIR-IET-00083 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | N/A | 39 to 42/TX to Q Z | FDN | N/A | N/A | 2022-05-17 | 2022-05-18 | 2022-05-18 | 2022-05-19 | DONE | B | L
P0020-ATR-SIR-IET-00084 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 12 | N/A | TX/33 to 38 | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00085 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | N/A | 26 to 33/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00086 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | N/A | 26 to 33/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00087 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | N/A | 16 to 26/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00088 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | N/A | 16 to 26/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00089 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | N/A | 16 to 26/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00090 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | N/A | 26 to 33/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00091 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | N/A | 26 to 33/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00092 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | N/A | 26 to 33/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00093 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | 33 to 38/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00094 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | 33 to 38/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00095 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | 33 to 38/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00096 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 8 | N/A | 33 to 38/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00097 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 8 | N/A | 33 to 38/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00098 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 8 | N/A | 33 to 38/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00099 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | N/A | 23 to 26/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00100 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | N/A | 23 to 26/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00101 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | N/A | 23 to 26/ G to J | FDN | N/A | N/A | 2022-05-25 | 2022-05-26 | 2022-05-26 | 2022-05-27 | DONE | B | L
P0020-ATR-SIR-IET-00102 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | N/A | 26 to 33/ G to J | FDN | N/A | N/A | 2022-05-25 | 2022-05-26 | 2022-05-26 | 2022-05-27 | DONE | B | L
P0020-ATR-SIR-IET-00103 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 33 to 38/ 46x to 47 | FDN | N/A | N/A | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00104 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | 33 to 38/ 42 to 46x | FDN | N/A | N/A | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00105 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | N/A | S To TX /36 To 38 | FDN | N/A | N/A | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00106 | Reinforced Concrete Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 33 to 38/ 46x to 47 | FDN | N/A | N/A | 2022-05-31 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00107 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 23 to27 /G to l | FDN | N/A | N/A | 2022-05-31 | 2022-06-01 | 2022-06-01 | 2022-06-02 | DONE | B | L
P0020-ATR-SIR-SCG-00001 | Installation and Gravity Test for Drainage Pipes | 00 | MEP | Mech | pluming | Drainage | Zone 7 | N/A | X Lines 45 - QZ y Lines 4 - Z | FDN | N/A | N/A | 2022-06-02 | 2022-06-05 | 2022-06-09 | 2022-06-06 | DONE | C |  | Lack of Construction Supervision
P0020-ATR-SIR-SCG-00001 | Installation and Gravity Test for Drainage Pipes | 01 | MEP | Mech | pluming | Drainage | Zone 6 & 7 & 8 | N/A | X Lines 45 - QZ y Lines 4 - Z | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-21 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00108 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | QZ TOTX /36 TO 38 | FDN | N/A | N/A | 2022-06-01 | 2022-06-02 | 2022-06-02 | 2022-06-03 | DONE | B | L
P0020-ATR-SIR-IET-00109 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | U TO Z / 46 to 42 | FDN | N/A | N/A | 2022-06-01 | 2022-06-02 | 2022-06-02 | 2022-06-03 | DONE | B | L
P0020-ATR-SIR-IET-00110 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-02 | 2022-06-04 | 2022-06-04 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00111 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-02 | 2022-06-04 | 2022-06-04 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00112 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 6 | N/A | 24 To 26 /Q ToN | FDN | N/A | N/A | 2022-06-02 | 2022-06-04 | 2022-06-07 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00113 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundries and Starter Bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 32x To 38/47 To 45 | FDN | N/A | N/A | 2022-06-04 | 2022-06-04 | 2022-06-04 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00114 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | A | L
P0020-ATR-SIR-IET-00115 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00116 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00117 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | A | L
P0020-ATR-SIR-IET-00118 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00119 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00120 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00121 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00122 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00123 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00124 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00125 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00126 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00127 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00128 | Excavation for Bottom level & Coordinate - (Tower Crane - 02 ) | 00 | Civil | Civil | Earthwork | Excavation | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | D
P0020-ATR-SIR-IET-00128 | Excavation for Bottom level & Coordinate - (Tower Crane - 02 ) | 01 | Civil | Civil | Earthwork | Excavation | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-13 | 2022-06-14 | 2022-06-13 | 2022-06-15 | DONE | B | L
P0020-ATR-SIR-SCG-00002 | MEP Work Release for R.C. Foundation TO level -4.775 | 00 | Civil | Mech | Concrete | Cast In Place | Zone 8 | N/A | V to Z / 46 × to 47 | FDN | N/A | N/A | 2022-06-15 | 2022-06-16 | 2022-06-21 | 2022-06-17 | DONE | B | L
P0020-ATR-SIR-IET-00129 | Reinforced Concrete Piers and Walls ( Reinforcement and Foemwork ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | V To Y/47 To 46x | FDN | N/A | N/A | 2022-06-14 | 2022-06-15 | 2022-06-15 | 2022-06-16 | DONE | B | L
P0020-ATR-SIR-IET-00130 | Plain concrete top level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | QX To TX / 35 To 38 | FDN | N/A | N/A | 2022-06-14 | 2022-06-15 | 2022-06-14 | 2022-06-16 | DONE | B | L
P0020-ATR-SIR-IET-00131 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | QX To TX / 35 To 38 | FDN | N/A | N/A | 2022-06-14 | 2022-06-15 | 2022-06-14 | 2022-06-16 | DONE | B | L
P0020-ATR-SIR-IET-00132 | Reinforced Concrete Foemwork for Walla & Piers | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | V to Z/46x To 47 | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-16 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00133 | Soil Replacement and Compaction work layer ( 1 ) level & Coordinate for Sump-pit | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | N/A | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-16 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00134 | Soil Replacement and Compaction work layer ( 1 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-16 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00135 | Soil Replacement and Compaction work layer ( 2 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-18 | 2022-06-19 | 2022-06-18 | 2022-06-20 | DONE | B | L
P0020-ATR-SIR-IET-00136 | Soil Replacement and Compaction work layer ( 3 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-18 | 2022-06-19 | 2022-06-19 | 2022-06-20 | DONE | B | L
P0020-ATR-SIR-IET-00137 | Drainage Pipes Location & Level To ( -5.325 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | U to Z/42 To 46x | FDN | N/A | N/A | 2022-06-20 | 2022-06-21 | 2022-06-21 | 2022-06-22 | DONE | B | L
P0020-ATR-SIR-SCG-00003 | MEP Work Release for R.C. Foundation TO level -5.325 | 00 | MEP | Mech | Concrete | Cast In Place | Zone 7 | C2 | U to Z / 42 to 46x | FDN | N/A | N/A | 2022-06-20 | 2022-06-21 | 2022-06-21 | 2022-06-22 | DONE | C |  | Lack of Construction Supervision
P0020-ATR-SIR-SCG-00003 | MEP Work Release for R.C. Foundation TO level -5.325 | 01 | Civil | Mech | Concrete | Cast In Place | Zone 7 | C2 | U to Z / 42 to 46x | FDN | N/A | N/A | 2022-06-22 | 2022-06-23 |  | 2022-06-24 | -472 | open | L
P0020-ATR-SIR-IET-00138 | Soil Replacement and Compaction work layer ( 4 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 31 To 32 / J | FDN | N/A | N/A | 2022-06-20 | 2022-06-21 | 2022-06-20 | 2022-06-22 | DONE | B | L
P0020-ATR-SIR-IET-00139 | Soil Replacement and Compaction work layer ( 2 ) level & Coordinate for Sump-pit | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B5 | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-06-22 | 2022-06-23 | 2022-06-22 | 2022-06-24 | DONE | B | L
P0020-ATR-SIR-IET-00140 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | B1 | 31 To 32 / J | FDN | N/A | N/A | 2022-06-22 | 2022-06-23 | 2022-06-22 | 2022-06-24 | DONE | B | L
P0020-ATR-SIR-IET-00141 | Soil Replacement and Compaction work layer ( 3 ) level & Coordinate for Sump-pit | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B5 | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-23 | 2022-06-26 | DONE | B | L
P0020-ATR-SIR-IET-00142 | Reinforced Concrete Top Layer Reinforcement & Formwork Boundries & Starter bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 46× To 41 / Z To U | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-25 | 2022-06-26 | DONE | B | L
P0020-ATR-SIR-IET-00143 | Permanent Shutter Strep Footing ( Reinforcement , Formwork , Top Level & Location ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-23 | 2022-06-26 | DONE | B | L
P0020-ATR-SIR-IET-00144 | Construction Joint Injectable Hose Installation - Between C1 & C2 | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 & C2 | 46× / Z To V | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-25 | 2022-06-26 | DONE | B | L |  |  | Shield
P0020-ATR-SIR-IET-00145 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | B1 | 31 to 32 X / G to J | FDN | N/A | N/A | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-28 | DONE | B | L |  |  | Shield
P0020-ATR-SIR-IET-00146 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | B1 | 31 to 32 X / G to J | FDN | N/A | N/A | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-28 | DONE | B | L |  |  | Shield
P0020-ATR-SIR-IET-00147 | Plain Concrete Top Level & coordinate and Formwork for TC - 02 | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 30 To 32 / J | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-29 | 2022-06-30 | DONE | B | L |  |  | Al-khaleej
P0020-ATR-SIR-IET-00148 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | EarthWork | Excavation | Zone 5 | C3 | 35 To 38 / QZ To RY | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-06-30 | DONE | B | L |  |  | Al-Abrar
P0020-ATR-SIR-IET-00149 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 46x To 47 / V To Z | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-29 | 2022-06-30 | DONE | B | L |  |  | Al-khaleej
P0020-ATR-SIR-IET-00150 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | C2 | 46x To 47 / V To Z | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-29 | 2022-06-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0001 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 28 / G To J | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-06-30 | 2022-07-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0002 | Reinforced Concrete Reinforcement Piers & Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 46x To 41 / Z To U | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-06-30 | 2022-07-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0003 | Reinforced Concrete Formwork Piers & Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 46x To 41 / Z To U | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-07-02 | 2022-07-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0004 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 28 / G To J | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-07-03 | 2022-07-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0005 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | C1 | 45 To 47 / V To Z | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-06-30 | 2022-07-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0006 | Mass Concrete Mockup | 00 | Civil | Civil | Concrete | Cast in place | Zone 13 | N/A | 12 To 14 / 3× To 4× | FDN | N/A | N/A | 2022-07-03 | 2022-07-06 | 2022-07-18 | 2022-07-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0007 | Modified Traverse Points | 00 | Civil | Civil | Surveying | Traverse | General | N/A | All Project | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0008 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 42 To 46x / Z To WX | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0009 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 42 To 46x / Z To WX | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0010 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0011 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0012 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0013 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-04 | 2022-07-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0014 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-04 | 2022-07-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0015 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | K To Q / 22× To 28 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-04 | 2022-07-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0016 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-05 | 2022-07-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0017 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-05 | 2022-07-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0018 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-05 | 2022-07-06 | 2022-07-06 | 2022-07-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0019 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-05 | 2022-07-06 | 2022-07-06 | 2022-07-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0020 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | C4 | 34 To 36 | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0021 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 12 | C4 | TX / 35 To 36 | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-21 | 2022-07-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0022 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0023 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0024 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-07-28 | 2022-07-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0025 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-07-28 | 2022-07-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0026 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-06-20 | 2022-07-22 | DONE | C |  | Consultant request extra documents and materials |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0026 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0027 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-07-23 | 2022-07-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0028 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0029 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0030 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0031 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0032 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28× TO 33 / H TO J | FDN | N/A | N/A | 2022-07-23 | 2022-07-24 | 2022-07-23 | 2022-07-25 | DONE | C |  | Using Improper Material |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0032 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28× TO 33 / H TO J | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0001 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C2 | 46x To 45 / WY To U | FDN | N/A | N/A | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-26 | DONE | C |  | Not following approved SD |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0001 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C2 | 46x To 45 / WY To U | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-25 | 2022-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0033 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 33 To 38 / 42 To 46x | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0034 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 33 To 38 / 42 To 46x | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0035 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 6 | B2 | 22x TO 28 / J TO QZ | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0036 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 6 | B2 | 22x TO 28 / J TO QZ | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0037 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0038 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0039 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0040 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 10 | B4 | 22x TO 28 / QX TO TX | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0041 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 11 | B3 | 28x TO 34 / QY TO TX | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0042 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 34 To 37 | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-30 | 2022-07-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0043 | PVC Protection - Screed & Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 6 | B2 | 22x TO 28 / J TO QZ | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-30 | 2022-07-31 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0044 | Soil Replacement Layer ( 5 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-28 | 2022-07-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0045 | Soil Replacement Layer ( 6 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-28 | 2022-07-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0046 | Existing Piles Record | 00 | Civil | Civil | Earthwork | Demolishing | Zone 10 | N/A | N/A | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-08-03 | 2022-08-01 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0047 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundries and Starter Bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22x To 32x / H To J | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-08-04 | 2022-08-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0048 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work to Level 72.075 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-07-31 | 2022-08-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0049 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work to Level 72.325 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-07-31 | 2022-08-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0050 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-08-03 | 2022-08-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0051 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-08-03 | 2022-08-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0052 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work to Level 72.575 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-07-31 | 2022-08-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0053 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work to Level 72.825 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-07-31 | 2022-08-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0054 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 35 To 38 / PX To RY | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-07-31 | 2022-08-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0055 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 & 12 | C3 | PX To RY / 38 To 36 | FDN | N/A | N/A | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-03 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0056 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 & 12 | C3 | PX To RY / 38 To 36 | FDN | N/A | N/A | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-03 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0057 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-02 | 2022-08-03 | 2022-08-07 | 2022-08-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0058 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 32x / PX To N | FDN | N/A | N/A | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0059 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | RY To TX / 35 To 38 | FDN | N/A | N/A | 2022-08-03 | 2022-08-04 | 2022-08-07 | 2022-08-05 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0060 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 & 12 | C3 | PX To RY / 38 To 36 | FDN | N/A | N/A | 2022-08-03 | 2022-08-04 | 2022-08-07 | 2022-08-05 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0061 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-04 | 2022-08-05 | 2022-08-07 | 2022-08-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0062 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-04 | 2022-08-05 | 2022-08-07 | 2022-08-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0063 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0064 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0065 | Existing Piles Record | 00 | Civil | Civil | Earthwork | Demolishing | Zone 5 | N/A | N/A | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0066 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0067 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0068 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0069 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0070 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0071 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0072 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0073 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0074 | Soil Replacement Layer ( 5 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0075 | Soil Replacement Layer ( 6 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0076 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0077 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | C3 & B4 | TX To QZ / 33 To 36 | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0078 | Dead Shutering Location | 00 | Civil | Civil | Concrete | Block Work | Zone 11 & 12 | C3 & B4 | TX To QZ / 33 To 39 | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0079 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | L To QZ / 22x To 33 | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-10 | 2022-08-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0080 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0081 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-08 | 2022-08-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0082 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-08 | 2022-08-10 | DONE | C |  | Reference coordinates not correct |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0082 | Soil Replacement Layer ( 1 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0083 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0084 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 | A4 | 3X To TX / 14 To15 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0085 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0086 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-11 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0087 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0088 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0089 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-14 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0090 | Reinforced Concrete Foundation Boundries and Starter Bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22x To 28x / J To L | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-10 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0091 | Reinforced Concrete Foundation Reinforcement and formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22x To 28x / J To L | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-10 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0092 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-10 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0093 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0094 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-09 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0095 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-10 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0096 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0097 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-14 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0098 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-14 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0099 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-15 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0100 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-21 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0101 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-22 | 2022-08-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0102 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-16 | 2022-08-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0103 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-18 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0104 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 & C3 | QX To TX / 35 To 38 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-11 | 2022-08-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0105 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-11 | 2022-08-13 | 2022-08-15 | 2022-08-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0106 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-11 | 2022-08-13 | 2022-08-18 | 2022-08-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0107 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-14 | 2022-08-15 | 2022-08-15 | 2022-08-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0108 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-14 | 2022-08-15 | 2022-08-18 | 2022-08-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0109 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | QX To TX / 34 To 38 | FDN | N/A | N/A | 2022-08-14 | 2022-08-15 | 2022-08-21 | 2022-08-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0110 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-15 | 2022-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0111 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-18 | 2022-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0112 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 33 / H To J | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-18 | 2022-08-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0113 | Reinforced Concrete Piers Reinforcement & formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 33 / J To H | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0002 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | 24 To 25 / N To Q | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0114 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-16 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0115 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0116 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-16 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0117 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0118 | Existing Piles Record | 00 | Civil | Civil | Earthwork | Demolishing | Zone 2 & 3 | A2 & A3 & A4 | 9Y To 13 / 3 To 9X | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 |  | 2022-08-18 | -417 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0119 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B3 & B5 | 16 & 27 / QX To RY | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0120 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 | 2022-08-21 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0121 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 | 2022-08-22 | 2022-08-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0003 | Installation and Gravity Test of Drainage Pipe lines as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | 24 To 25 / N To Q | FDN | N/A | N/A | 2022-08-18 | 2022-08-20 | 2022-08-21 | 2022-08-21 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0122 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-21 | 2022-08-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0123 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0124 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0125 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-23 | 2022-08-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0004 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | R To TX/ QY To S | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-22 | 2022-08-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0126 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0127 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-23 | 2022-08-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0005 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To V / N To Q | FDN | N/A | N/A | 2022-08-20 | 2022-09-01 | 2022-09-03 | 2022-09-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0128 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-21 | 2022-08-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0129 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-22 | 2022-08-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0130 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0131 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0132 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B3 | 31 To 32x / QY To RY | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0133 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B3 | 31 To 32x / QY To RY | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0134 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 & 12 | B3 & B4 & C3 | QX To S / 26 To 34 | FDN | N/A | N/A | 2022-08-22 | 2022-08-24 | 2022-08-25 | 2022-08-25 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0135 | Soil Replacement Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-08-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0136 | Soil Replacement Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-08-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0137 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 10 | B3 | QX To RY / 18 To 26 | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-08-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0138 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 & 15 | B5 | J To L / 16 To 23 | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0139 | Soil Replacement Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0140 | Soil Replacement Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-23 | 2022-08-24 | 2022-08-27 | 2022-08-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0141 | Reinforced Concrete Piers formwork & Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32X / H To J | FDN | N/A | N/A | 2022-08-23 | 2022-08-24 | 2022-08-27 | 2022-08-25 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0142 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 10 | B3 | QZ To RY / 18 To 26 | FDN | N/A | N/A | 2022-08-24 | 2022-08-25 | 2022-08-25 | 2022-08-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0006 | Installation for drainage and Electrical pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | R To TX /38 To 35 | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-08-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0007 | Gravity test for Drainage pipes only | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | R To TX /38 To 35 | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-08-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0143 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX To RY | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-08-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0144 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RX To TX | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-29 | 2022-08-28 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0145 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 & 15 | B5 | J To L / 16 To 23 | FDN | N/A | N/A | 2022-08-27 | 2022-08-28 | 2022-08-28 | 2022-08-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0146 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 & 15 | B5 | J To L / 16 To 23 | FDN | N/A | N/A | 2022-08-27 | 2022-08-28 | 2022-08-28 | 2022-08-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0147 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 10 | B3 | QX To RY / 18 To 26 | FDN | N/A | N/A | 2022-08-27 | 2022-08-28 | 2022-08-28 | 2022-08-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0148 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B3 | QX To RY / 26 To 36 | FDN | N/A | N/A | 2022-08-28 | 2022-08-29 | 2022-08-28 | 2022-08-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0149 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B3 | QX To RY / 26 To 36 | FDN | N/A | N/A | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-08-31 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0150 | Reinforced Concrete Boundries Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 & B5 | PX To K / 18 To 26 | FDN | N/A | N/A | 2022-08-29 | 2022-08-30 | 2022-08-29 | 2022-08-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0151 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | K To QX / 18 To 27 | FDN | N/A | N/A | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-08-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0152 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B3 | QX To RY / 26 To 36 | FDN | N/A | N/A | 2022-08-30 | 2022-08-31 | 2022-08-31 | 2022-09-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0153 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-08-31 | 2022-09-01 | 2022-09-04 | 2022-09-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0154 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-08-31 | 2022-09-01 | 2022-09-04 | 2022-09-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0155 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | RY To T / 32X To 34 | FDN | N/A | N/A | 2022-08-31 | 2022-09-01 | 2022-09-03 | 2022-09-02 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0156 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-09-01 | 2022-09-03 | 2022-09-04 | 2022-09-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0157 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-09-01 | 2022-09-03 | 2022-09-04 | 2022-09-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0008 | Installation and gravity test for drainage pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To V / N To Q | FDN | N/A | N/A | 2022-09-01 | 2022-09-04 | 2022-09-14 | 2022-09-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0009 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | QX To N/ 18 To 21 | FDN | N/A | N/A | 2022-09-01 | 2022-09-03 | 2022-09-03 | 2022-09-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0010 | Installation and gravity test for drainage pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | QX To N/ 18 To 21 | FDN | N/A | N/A | 2022-09-03 | 2022-09-04 | 2022-09-06 | 2022-09-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0158 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 3 | A4 | 13X To 9Y / TX To S | FDN | N/A | N/A | 2022-09-04 | 2022-09-05 | 2022-09-04 | 2022-09-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0159 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-07 | 2022-09-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0160 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-11 | 2022-09-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0161 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 22X To 18 / QZ To K | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-10 | 2022-09-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0162 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 22X To 18 / QZ To K | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0163 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-07 | 2022-09-08 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0164 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-11 | 2022-09-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0165 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 32X To 34 / RY To T | FDN | N/A | N/A | 2022-09-07 | 2022-09-08 | 2022-09-10 | 2022-09-09 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0166 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 32X To 34 / RY To T | FDN | N/A | N/A | 2022-09-07 | 2022-09-08 | 2022-09-10 | 2022-09-09 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0167 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-07 | 2022-09-08 | 2022-09-07 | 2022-09-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0168 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To V / M To PX | FDN | N/A | N/A | 2022-09-08 | 2022-09-10 | 2022-09-08 | 2022-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0011 | Mechanical (Installation and gravity test for drainage pipes) & Survey Inspection (Drainage Pipes Location & Level) as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 | 46X To 44X / 33 To 34 | FDN | N/A | N/A | 2022-09-08 | 2022-09-10 | 2022-09-08 | 2022-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0169 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 26 To 33 / J To H | FDN | N/A | N/A | 2022-09-08 | 2022-09-10 | 2022-09-10 | 2022-09-11 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0170 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 33 / K To QZ | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0171 | PVC Protection cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B4 | 32 To 34 / RY To T | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0172 | PVC Protection Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B4 | 32 To 34 / RY To T | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0012 | Mechanical (Installation and gravity test for FFD Pipes line which added as per attached RFI ) & Survey (Drainage Pipes Location & Level) as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | PX To Q / 30 To 31 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-14 | 2022-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0173 | Wood Planks Extending for Berlin Shoring system | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 | A4 | 8 To TX / 9Y To 15 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0174 | Construction Joint Injectable Hose Installation Between B5a- B5b | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 5 | B5a & B5b | 8 To 20 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0013 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 & 6 | B2 | M ToQX/ 24 To 28 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-13 | 2022-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0175 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0176 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-11 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0177 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0178 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0179 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0180 | RC Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C3 | 32X To 38 / 39X To 42X | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-17 | 2022-09-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0181 | Construction Joint Injectable Hose Installation Between B5(B) & B2(A) | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | B5 & B2 | 22X To 23 / QX To K | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0182 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 26 To 30 / J To H | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0183 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-13 | 2022-09-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0184 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-22 | 2022-09-15 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0185 | Reinforced Concrete piers Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 & C2 | X To Y / 41 TO 44 | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-14 | 2022-09-15 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0014 | Installation and Water test for Drainage Pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 5 & 6 | B2 | M To QZ / 24 To 28 | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-13 | 2022-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0186 | Reinforced Concrete Foundation Boundaries Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | RY To PX / V To 38 | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-17 | 2022-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0187 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0188 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-22 | 2022-09-15 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0189 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-14 | 2022-09-15 | 2022-09-21 | 2022-09-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0190 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-14 | 2022-09-15 | 2022-09-17 | 2022-09-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0191 | Construction Joint Injectable Hose Installation Between B2(A) & B2(B) | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | B2 | 28 / L To Q | FDN | N/A | N/A | 2022-09-15 | 2022-09-16 | 2022-09-19 | 2022-09-17 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0192 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0193 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-15 | 2022-09-16 | 2022-09-22 | 2022-09-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0194 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 32X To 35 / TX To RY | FDN | N/A | N/A | 2022-09-17 | 2022-09-18 | 2022-09-17 | 2022-09-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0195 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 32X To 35 / TX To RY | FDN | N/A | N/A | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0196 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 22X / K To QZ | FDN | N/A | N/A | 2022-09-18 | 2022-09-19 | 2022-09-19 | 2022-09-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0015 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 12 | C3 | 33 To 38 / RY To 43 | FDN | N/A | N/A | 2022-09-18 | 2022-09-19 | 2022-09-19 | 2022-09-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0197 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 41 To 45 / U To YY | FDN | N/A | N/A | 2022-09-19 | 2022-09-20 | 2022-09-19 | 2022-09-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0198 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 2 | A2 & A3 | 4X To 9 / A To E | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-20 | 2022-09-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0199 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 22X / K To QZ | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-24 | 2022-09-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0200 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 41 To 45 / U To YY | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0016 | Installation and gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 12 | C3 | 33 To 38 / RY To 43 | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-25 | 2022-09-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0201 | Underlayment Layer - Geotextile - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0202 | Waterproofing PVC Layer - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0203 | PVC Protection cartmode - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0204 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 3 | A4 | 10X To 12 / Q To S | FDN | N/A | N/A | 2022-09-21 | 2022-09-22 | 2022-09-26 | 2022-09-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0017 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 | 45 To 47 / Z To Y | FDN | N/A | N/A | 2022-09-21 | 2022-09-22 | 2022-09-25 | 2022-09-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0205 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 | A2 & A3 | 8 / 4X | FDN | N/A | N/A | 2022-09-21 | 2022-09-22 | 2022-09-24 | 2022-09-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0206 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-24 | 2022-09-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0207 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-25 | 2022-09-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0208 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-24 | 2022-09-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0209 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 32X To 38 / RY To 42 | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-25 | 2022-09-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0210 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C3 | 32X To 38 / RY To 42 | FDN | N/A | N/A | 2022-09-24 | 2022-09-25 | 2022-09-27 | 2022-09-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0211 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C3 | 32X To 38 / RY To 42 | FDN | N/A | N/A | 2022-09-24 | 2022-09-25 | 2022-09-27 | 2022-09-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0212 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 34 / RY To Q | FDN | N/A | N/A | 2022-09-24 | 2022-09-25 | 2022-09-29 | 2022-09-26 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0213 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-26 | 2022-09-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0214 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-25 | 2022-09-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0215 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0216 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-29 | 2022-09-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0217 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0218 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | 22 To 34 / RY To TX | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0219 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 32X / K To QZ | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0018 | Installation and gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 | 45 To 47 / Z To Y | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2022-09-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0220 | Reinforced Concrete Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 To 35 / RY To TX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-10-03 | 2022-09-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0221 | Soil Replacement Layer ( 1 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0222 | Soil Replacement Layer ( 2 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0223 | Soil Replacement Layer ( 3 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0224 | Soil Replacement Layer ( 4 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-28 | DONE | C |  | Reference level not correct |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0224 | Soil Replacement Layer ( 4 ) level & Coordinates Gravel | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-29 | 2022-10-01 | 2022-10-01 | 2022-10-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0225 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0226 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0227 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0228 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-10-05 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0229 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0230 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0231 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-27 | 2022-09-28 | 2022-09-27 | 2022-09-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0232 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | 22 To 34 / RY To TX | FDN | N/A | N/A | 2022-09-27 | 2022-09-28 | 2022-10-02 | 2022-09-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0233 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 32X / K To QZ | FDN | N/A | N/A | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0234 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | 22 To 34 / RY To TX | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-03 | 2022-09-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0235 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 28 To 32X / J To L | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0236 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 | B5 | 17 To 22X / K To QZ | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0237 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-01 | 2022-09-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0238 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-03 | 2022-09-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0239 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-01 | 2022-09-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0240 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0241 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-01 | 2022-09-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0242 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-29 | 2022-10-01 | 2022-10-02 | 2022-10-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0019 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 28 To 34 / RY To QX | FDN | N/A | N/A | 2022-09-29 | 2022-10-01 | 2022-10-06 | 2022-10-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0243 | Construction Joint injectable Hose installation Between B2(B) & C3(A) / C4 & C3(B) / C3(A) & C3(B) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | B2 & C3 & C4 | U To V / 39 To 42 & Y To X / 39 To 42 & 38 To RY | FDN | N/A | N/A | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0244 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 28 To 32X / J To L | FDN | N/A | N/A | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0245 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 | B5 | 18 To 22X / K To QS | FDN | N/A | N/A | 2022-10-02 | 2022-10-03 | 2022-10-05 | 2022-10-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0246 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-02 | 2022-10-03 | 2022-10-03 | 2022-10-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0247 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 9 & 10 | B6 & B8 | 15 To 22X / RY To TX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0248 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-04 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0249 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0250 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0251 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-04 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0252 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0253 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-10 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0020 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B3A & B6B | 22X To 27 / Q To RY | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0254 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0255 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0256 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0257 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0258 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 33 / TX To RY | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0259 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0260 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0261 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-10 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0262 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0263 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-10 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0264 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0265 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-10 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0266 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-08 | 2022-10-09 | 2022-10-13 | 2022-10-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0267 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0268 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | SX To TX / B To E | FDN | N/A | N/A | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0269 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 24 To 34 / RY To TX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0270 | Construction Joint injectable Hose installation Between B2/B3 & C3/B3 | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 & B3 & C3 | 23 To 35 / Q To RY | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-13 | 2022-10-11 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0271 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0272 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0273 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-13 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0274 | Reinforced Concrete Piers & Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 33 To 38 / RY To M | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0021 | Installation and gravity test for drainage pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 28 To 34 / RY To QX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0021 | Installation and gravity test for drainage pipes as per Highlighted | 01 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 28 To 34 / RY To QX | FDN | N/A | N/A | 2022-10-12 | 2022-10-13 | 2022-10-13 | 2022-10-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0275 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 10 | B6 | 21 To 22 / RY To SY | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0276 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 27 To W / RY To QZ | FDN | N/A | N/A | 2022-10-10 | 2022-10-11 | 2022-10-13 | 2022-10-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0022 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 33 To 34 / RY To RY | FDN | N/A | N/A | 2022-10-10 | 2022-10-11 | 2022-10-13 | 2022-10-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0023 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 43 To 25 / K To 41 | FDN | N/A | N/A | 2022-10-10 | 2022-10-11 | 2022-10-17 | 2022-10-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0277 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0278 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-17 | 2022-10-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0279 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B3-B | 34 To 28 / QX To RY | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-16 | 2022-10-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0280 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0281 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0282 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0283 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0284 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0285 | Reinforced Concrete Piers and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | C3 | W To Y / RY To 41 | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0286 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 4 | A3 & B7 | 10X To 11 / K To Q | FDN | N/A | N/A | 2022-10-12 | 2022-10-13 | 2022-10-12 | 2022-10-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0287 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-15 | 2022-10-16 | 2022-10-16 | 2022-10-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0288 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-12 | 2022-10-13 | 2022-10-12 | 2022-10-14 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0289 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 38 To 31X / N To RX | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-16 | 2022-10-16 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0290 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-13 | 2022-10-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0291 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-13 | 2022-10-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0292 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-16 | 2022-10-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0024 | Installation and Water Leakage test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B3A & B6B | 22X To 27 / Q To RY | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-15 | 2022-10-17 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0024 | Installation and Water Leakage test for drainage pipes as per Highlighted | 01 | MEP | Mech | Pluming | Drainage | Zone 10 | B3A & B6B | 22X To 27 / Q To RY | FDN | N/A | N/A | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0293 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 23 To 28 / QX To RY | FDN | N/A | N/A | 2022-10-16 | 2022-10-17 | 2022-10-17 | 2022-10-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0294 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 23 To 28 / QX To RY | FDN | N/A | N/A | 2022-10-16 | 2022-10-17 | 2022-10-19 | 2022-10-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0295 | Construction Joint injectable Hose installation Between B3(B) & B3(A) | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B3 | 28 / QX To RY | FDN | N/A | N/A | 2022-10-17 | 2022-10-18 | 2022-10-17 | 2022-10-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0296 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-17 | 2022-10-18 | 2022-10-17 | 2022-10-19 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0297 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-17 | 2022-10-24 | 2022-10-24 | 2022-10-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0298 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-18 | 2022-10-19 | 2022-10-19 | 2022-10-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0299 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-19 | 2022-10-20 | 2022-10-23 | 2022-10-21 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0300 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 24 To 32X / L To Q | FDN | N/A | N/A | 2022-10-19 | 2022-10-20 | 2022-10-23 | 2022-10-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0301 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 32 / M To Q | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0302 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0303 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 32 To 35 / M To QX | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0304 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0305 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 11 To 10X / QX To SX | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-24 | 2022-10-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0306 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 11 To 10X / QX To SX | FDN | N/A | N/A | 2022-10-20 | 2022-10-31 | 2022-10-31 | 2022-11-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0307 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-25 | 2022-10-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0308 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-25 | 2022-10-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0309 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 4 | A3 & B7 | 10X To 11 / K To Q | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-23 | 2022-10-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0310 | Reinforced Concrete Walls Reinforcement to level -4.775 | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 40X To 42 / 36 To 38 | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-23 | 2022-10-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0311 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 & B8 | 16 To 22 / TX To QX | FDN | N/A | N/A | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0312 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 & A2 | 2 To 6 / CX To 10Y | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-25 | 2022-10-26 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0313 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 & A2 | 3 To 4X / A To C | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-25 | 2022-10-26 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0314 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 35 / RY To TX | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-27 | 2022-10-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0025 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 29 To 31 / M To L | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0026 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 36 To 38 / RY To QY | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0315 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 24 To 35 / RY To SY | FDN | N/A | N/A | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0316 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0317 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-10-27 | 2022-10-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0318 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-10-30 | 2022-10-28 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0319 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-10-27 | 2022-10-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0027 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 41 To 44 / U To X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-11-01 | 2022-10-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0001 | Duct Bank Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | 38 To 35 / QX To PX | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-11-01 | 2022-10-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0320 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 25 To 32X / M To QX | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-30 | 2022-10-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0321 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-30 | 2022-10-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0322 | Soil Replacement Layer ( 1 & 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-11-01 | 2022-10-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0323 | Soil Replacement Layer ( 1 & 2 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-31 | 2022-10-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0324 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 33 To 38 / N To RY | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-30 | 2022-10-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0325 | Soil Replacement Layer ( 2 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-10-30 | 2022-10-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0326 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0327 | Soil Replacement Layer ( 3 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0328 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-10-31 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0329 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 3 & 9 | A4 & B8 | 11 To 15 / TX To RY | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0330 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 9 | B8 | 13 To 16 / TX To RY | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0331 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 4 & 9 & 13 | B7 & B8 | 12 To 14 / H To S | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | C |  | Survey Supervision |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0331 | Excavation for Bottom Level & Coordinate | 01 | Civil | Civil | Earthwork | Excavation | Zone 4 & 9 & 13 | B7 & B8 | 12 To 14 / H To S | FDN | N/A | N/A | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0332 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0333 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0334 | Construction Joint injectable Hose installation Between B3 & B6 | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B3 | 22X To 23 / QZ To RY | FDN | N/A | N/A | 2022-10-30 | 2022-10-31 | 2022-11-02 | 2022-11-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0335 | Soil Replacement Layer ( 4 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0336 | Soil Replacement Layer ( 2 & 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0337 | Soil Replacement Layer ( 2 & 3 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-10-31 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0338 | Soil Replacement Layer ( 3 & 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0339 | Soil Replacement Layer ( 3 & 4 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-10-31 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0340 | Soil Replacement Layer ( 4 & 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0341 | Soil Replacement Layer ( 4 & 5 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-10-31 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0342 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 25 To 32X / M To Q | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0343 | Reinforced Concrete Piers and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 33 / RY To QZ | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0344 | Soil Replacement Layer ( 5 & 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0345 | Soil Replacement Layer ( 5 & 6 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-05 | 2022-11-06 | 2022-11-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0346 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0347 | Soil Replacement Layer ( 6 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-05 | 2022-11-06 | 2022-11-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0348 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | S To Q / 9Y To 12 | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0349 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | S To Q / 9Y To 12 | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0350 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0351 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0352 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 | A To B / 3X To 4 | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-02 | 2022-11-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0353 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 23 / TX To Z | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0028 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B6 | 20 To 22X / RY To QZ | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-02 | 2022-11-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0029 | Sleeve Pipes Location & Level as per Highlighted ( Survey Inspection ) and Mechanical Installation | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | RY To 32X | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-06 | 2022-11-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0030 | Installation and Water Leakage test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 41 To 44 / U To X | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-06 | 2022-11-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0354 | Reinforced Concrete Piers and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 28X / H To 47X | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0355 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-02 | 2022-11-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0356 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-02 | 2022-11-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0357 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 35 / QX To RY | FDN | N/A | N/A | 2022-11-03 | 2022-11-04 | 2022-11-07 | 2022-11-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0358 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0359 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0360 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 & 4 | A3 & A4 | 12 To 9Y / TX To M | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0361 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0362 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0363 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3 & A4 & B7 | 9Y To 12 / TX To M | FDN | N/A | N/A | 2022-11-06 | 2022-11-09 | 2022-11-10 | 2022-11-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0364 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 & 9 | A4 & B8 | TX / 12 To 16 | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-09 | 2022-11-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0365 | "Stair 11" To Level (-5.875) Level and Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / RX To QX | S.B | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0031 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C6 | 37 / RX To QZ | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0032 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B6 | 20 To 22X / RY To QZ | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0366 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 4 & 9 & 13 | B7 & B8 | 14 To 16 / RY To J | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0367 | Reinforced Concrete Piers Formwork & Walls To Level ( -4.775 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0368 | Reinforced Concrete Piers Formwork To Level ( -4.775 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 25 To 23X / Q To M | FDN | N/A | N/A | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0369 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX To RY | FDN | N/A | N/A | 2022-11-07 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0033 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B2 | 27 / M | FDN | N/A | N/A | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0370 | Reinforced Concrete Walls Formwork for H Vac Opening | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 42 / X To YY | FDN | N/A | N/A | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0371 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0372 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0373 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-13 | 2022-11-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0374 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-13 | 2022-11-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0034 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 21 / QX To RY | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-10 | 2022-11-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0375 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3 & A4 & B7 | 9Y To 12 / TX To M | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-10 | 2022-11-11 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0376 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 | A1 | A To B / 1 To 3 | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-10 | 2022-11-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0377 | Reinforced Concrete Piers and Walls Reinforcement to Level (-4.775) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 25 To 35 / TX To RY | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0378 | Underlayment Layer - Geotextile (Walls) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 9Y To 11 / TX To QX | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0379 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0380 | Soil Replacement Layer ( 1 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0381 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3 & A4 & B7 | 9Y To 12 / TX To M | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0382 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0383 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0384 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0385 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0386 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-16 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0387 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0388 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-16 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0389 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 1 | A1 | 2X / 4 To A | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0390 | Waterproofing PVC Layer ( for Walls ) – to Level ( -6.25 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 9Y To 10Y / TX | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0391 | PVC Protection & Cartmode – to Level ( -6.25 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 9Y To 10Y / TX | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0392 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-13 | 2022-11-14 | 2022-11-13 | 2022-11-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0393 | Underlayment Layer - Geotextile ( Sump Walls & Floor ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 10Y / QX To RX | FDN | N/A | N/A | 2022-11-13 | 2022-11-14 | 2022-11-14 | 2022-11-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0394 | Waterproofing PVC Layer ( Sump Walls & Floor ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 10Y / QX To RX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0395 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0396 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0397 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0398 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0399 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-17 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0400 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0401 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 42 To 45 / V To Y | L.G | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0402 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / V To Z | L.G | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-15 | 2022-11-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0403 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 25 To 27 / M To PX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0404 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 25 To 27 / M To PX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-17 | 2022-11-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0405 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-15 | 2022-11-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0406 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0407 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0408 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0409 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0410 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0411 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 | C3 | PX To QY / Z To U | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0412 | Reinforced Concrete Sub Basement Bottom Layer Reinforcement to Level ( -5.875 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / RY To QS | S.B | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0413 | Reinforced Concrete Sub Basement Top Layer Reinforcement to Level ( -5.875 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / RY To QS | S.B | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0414 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 24 / QX To SY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0415 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A1 & A2 & A3 | N To TX / A To EY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0035 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22 / R To RY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-19 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0036 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B6 | 16 To 18 / QZ To RY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-19 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0416 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 24 / TX To S | FDN | N/A | N/A | 2022-11-16 | 2022-11-17 | 2022-11-16 | 2022-11-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0417 | PVC Protection - Surface Preparation Screed & Cartmode ( Sump Walls & floor ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 10Y / QX To RX | FDN | N/A | N/A | 2022-11-16 | 2022-11-17 | 2022-11-17 | 2022-11-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0418 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 & B4 | 23 To 34 / QX To TX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-20 | 2022-11-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0419 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22X To 28X / H To G | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-17 | 2022-11-20 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0419 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 01 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22X To 28X / H To G | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0002 | Installation of Duct Bank Pipe Lines | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | 38 To 35 / QX To PX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-21 | 2022-11-20 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0002 | Installation of Duct Bank Pipe Lines | 01 | MEP | Elec | Elec | Power | Zone 7 | C3 | 38 To 35 / QX To PX | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-10 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0420 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-20 | 2022-11-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0421 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-21 | 2022-11-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0422 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-23 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0423 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-22 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0424 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-22 | 2022-11-21 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0425 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-23 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0426 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-24 | 2022-11-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0426 | RC Foundation Waterproofing Bitumen | 01 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0427 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-24 | 2022-11-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0427 | RC Foundation Waterproofing Bitumen | 01 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0428 | Reinforced Concrete Foundation Bottom Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 9Y To 10Z / TX To 9 | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0428 | Reinforced Concrete Foundation Bottom Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 9Y To 10 / TX To 9 | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-22 | 2022-11-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0037 | Installation of drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0037 | Installation of pluming Network as per Highlighted | 01 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-05 | 2022-12-08 | 2022-12-08 | 2022-12-09 | DONE | B | L
1176-FSL-CP01-CN-AT-CIR-ST-0429 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 12 | C3 & C4 | 33 To 38 / N To RX | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0430 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-23 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0431 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0432 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-21 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0433 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0434 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-21 | 2022-11-22 | 2022-11-22 | 2022-11-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0435 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-23 | 2022-11-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0436 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-27 | 2022-11-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0437 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0438 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-27 | 2022-11-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0439 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A4-B & A3-A | A To 10Y / 6 To TX | FDN | N/A | N/A | 2022-11-23 | 2022-11-24 | 2022-11-24 | 2022-11-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0440 | Soil Replacement Layer( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To D / 2X To 4X | FDN | N/A | N/A | 2022-11-23 | 2022-11-24 | 2022-11-24 | 2022-11-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0038 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | SX To TX / 9Y To 10 | FDN | N/A | N/A | 2022-11-23 | 2022-11-27 | 2022-11-30 | 2022-11-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0441 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0442 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0443 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-24 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0444 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0445 | Soil Replacement Layer( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0446 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 4 & 9 | B7 & B8 & A2 | 10X To 17 / J To TX | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0447 | Soil Replacement Layer( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-28 | 2022-11-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0448 | Soil Replacement Layer( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To D / 2X To 4X | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-29 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0449 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 17 To 23 / TX To S | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0450 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | S/31 To 33 | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0039 | Installation and survey inspection of sleeve pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | T To Sy / 38 | FDN | N/A | N/A | 2022-11-26 | 2022-11-29 | 2022-12-01 | 2022-11-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0451 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S / 37 | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0452 | Reinforced Concrete Cloumns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 35 / RY To 4X | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-27 | 2022-11-29 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0453 | Construction Joint injectable Hose installation Between B5 & B6 | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B5 & B6 | 16 To 23 / Q To QX | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0454 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 12 To 15 / TX To RX | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-27 | 2022-11-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0455 | Reinforced Concrete Walls Reinforcement to Level ( -4.775 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / QX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0456 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 15 To 24 / RY To TX | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0457 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 12 To 15 / TX To RX | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-28 | 2022-11-30 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0458 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10 To 9Y / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-11-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0459 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0460 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-12-03 | 2022-11-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0461 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0462 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 12 To 15 / TX To RX | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-29 | 2022-12-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0463 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | 1X To 5 / A To 9Y | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-29 | 2022-12-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0464 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 4 | A3 & B7 | K To N / 10Y To D | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-29 | 2022-12-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0465 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 9Y To 10 / TX To 9 | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-30 | 2022-12-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0466 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-12-03 | 2022-12-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0467 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 16 / TX To RX | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0468 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0469 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-03 | 2022-12-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0470 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0471 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-03 | 2022-12-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0472 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QZ / 17 To 27 | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0473 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QZ / 17 To 27 | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-03 | 2022-12-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0474 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22X / RY To QZ | FDN | N/A | N/A | 2022-12-01 | 2022-12-03 | 2022-12-05 | 2022-12-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0475 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 16 / TX To RX | FDN | N/A | N/A | 2022-12-01 | 2022-12-03 | 2022-12-03 | 2022-12-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0476 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 35 / TX | FDN | N/A | N/A | 2022-12-01 | 2022-12-03 | 2022-12-03 | 2022-12-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0040 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 17 To 23 / RY To QX | FDN | N/A | N/A | 2022-12-03 | 2022-12-04 | 2022-12-08 | 2022-12-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0477 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4-B & B8-A | 11 To 14 / RY To TX | FDN | N/A | N/A | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-05 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0477 | Reinforced Concrete Foundation Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4-B & B8-A | 11 To 14 / RY To TX | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-11 | 2022-12-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0478 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 16 / TX To RX | FDN | N/A | N/A | 2022-12-03 | 2022-12-04 | 2022-12-04 | 2022-12-05 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0479 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4-B | 11 To 13X / TX To S | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-04 | 2022-12-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0480 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0481 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-12 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0482 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0483 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-12 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0484 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0484 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | FDN | N/A | N/A | 2022-12-05 | 2022-12-06 | 2022-12-06 | 2022-12-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0485 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 TO 16 / RY To RX | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-08 | 2022-12-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0486 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B3 | QZ To RY / 23 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0487 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B3 | QZ To RY / 23 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0488 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 | B2 | L To QZ / 27 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0489 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 | B2 | L To QZ / 27 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0490 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 & 3 | B7 & A1 & A2 | A To D / 1 To 4 & L To P / 10 To 12 | FDN | N/A | N/A | 2022-12-05 | 2022-12-06 | 2022-12-06 | 2022-12-07 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0491 | Exhaust Duct Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 43 To 41 / X To XY | FDN | N/A | N/A | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-07 | DONE | C |  |  |  | N/A
1176-FSL-CP01-CN-AT-CIR-ST-0491 | Exhaust Duct Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 43 To 41 / X To XY | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | N/A
1176-FSL-CP01-CN-AT-CIR-ST-0492 | Reinforced Concrete Foundation Bottom Layer Reinforcement & Columns Starter bars & Grade Beams Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | S To T / 11 To 13X | FDN | N/A | N/A | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0493 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 11 To 15 / K To RY | FDN | N/A | N/A | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0041 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 32 To 33 / S To SY | FDN | N/A | N/A | 2022-12-06 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0494 | Reinforced Concrete Columns &Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4 & B8 | 10 To 14 / TX To SX | FDN | N/A | N/A | 2022-12-07 | 2022-12-08 | 2022-12-08 | 2022-12-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0495 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B8 | TX / 33 To 35 | FDN | N/A | N/A | 2022-12-07 | 2022-12-08 | 2022-12-07 | 2022-12-09 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0496 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 & 4 | A1 & A2 & B7 | 2X To 5 / A To C & M To PX / 10X To 12 | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0497 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-08 | 2022-12-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0498 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0499 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-12 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0500 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0501 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-11 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0502 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0503 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-11 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0504 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0505 | Reinforced Concrete Tie Beams Foundation Top Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | S To RX / 36 To 37 | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-15 | 2022-12-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0506 | Reinforced Concrete Grade Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | RY To TX / 35 To 24 | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-11 | 2022-12-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0507 | Planted Steel Bars in Column | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S / 36 | L.G | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-18 | 2022-12-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0042 | Gravity Test for Drainage Network as Attached | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0003 | Duct Bank Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 35 To 36 | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-13 | 2022-12-12 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0003 | Duct Bank Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 01 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 39 To 40 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-22 | 2022-12-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0508 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 & 4 | A1 & A2 & B7 | 2X To 4X / A To C & K To PX / 10 To 13 | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-13 | 2022-12-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0509 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 | 3X To 4 / A To B | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0510 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0511 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0512 | Soil Replacement Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0513 | Soil Replacement Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0514 | Soil Replacement Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0515 | Soil Replacement Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-14 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0516 | Soil Replacement Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0517 | Soil Replacement Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0518 | Soil Replacement Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0519 | Soil Replacement Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0520 | Soil Replacement Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0521 | Soil Replacement Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0522 | Soil Replacement Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0523 | Soil Replacement Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0524 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22X / RY To QZ | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0525 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | RY To TX / 9Y To 10 | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0043 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4-B | 10 To 11 / RY To TX | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0004 | Installation of Duct Bank Pipes as Highlighted | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 35 To 36 | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0004 | Installation of Duct Bank Pipes as Highlighted | 01 | MEP | Elec | Elec | Power | Zone 7 & 10 & 11 | C3 & B4 | RY To P / 20 To 33 | L.G | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0005 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 & 12 | C1 & C2 & C3 | 42 To 47 / U To Z | FDN | N/A | N/A | 2022-12-10 | 2022-12-14 | 2022-12-14 | 2022-12-15 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0526 | Reinforced Concrete Piers and Walls Tie beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22X / RY To QZ | FDN | N/A | N/A | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-14 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0044 | Installation and Gravity Test for pluming network as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4-B | 10 To 11 / RY To TX | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0006 | Installation of Access Control Conduit as Highlighted | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | S To 35 | FDN | N/A | N/A | 2022-12-12 | 2022-12-13 | 2022-12-15 | 2022-12-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0527 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 TO 16 / TX To RX | FDN | N/A | N/A | 2022-12-12 | 2022-12-13 | 2022-12-13 | 2022-12-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0528 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 1 To 2X / A To CX | FDN | N/A | N/A | 2022-12-13 | 2022-12-14 | 2022-12-14 | 2022-12-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0529 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 22X To 27/ H To G | FDN | N/A | N/A | 2022-12-13 | 2022-12-20 | 2022-12-21 | 2022-12-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0530 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 1 To 2X / A To CX | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0531 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4 -B1 | 10 To 14 / S To T | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0532 | Reinforced Concrete Foundation Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 13X / S To T | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0533 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-15 | 2022-12-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0534 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 & B7 | 13 To 16 / RX To S | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-15 | 2022-12-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0045 | Gravity Test for Drainage Network after concrete pouring as Attached | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-27 | 2022-12-16 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0045 | Gravity Test for Drainage Network after concrete pouring as Attached | 01 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-09 | 2023-08-07 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0046 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 32 / H To K | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0535 | Reinforced Concrete Lower Ground Slab Reinforcement Bottom Layer | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 47 To 42X / Z To V | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0536 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28 To 31 / H To G | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-15 | 2022-12-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0537 | Lower Ground Slab Coordinates & Top Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 47 To 42X / U To Z | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0538 | Plain Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 | 3 To 6 / A To B | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0539 | Construction Joint injectable Hose installation Between A4-B & A4-A | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10 To 10X / TX To RY | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0540 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0541 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0542 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | U To Z / 47 To 42 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0543 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / 34 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-21 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0544 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 3 / A To CY | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0545 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0546 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0547 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32 / G To K | FDN | N/A | N/A | 2022-12-17 | 2022-12-21 | 2022-12-24 | 2022-12-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0548 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32 / G To K | FDN | N/A | N/A | 2022-12-17 | 2022-12-21 | 2022-12-24 | 2022-12-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0549 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0550 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47 To 46X / Z To V | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0551 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0552 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 18 / J To RY | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0553 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 18 / J To RY | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-20 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0554 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 32X / J To G | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0555 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 & 11 | B2 & B3 | 33 To 27 / RY To L | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0556 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0557 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 18 / J To RY | FDN | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-20 | 2022-12-21 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0558 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 & 11 | B2 & B3 | 33 To 27 / RY To L | FDN | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0559 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0560 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 42 To 46 / U To Z | L.G | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-20 | 2022-12-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0561 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0562 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0563 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B4 | 33 To 25 / RY To SY | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0564 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 & 10 | B4 & B6 | 25 To 18 / RY To TX | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0565 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0566 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / Q To S | S.B | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0567 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-21 | 2022-12-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0568 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0569 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B4 | 33 To 25 / RY To SY | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-21 | 2022-12-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0570 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 30 / G To L | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0571 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 4 & 9 | B7 & B8 | R To J / 14 To 16 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-21 | 2022-12-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0572 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 13 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0573 | PVC Protection - Surface Preparation Screed & Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 13 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0574 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 43 To 47 / V To Y | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0575 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0576 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0577 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 16 To 11 / J To RX | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0578 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | A To CY / 1 To 6 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0579 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S TO 36 | FDN | N/A | N/A | 2022-12-21 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0580 | Underlayment Layer - Geotextile – Vertical to Level “77.60” | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4-A | 9Y To 10 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0581 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0582 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0583 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | S To QX / 38 | S.B To L.G | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-25 | 2022-12-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0584 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 & 10 | B4 & B6 | 25 To 18 / RY To TX | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0585 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To L | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0586 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To L | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0587 | Reinforced Concrete Stair Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | S To QX / 38 | S.B To L.G | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0588 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | QX To RY / 17 To 23 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0589 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 & A4 | A To E / 5 To 8 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0590 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To H | L.G | N/A | N/A | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0591 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To H | L.G | N/A | N/A | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-26 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0007 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 | C1 | 42 To 47 / V To Z | FDN | N/A | N/A | 2022-12-24 | 2022-12-29 | 2022-12-31 | 2022-12-30 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0592 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-24 | 2022-12-25 | 2022-12-25 | 2022-12-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0593 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4-B | 10Z To 14 / S To TX | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-26 | 2022-12-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0594 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0595 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 & 7 | B1 & B2 | 24 To 32 / PX To H | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-25 | 2022-12-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0596 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 & 7 | B1 & B2 | 24 To 32 / PX To H | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-26 | 2022-12-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0597 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 30 / G | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0598 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 30 / G | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0599 | Reinforced Concrete Grade Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 31 To 34 / RY To S | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0600 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0601 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-28 | 2022-12-27 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0601 | Backfilling Layer ( 1 ) Compaction Work | 01 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-28 | 2022-12-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0602 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0603 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0604 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0605 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0606 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 | B1 | 26 To 30 / H To G | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0607 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 | B1 | 26 To 30 / H To G | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0608 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 17 / RX To SY | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0609 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28 To 30 / G | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2022-12-28 | 2022-12-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0610 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28 To 30 / G | FDN | N/A | N/A | 2022-12-27 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0611 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0047 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | K To G / 23 To 32 | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2023-01-01 | 2022-12-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0612 | Waterproofing PVC Layer – Vertical to Level “77.60” | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4-A | 9Y To 10 | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0613 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-27 | 2022-12-29 | 2022-12-31 | 2022-12-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0614 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 & A3 | C To E / 5 To 7 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-28 | 2022-12-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0615 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / Z | L.G | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0616 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 46 / W To X | L.G | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0617 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 15 To 16 / SX To TX | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0618 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 & A3 | C To E / 5 To 7 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0619 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-31 | 2022-12-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0620 | PVC Protection – Cartmode _Vertical to Level “77.60” | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4-A | 9Y To 10 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0621 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 & A3 | C To E / 5 To 7 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0622 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | RY To QX / 16 To 13X | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-29 | 2023-01-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0623 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0624 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0624 | Backfilling Layer ( 3 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0625 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0626 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 16 To 14 / S To TX | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0627 | Reinforced Concrete Walls Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 34 / SX To TX | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0628 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 30 / G | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-03 | 2023-01-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0629 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0630 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0631 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0632 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0048 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 & B3 | T To RX / 33 To 34 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-03 | 2023-01-01 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0048 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 & B3 | T To RX / 33 To 34 | FDN | N/A | N/A | 2023-05-25 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0633 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0634 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0635 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 24 To 32 / G To J | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0636 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0637 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0638 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0639 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0640 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | A To 10 / 9 To SX | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0641 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 32 / G To J | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0642 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 18 To 31 / G | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0643 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 32 / G To J | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0644 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | A To CX / CZ To 3 | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0645 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | 31 To 35 / RY To SY | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0646 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 2X / A To D | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0049 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | J To G / 22X To 33 | FDN | N/A | N/A | 2022-12-31 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0647 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 47 To 42X / Y To V | L.G To G.F | N/A | N/A | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0648 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 | 12 To 10Y / K To QX | FDN | N/A | N/A | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0649 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 & A3 | 2 To 8 / 11 To A | FDN | N/A | N/A | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0650 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | A To 10 / 9 To SX | S.B To L.G | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | B |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0650 | Reinforced Concrete Columns Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | A To 10 / 9 To SX | S.B To L.G | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0050 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To 34 / L To N | FDN | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-11 | 2023-01-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0651 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 12 To 18 / K To RY | FDN | N/A | N/A | 2023-01-02 | 2023-01-09 | 2023-01-09 | 2023-01-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0652 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | W / 43 | L.G To G.F | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-04 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0653 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | 31 To 35 / RY To SY | FDN | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0654 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S / 36 To 37 | S.B To L.G | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0655 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 22X To 26 / K To G | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-07 | 2023-01-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0656 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 22X To 26 / K To G | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-07 | 2023-01-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0657 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0658 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0659 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0660 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-09 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0661 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | 9Y To 10Y / QY To L | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0008 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 | C1 | 44 To 47 / Y To VX | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-12 | 2023-01-05 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0662 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-04 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0663 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0664 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-04 | 2023-01-09 | 2023-01-09 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0665 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-04 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0666 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 12 | C3 | 33 To 37 / M To RX | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0667 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 12 | C3 | 33 To 37 / M To RX | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0668 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 | 24 To 28 / L To Q | FDN | N/A | N/A | 2023-01-04 | 2023-01-08 | 2023-01-08 | 2023-01-09 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0669 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 | 24 To 28 / L To Q | FDN | N/A | N/A | 2023-01-04 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0670 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | Y To X / 39 | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0671 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | Y To X / 39 | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0672 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0051 | Installation for pluming network as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To 34 / L To N | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-11 | 2023-01-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0673 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8-A | 13X To 18 / S To TX | FDN | N/A | N/A | 2023-01-05 | 2023-01-07 | 2023-01-07 | 2023-01-08 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0674 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / M To Q | FDN | N/A | N/A | 2023-01-05 | 2023-01-08 | 2023-01-08 | 2023-01-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0675 | Reinforced Concrete Columns & Walls Reinforcement to Level "-5.35" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX / 9Y To 10 | S.B To L.G | N/A | N/A | 2023-01-05 | 2023-01-07 | 2023-01-07 | 2023-01-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0676 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-05 | 2023-01-10 | 2023-01-11 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0677 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-05 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0678 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 To 41 / QX To RY | FDN | N/A | N/A | 2023-01-05 | 2023-01-07 | 2023-01-08 | 2023-01-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0679 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0680 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0681 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-10 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0682 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0683 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0684 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0685 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-07 | 2023-01-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0686 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | W To Z / 45 To 47 | L.G To G.F | N/A | N/A | 2023-01-07 | 2023-01-10 | 2023-01-11 | 2023-01-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0687 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0688 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0689 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0690 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0691 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 11 To 14 / K To RY | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0692 | Reinforced Concrete Wall Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 | QX To R / 18 | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-08 | 2023-01-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0693 | Reinforced Concrete Wall Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 | QX To R / 18 | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0694 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / ZY | L.G To G.F | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-11 | 2023-01-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0695 | Reinforced Concrete GB Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 / RX To S | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0696 | "Stair 11" To Level (-4.25) Level and Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 38 / Q To QY | S.B | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-16 | 2023-01-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0697 | Reinforced Concrete Columns & Walls Reinforcement from Level "73.75" to Level "74.95" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX / 9Y To 10 | S.B To L.G | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0698 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C4 & C3 | QX To TX / 37 To 38 | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0699 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0700 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0701 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0702 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0703 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0704 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0705 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0706 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0707 | Reinforced Concrete Wall Reinforcement from Level "70.75" to Level "74.95" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX To 9X / 9Y | FDN To L.G | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0052 | Installation of Pipe Sleeves as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 45 To J / 22X To 26 | FDN | N/A | N/A | 2023-01-09 | 2023-01-18 | 2023-01-19 | 2023-01-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0053 | Installation and Survey Inspection of sleeves Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | G To J / 22X To 24 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0009 | Reinforced Concrete Duct Bank Coordinates | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 12 | C3 & C4 | X To Yy / 41 To S | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0708 | Reinforced Concrete Wall Reinforcement from Level "70.75" to Level "73.10" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9Y To B / 9X | FDN | N/A | N/A | 2023-01-10 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0709 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 | B6 | 18 To 22X / QX To RY | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-10 | 2023-01-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0710 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | RX To M / 12 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0711 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | RX To M / 12 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0712 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | RX To K / 12 To 13 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0713 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | Q To QX / 38 | FDN | N/A | N/A | 2023-01-10 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0714 | Plain Concrete S.O.G Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 40 To 44 / X To Z | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0715 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 12 | C3 & C4 | 35 To 38 / QZ To S | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-14 | 2023-01-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0716 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / Z | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0717 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 | 12 To 14 / K To RY | FDN | N/A | N/A | 2023-01-11 | 2023-01-12 | 2023-01-12 | 2023-01-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0718 | Reinforced Concrete Walls Reinforcement to L.G Slab | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 23 To 26 / G To J | FDN | N/A | N/A | 2023-01-11 | 2023-01-12 | 2023-01-12 | 2023-01-13 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0719 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-11 | 2023-01-12 | 2023-01-14 | 2023-01-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0720 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-11 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0721 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-15 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0722 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0723 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-15 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0724 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0725 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 44 / Z To Yy | L.G | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0726 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-17 | 2023-01-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0727 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0728 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-14 | 2023-01-18 | 2023-01-19 | 2023-01-19 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0729 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0730 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-17 | 2023-01-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0731 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0732 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-18 | 2023-01-19 | 2023-01-19 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0733 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0734 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-22 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0735 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0736 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / K To QZ | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0737 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / QX To RX | FDN | N/A | N/A | 2023-01-14 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0738 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | 2X To 5 /EY | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-15 | 2023-01-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0739 | Underlayment Layer - Geotextile Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-14 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0054 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 32 To 38 / PX To P | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-18 | 2023-01-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0010 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 | C1 | 43 To 44 / Z To Y | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-17 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0740 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0741 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0742 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0743 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0744 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 44 / Z To Yy | L.G | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-16 | 2023-01-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0745 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-16 | 2023-01-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0055 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 | A3 | 7 To 8 / B To C | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-18 | 2023-01-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0011 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 6 | B2 | 28 To 24 / N To L | L.G | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-02-09 | 2023-01-18 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0746 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3-A | 9 To 6 / A To C | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0747 | Lower Ground Slab RC Coordinates & Top Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 44 / Z To Yy | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-16 | 2023-01-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0748 | Reinforced Concrete Stairs Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / 42 To QY | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0749 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / ZY | L.G To G | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0750 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 10 | B6 | 18 To 23 / QX To RY | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0751 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 10 | B6 | 18 To 23 / QX To RY | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-25 | 2023-01-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0752 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 22 To 25 / H To J | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0753 | Reinforced Concrete Walls & Columns Formwork to L.G Slab | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 23 To 26 / G To J | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0754 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 38 / 41 | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0755 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 38 / 41 | FDN | N/A | N/A | 2023-01-16 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0756 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | N To S / 12 To 13 | FDN | N/A | N/A | 2023-01-17 | 2023-01-18 | 2023-01-18 | 2023-01-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0056 | Gravity Test for pluming network as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To 34 / L To N | FDN | N/A | N/A | 2023-01-17 | 2023-01-18 | 2023-01-18 | 2023-01-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0012 | Electrical Cables Sleeves Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | Q To QX / 37 To 38 | FDN | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-19 | 2023-01-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0757 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C3 | QX To RY / 35 To 38 | FDN | N/A | N/A | 2023-01-18 | 2023-01-21 | 2023-01-22 | 2023-01-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0758 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-21 | 2023-01-20 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0759 | Reinforced Concrete Walls Reinforcement to Level "74.325" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 | S.B To L.G | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-21 | 2023-01-20 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0760 | Reinforced Concrete Walls Reinforcement to Level "72.70" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9 To 9X / A | S.B To L.G | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-21 | 2023-01-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0761 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / K To QZ | L.G | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0762 | Lower Ground Slab Plain Concrete Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 10 & 11 | B2 & B3 | 27 To 32X / RY To PX | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0763 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0763 | Backfilling Layer ( 1 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0764 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0765 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0765 | Backfilling Layer ( 2 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0766 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0767 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0767 | Backfilling Layer ( 5 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0768 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0769 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0769 | Backfilling Layer ( 6 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0770 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0771 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 | 11 To 13 / N To R | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0772 | PVC Protection - Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0773 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47 / Z | L.G To G.F | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0774 | Reinforced Concrete Lower Ground Slab level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / QZ To M | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0775 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | CZ To 2X / A To CY | FDN | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0776 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0777 | Reinforced Concrete Column Reinforcement to Level "72.10" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 / S | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0778 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-26 | 2023-01-28 | 2023-01-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0779 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0780 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-26 | 2023-01-28 | 2023-01-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0781 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0782 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 11 To 12 / K To M | FDN | N/A | N/A | 2023-01-21 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0783 | Waterproofing PVC Layer - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | QX To RY / 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0784 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0785 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0786 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0787 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0788 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A4 | CZ To 1 / B To C | FDN | N/A | N/A | 2023-01-21 | 2023-01-22 | 2023-01-24 | 2023-01-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0789 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0790 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-22 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0791 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX To 9X / 9Y To D | S.B To L.G | N/A | N/A | 2023-01-22 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0792 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | J To G / 22X To 27 | FDN | N/A | N/A | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0793 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | 10Y To B / 5 To 8 | FDN | N/A | N/A | 2023-01-23 | 2023-01-29 | 2023-01-30 | 2023-01-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0794 | PVC Protection – Cartmode - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | QX To RY / 38 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0795 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0796 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-23 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0057 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 12 To 18 / RY To K | FDN | N/A | N/A | 2023-01-23 | 2023-01-26 | 2023-01-31 | 2023-01-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0797 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 16 To 18 / K To RY | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-26 | 2023-01-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0798 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | J To G / 22X To 27 | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-24 | 2023-01-26 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0799 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0800 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0801 | Reinforced Concrete Walls Reinforcement to Level "74.50" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S To RY / 35 | S.B To L.G | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0802 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0803 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0804 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0805 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0806 | Underlayment Layer - Geotextile Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | A To D / 1 & 2 | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-24 | 2023-01-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0807 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 & 11 | B4 & B6 | RY To SX / 33 To 34 | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0808 | Reinforced Concrete Stairs Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / 42 To QX | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0809 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | A To D / 1 & 2 | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-28 | 2023-01-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0810 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | A To D / 1 & 2 | FDN | N/A | N/A | 2023-01-25 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0811 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0812 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-25 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0813 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0814 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 16 To 14 / K To RY | FDN | N/A | N/A | 2023-01-25 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0815 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-26 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0816 | Construction Joint injectable Hose installation Between B7-B8 & B5-B6 Foundation | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 16 To 18 / K To RY | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0817 | Reinforced Concrete Column Formwork to Level ( -4.775 / -7.00 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | K To S / 12 To 13 | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-28 | 2023-01-29 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0818 | Reinforced Concrete Foundation Sumpit Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B2 | QZ To RY / 11 To 10 Z | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-26 | 2023-01-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0819 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-28 | 2023-01-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0820 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-26 | 2023-02-04 | 2023-02-04 | 2023-02-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0058 | Installation of Drainage Pipes & Gravity Test as highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 12 To 18 / RY To K | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0059 | Drainage Pipes Locations & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 & 11 | B4 & B6 | 18 To 33 / RY To S | FDN | N/A | N/A | 2023-01-28 | 2023-01-29 | 2023-01-31 | 2023-01-30 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0059 | Drainage Pipes Locations & Level ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 & 11 | B4 & B6 | 18 To 33 / RY To S | FDN | N/A | N/A | 2023-02-14 | 2023-02-22 | 2023-02-23 | 2023-02-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0821 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | L To RY / 30 To 33 | FDN | N/A | N/A | 2023-01-28 | 2023-01-30 | 2023-01-31 | 2023-01-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0822 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A3 | 2X To 6 / 10X & 10Y | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-02-01 | 2023-01-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0013 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | 12 / N | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-02-09 | 2023-01-31 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ME-0060 | Drainage Pipes Locations & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A3 | 10X To 10 / RY To N | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-01-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0823 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-01-30 | 2023-01-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0824 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-29 | 2023-02-04 | 2023-02-04 | 2023-02-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0825 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-01-30 | 2023-01-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0826 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-29 | 2023-02-08 | 2023-02-08 | 2023-02-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0061 | Installation For Tank Drain Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A3 | 9Y To 10 / RY To N | FDN | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-02-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0827 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 32X To 28 / Q To RY | L.G | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-02-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0828 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 11 | B6 | 17 To 24 / RY To Q | FDN | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-02-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0829 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 11 | B6 | 17 To 24 / RY To Q | FDN | N/A | N/A | 2023-01-30 | 2023-02-04 | 2023-02-04 | 2023-02-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0830 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0831 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 & 4 | A3-B | C To EY / 6 To 8 | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0832 | Underlayment Layer - Geotextile to Level ( -5.675 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | B1 | 22X To 27 / G To K | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-01 | 2023-02-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0833 | Backfilling Layer ( 3 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-01 | 2023-02-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0834 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0835 | Backfilling Layer ( 4 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-01 | 2023-02-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0836 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0837 | Construction Joint injectable Hose installation Between A3-A | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A3-B | B To C / M To QX | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0838 | Waterproofing PVC Layer To Level ( -5.675 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | B1 | 22X To 27 / G To K | FDN | N/A | N/A | 2023-02-01 | 2023-02-02 | 2023-02-01 | 2023-02-03 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0839 | PVC Protection – Cartmode To Level ( -5.675 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | B1 | 22X To 27 / G To K | FDN | N/A | N/A | 2023-02-01 | 2023-02-02 | 2023-02-01 | 2023-02-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0840 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | 5 To 2X / EY To 10Y | FDN | N/A | N/A | 2023-02-02 | 2023-02-04 | 2023-02-05 | 2023-02-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0841 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 14 | C3 | 37 To 38 / PX To RX | FDN | N/A | N/A | 2023-02-02 | 2023-02-04 | 2023-02-05 | 2023-02-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0842 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-05 | 2023-02-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0843 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-08 | 2023-02-08 | 2023-02-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0844 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-05 | 2023-02-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0845 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-08 | 2023-02-08 | 2023-02-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0846 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 & B7 | SY To RX / 11 To 18 | FDN | N/A | N/A | 2023-02-04 | 2023-02-06 | 2023-02-07 | 2023-02-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0847 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 12 | C3 | PX To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-11 | 2023-02-11 | 2023-02-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0848 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | S To TX / 33 To 35 | FDN | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-05 | 2023-02-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0849 | Reinforced Concrete Slab Formwork Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 46 To 42X / V To Z | G.F | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0850 | Reinforced Concrete Corbel Beam Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 38 | L.G | N/A | N/A | 2023-02-05 | 2023-02-11 | 2023-02-11 | 2023-02-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0851 | Reinforced Concrete Walls & Piers Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B8 & B7 | RY To K / 18 To 13X | FDN | N/A | N/A | 2023-02-06 | 2023-02-07 | 2023-02-07 | 2023-02-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0852 | Reinforced Concrete Slab Level & Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | RX To S / 38 | L.G | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-11 | 2023-02-09 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0852 | Reinforced Concrete Slab Level & Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | RX To S / 38 | L.G | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0853 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | Z To ZY / 44 To PX | L.G | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-12 | 2023-02-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0854 | Reinforced Concrete Walls & Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | S To TX / 14 To 16 | FDN | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0062 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 35 To 38 / RY To Q | FDN | N/A | N/A | 2023-02-07 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0014 | Electrical Cables Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 & 9 & 10 & 11 | B6 & B4 & B3 & C3 | P To S / 18 To 36 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0855 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-02-08 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0856 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 & B7 | RY To S / 12 To 15 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0857 | Reinforced Concrete Sumpit Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | QX To RY / 10Z To 10Y | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-11 | 2023-02-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0858 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0859 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0860 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0861 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0015 | Electrical Cables Sleeves Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 4 | B7 | 12 / N | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0862 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QX / 17 To 24 | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-09 | 2023-02-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0863 | Reinforced Concrete Sump pit Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10Y / QX To RY | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-09 | 2023-02-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0864 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 & B5 & B6 | L To RY / 17 To 24 | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-13 | 2023-02-12 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0864 | Plain Concrete Foundation Top Level Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 & B5 & B6 | L To RY / 17 To 24 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0865 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B3 & B6 | QX To RY / 16 To 27 | L.G | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-13 | 2023-02-12 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0865 | Plain Concrete Foundation Top Level Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B3 & B6 | QX To RY / 16 To 27 | L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0866 | Underlayment Layer - Geotextile – Vertical to Level “-4.575” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 9Y To Q / 38 | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-11 | 2023-02-12 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0867 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | W To V / 46X To 47 | L.G | N/A | N/A | 2023-02-09 | 2023-02-13 | 2023-02-13 | 2023-02-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0016 | Electrical Cables Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 40 To 41 | FDN | N/A | N/A | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0868 | Waterproofing PVC Layer – Vertical to Level “-4.575” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 9Y To Q / 38 | FDN | N/A | N/A | 2023-02-11 | 2023-02-12 | 2023-02-14 | 2023-02-13 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0869 | Underlayment Layer - Geotextile – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 18 To 10 / J To K | FDN | N/A | N/A | 2023-02-11 | 2023-02-12 | 2023-02-12 | 2023-02-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0870 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | YY / 42 | L.G | N/A | N/A | 2023-02-12 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0871 | Waterproofing PVC Layer – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 18 To 10 / J To K | FDN | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-12 | 2023-02-14 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0872 | Reinforced Concrete Walls & Columns Reinforcement to Level 74.50 | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 11 To 13 / TX To SY | S.B To L.G | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-12 | 2023-02-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0873 | Reinforced Concrete Walls Reinforcement to Level 74.05 | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10 / S To RY | S.B To L.G | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-12 | 2023-02-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0063 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 15 | B1 | 28X To 32X / H To M | FDN | N/A | N/A | 2023-02-12 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0874 | Reinforced Concrete Walls Openings Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10X / SX To RY | L.G | N/A | N/A | 2023-02-12 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0875 | Reinforced Concrete Walls Openings Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX To T / 11 | L.G | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0876 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | S / 15 | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0877 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 To 16 / RY To TX | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0878 | Reinforced Concrete Columns and Grade Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 12 To 13X / RY To T | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0064 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 27 / G To H | FDN | N/A | N/A | 2023-02-13 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0879 | PVC Protection – Cartmode – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 18 To 10 / J To K | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0880 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 41 To 44 / YY To Z | L.G | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0881 | Construction Joint injectable Hose installation for Sub_basement Walls | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 11 To 14 / SX To TX | S.B | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0882 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 33 / SY To SX | L.G | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-16 | 2023-02-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0065 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 32X To 33 / H To J | L.G | N/A | N/A | 2023-02-13 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0883 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 42 / YY | L.G To G.F | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0884 | Reinforced Concrete Walls Reinforcement to Level -1.62 | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / QZ To RX | L.G To G.F | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0885 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 33 To 31X / L To RY | L.G | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0066 | Installation of Drainage Pipes as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 35 To 38 / RY To Q | FDN | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0067 | Installation of Drainage Pipes Network as per highlighted / Gravity Test | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 & 11 | B4 & B6 | 18 To 33 / RY To S | FDN | N/A | N/A | 2023-02-14 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0886 | PVC Protection – Cartmode – Vertical to Level “-4.575” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 9Y To Q / 38 | FDN | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0887 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | SX To S / 10 To 10Z | S.B To L.G | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0888 | Reinforced Concrete Oil Intercptor pit Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 34 / RY To S | FDN | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-02-16 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0068 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C3 & B3 | 33 To 34 / M To RY | L.G | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0069 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23 To 28 / J To H | FDN | N/A | N/A | 2023-02-15 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0070 | Installation for Drainage Network as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C3 & B3 | 33 To 34 / M To RY | L.G | N/A | N/A | 2023-02-15 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0889 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S To RX / 38 | L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0890 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S To RX / 38 | L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0891 | Reinforced Concrete Core Walls and Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | M To L / 11 To 12 | FDN To L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0892 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | K To RY / 16 To 13 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0893 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0893 | Soil Replacement Layer ( 3 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0894 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-02-15 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0071 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | K /11 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0072 | Installation Sleeves Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | K /11 | FDN | N/A | N/A | 2023-02-16 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0073 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | M To P / 13X To 16 | FDN | N/A | N/A | 2023-02-16 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0074 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 & B4 | RX To QZ / 30 To 33 | FDN | N/A | N/A | 2023-02-16 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0075 | Gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 35 To 38 / RY To Q | FDN | N/A | N/A | 2023-02-16 | 2023-02-18 | 2023-02-18 | 2023-02-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0076 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B1 | K / 43 | FDN | N/A | N/A | 2023-02-16 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0895 | Reinforced Concrete Piers and Walls Formwork to Level “-4.775” | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | K To RY / 16 To 13 | FDN | N/A | N/A | 2023-02-16 | 2023-02-18 | 2023-02-18 | 2023-02-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0896 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 46 To 45 / 32 To 34 | FDN | N/A | N/A | 2023-02-16 | 2023-02-20 | 2023-02-20 | 2023-02-21 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0017 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | 14 To 16 / N To L | L.G | N/A | N/A | 2023-02-16 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0897 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QX / 17 To 24 | FDN | N/A | N/A | 2023-02-18 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0018 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 5 | B5 | 18 To 23 / L To QX | L.G | N/A | N/A | 2023-02-18 | 2023-02-19 | 2023-03-05 | 2023-02-20 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0898 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 32 To 32X / G | FDN | N/A | N/A | 2023-02-18 | 2023-02-19 | 2023-02-18 | 2023-02-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0077 | Gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C3 & B3 | 33 To 34 / M To RY | L.G | N/A | N/A | 2023-02-18 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0899 | Reinforced Concrete Corbel Beam Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 38 | L.G | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-19 | 2023-02-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0900 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / QX To RX | L.G | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-19 | 2023-02-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0901 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-20 | 2023-02-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0902 | Reinforced Concrete Foundation Manholes Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 27 To 32 / RY To S | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0902 | Reinforced Concrete Foundation Manholes Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 27 To 32 / RY To S | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0078 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 & C2 | 44 To 47 / X To Z | FDN | N/A | N/A | 2023-02-19 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0078 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 & C2 | 44 To 47 / X To Z | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L
1176-FSL-CP01-CN-AT-CIR-ME-0079 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10 / R | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-20 | 2023-02-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0080 | Installation Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10 / R | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0903 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 24 To 27 / X To RX | FDN | N/A | N/A | 2023-02-20 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0904 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 42 / YY | L.G | N/A | N/A | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0905 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | A3 | 10 To 11 / L To M | FDN | N/A | N/A | 2023-02-20 | 2023-02-21 | 2023-02-21 | 2023-02-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0906 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | A3 | 10 To 11 / L To M | FDN | N/A | N/A | 2023-02-20 | 2023-02-21 | 2023-02-21 | 2023-02-22 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0907 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0908 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0909 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0910 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0911 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0912 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0913 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0019 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 12 | C3 | 36 To 38 / RX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-03-05 | 2023-02-24 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0914 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 30 To 33 / M To RY | L.G | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0915 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 45 To 47X / VX To Z | G.F | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-25 | 2023-02-24 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0915 | Reinforced Concrete Ground Slab Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 45 To 47X / VX To Z | G.F | N/A | N/A | 2023-02-26 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0916 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 13 To 18 / T To RY | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-22 | 2023-02-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0917 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0918 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0919 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0920 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0921 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 35 To 33 / 47X | FDN | N/A | N/A | 2023-02-22 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0921 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 35 To 33 / 47X | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0922 | Reinforced Concrete Duct Bank Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 39 To 41 / X To YY | -4.825 | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0081 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | Q To RY / 10X To 11 | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-26 | 2023-02-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0923 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0924 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0925 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0926 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0020 | Installation of Duct Bank Conduits as Highlighted | 00 | MEP | Elec | Elec | Duct Bank | Zone 12 | C3 | 34 To 36 / P To RX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-03-01 | 2023-02-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0021 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 12 | C4 | 38 / S To RX & V / 40X | L.G | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-03-05 | 2023-02-26 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ME-0082 | Installation Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10X To 11 / RY To Q | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-26 | 2023-02-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0927 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0928 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0929 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0930 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0931 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 39 To 42 / Z To V | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0932 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 39 To 42 / Z To V | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0933 | PVC Protection – Cartmode – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | A3 | 10 To 11 / L To M | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-26 | 2023-02-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0934 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 24 / L To Q | L.G | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0935 | Backfilling Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 12 | C3 | 35 To 37 / RX To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0936 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | A To C / 9Y To 9 | FDN To L.G | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0937 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 39X To 42 / V To Z | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0083 | Installation for Water Supply as per Highlighted | 00 | MEP | Mech | Pluming | Water Supply | Zone 5 | B5 | N To Q / 18 To 21 | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 |  | 2023-02-26 | -225 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0084 | Installation for Water Supply as per Highlighted | 00 | MEP | Mech | Pluming | Water Supply | Zone 6 | B2 | 30 To 32 / N To Q | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 |  | 2023-02-26 | -225 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0085 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 15 | B2 | L To N / 26 To 32 | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0938 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | V To Y / 47 | L.G To G.F | N/A | N/A | 2023-02-23 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0939 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | C1 & B1 | 32 To 35 / G | FDN | N/A | N/A | 2023-02-25 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0939 | Reinforced Concrete Foundation Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | C1 & B1 | 32 To 35 / G | FDN | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0940 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 32X To 34 / 45 To 47X | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0941 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | SX To CX / 10Z To 10 | FDN To L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-25 | 2023-02-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0942 | Reinforced Concrete Walls & Columns Reinforcement to Level "-4.775" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 13 / RY To S | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-25 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0943 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 46 / 32 To 34 | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0086 | Water Supply Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 5 & 6 | B2 & B5 | 18 To 32 / R To N | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-28 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0944 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 30 To 33 / M To RY | L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0945 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 32X To 28 / Q To RY | L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0946 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 11 / Q To RY | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0947 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 & B3 | 22X To 28 / K To RY | L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0948 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 15 To 18 / T To RY | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0949 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4 | SX To TX / 11 To 14 | FDN To L.G | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0950 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 4 | A3 | 10Y To 10X / M To L | FDN | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0951 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 45 To 44X / 37 To 38 | L.G | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0952 | Duct Bank Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | YY To WY / 39 To 40 | L.G | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0953 | Reinforced Concrete Lower Ground Slab Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 28 To 33 / M To RY | FDN | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0954 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 | B5 & B6 | RY To Q / 23 To 18 | S.O.G LG | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0955 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 12 To 18 / L To RY | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-27 | 2023-03-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0956 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 33 To 30 / G ToH | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0956 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 33 To 30 / G ToH | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0957 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9Y To 11 / QZ To S | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0958 | Underlayment Layer - Geotextile - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 38 To 35 / TX | L.G | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0959 | Waterproofing PVC Layer - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 38 To 35 / TX | L.G | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0960 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0961 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0962 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0963 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0964 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0965 | Reinforced Concrete Foundation ( Trenches ) Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Y To B/ Q To RY | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0966 | Construction Joint injectable Hose installation at A4-B2 Raft | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | S To QZ / 10X To 11 | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0087 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 44 / WY To YY | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0088 | Test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10Z To 11 / RY To Q | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0967 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0968 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0969 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0970 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0971 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0972 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0973 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0974 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0975 | Plain Concrete Foundation Top Level Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 34 To 36 / QX To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0976 | Reinforced Concrete Core Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 11 To 12 / M To L | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0977 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2 & B3 | 34 To 27 / L To RY | L.G | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0978 | Reinforced Concrete Lower Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B5 & B6 | 10Y To B/ K To RY | L.G | N/A | N/A | 2023-02-28 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0089 | Test for drainage pipes after Concrete Pouring as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 5 & 9 & 10 | B5 & B6 & B7 & B8 | 13 To 28 / RY To L | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0022 | Electrical Cables for Earth work as per Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 5 | B5 | L / 22X | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-05 | 2023-03-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0979 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / RX To TX | -4.60 | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-04 | 2023-03-03 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0979 | Reinforced Concrete Columns and Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / RX To TX | -4.60 | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0980 | Reinforced Concrete Reinforcement (Duct Bank) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | RY To S / 22 To 33 | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0981 | Reinforced Concrete Walls & Columns Formwork to Level "-4.775" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 13X / RY To S | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-06 | 2023-03-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0982 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 12 To 18 / L To RY | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-06 | 2023-03-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0983 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | B To EY / 5 To 8 | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-02 | 2023-03-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0090 | Installation of Drainage Pipes as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 27 / G To H | L.G | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-07 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0091 | Installation of Drainage Pipes as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 32 / H To J | L.G | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-07 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0023 | Electrical Cables Sleeves & Manhole Ineer Walls Points Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 12 | C3 | 34 To 35 / QY To RY | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-05 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0024 | Installation of Duct Bank Conduits as Highlighted | 00 | MEP | Elec | Elec | Power | Zone 12 | C3 | 34 To 35 / QY To RY | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-05 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0984 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 23 / RX To L | L.G | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0092 | Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 15 | B2 | L To N / 26 To 32 | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0985 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0986 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-03-04 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0987 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0025 | Electrical Cables for Earth work as per Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 12 | C3 & C4 | 37 To 38 / Q To RY | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | C |  |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-EL-0025 | Electrical Cables for Earth work as per Highlighted | 01 | MEP | Elec | Elec | Earthing | Zone 7 & 12 | C3 & C4 | 37 To 38 / Q To RY | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0988 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 15 | B1 | 31 To 34 / G To M | FDN | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-07 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0988 | Plain Concrete Foundation Top Level Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 6 & 15 | B1 | 31 To 34 / G To M | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0989 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4 | 21 To 23 / T | L.G | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0990 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 44X / Z | L.G To G.F | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0991 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B5-A2 | 20 To 23 / RX To L | L.G | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0992 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 22X To 28 / K To RY | L.G | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0993 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Y / R To RY | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0994 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | W / 47 | L.G To G.F | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0995 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B4 | 23 To 33 / RY To S | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0996 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 & A2 | A To C / 1 To 4X | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0997 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | B1 | 45 To 47X / 34 To 32X | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0998 | Reinforced Concrete Columns Reinforcement from Lower Ground Level to Ground | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B3-A & B4-A | 28 To 30 / Q To RY | L.G To G | N/A | N/A | 2023-03-07 | 2023-03-08 | 2023-03-07 | 2023-03-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0093 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 24 To 25 / H To G | FDN | N/A | N/A | 2023-03-07 | 2023-03-08 | 2023-03-08 | 2023-03-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0999 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / 47 | L.G | N/A | N/A | 2023-03-07 | 2023-03-08 | 2023-03-08 | 2023-03-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1000 | Reinforced Concrete Piers & Grade Beam Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 33 To 34 / 46X | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1001 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 | B2 & B5 & B6 | 28 To 21 / K To RY | L.G | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-11 | 2023-03-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1002 | Reinforced Concrete Lower Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 42 To RX / 32 To 38 | L.G | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-09 | 2023-03-10 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1002 | Reinforced Concrete Lower Slab Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 42 To RX / 32 To 38 | L.G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1003 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1004 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1005 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1006 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1007 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1008 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1009 | Reinforced Concrete Lower Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C2 | RY To L / 32X To 38 | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-13 | 2023-03-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1010 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 32X / RY To S | L.G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1011 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1012 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1013 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1014 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-13 | 2023-03-11 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1015 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-13 | 2023-03-11 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1016 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-03-09 | 2023-03-13 | 2023-03-11 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1017 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 28X To 33 / M To PX | L.G To G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1018 | Reinforced Concrete Lower Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 42 To RX / 32 To 38 | L.G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1019 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 & 3 | A1 & A3 | A To EY / 3 To 8 | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1020 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / WY To Y | L.G To G.F | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-12 | 2023-03-13 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1020 | Reinforced Concrete Walls Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / WY To Y | L.G To G.F | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-15 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1021 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-11 | 2023-03-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1022 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-11 | 2023-03-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1023 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-14 | 2023-03-13 | 2023-03-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1024 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-14 | 2023-03-13 | 2023-03-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1025 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-12 | 2023-03-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1026 | Reinforced Concrete Walls Formwork to Level "-1.62" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | RX To QZ / 38 | L.G To G.F | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1027 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-12 | 2023-03-15 | 2023-03-13 | 2023-03-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1028 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 3 To 5 / EY | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1029 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3-B & A3-A | 9Y To 10Y / 6 To 8 | S.B To L.G | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1030 | Reinforced Concrete Piers Formwork & Grade Beams | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47X To 46X / 33 To 34 | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1031 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 28 To 33 / M To QY | L.G To G | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-15 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1032 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | B To E / 3X To 6 | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1033 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A4 | B To EY / Q To S | S.B | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1034 | Reinforced Concrete Walls Formwork to Level "-3.555" | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 44X To 47 / Z | L.G | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1035 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1036 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-12 | 2023-03-15 | 2023-03-16 | 2023-03-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1037 | Underlayment Layer - Geotextile – Vertical to Level “73.225” | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 11 To 13 / M To K | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1038 | Reinforced Concrete Duct Bank Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B6 | 23 To 18 / RY | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-13 | 2023-03-15 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1039 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 28 To 33 / M To QY | L.G To G | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1040 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-15 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1041 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-13 | 2023-03-16 | 2023-03-16 | 2023-03-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1042 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | EY / 3 To 5 | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-14 | 2023-03-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1043 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | M To RY / 31X To 38 | L.G | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1044 | Waterproofing PVC Layer – Vertical to Level “73.225” | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 11 To 14 / M To J | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-14 | 2023-03-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1045 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A & B5-A | 20 To 22X / N To R | L.G To G | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1046 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | WY To YY / 44 | L.G | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1047 | Reinforced Concrete Foundation Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Z To 11 / RY To S | FDN | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1048 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To E / 3 To 4 | FDN | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1049 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | B To E / 3X To 4X | FDN | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-14 | 2023-03-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1050 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C4 | 34 To 35 / RY To TX | L.G | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-16 | 2023-03-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1051 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3-A | 39 To 42 / V To ZY | L.G | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-16 | 2023-03-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1052 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1 To 3 / D To EY | FDN | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-15 | 2023-03-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1053 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1 To 3 / D To EY | FDN | N/A | N/A | 2023-03-15 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1054 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1X To 3 / D To EY | FDN | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-15 | 2023-03-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1055 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1X To 2X / C To E | FDN | N/A | N/A | 2023-03-15 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1056 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | WX To YY / 40X To 40 | L.G To G | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-18 | 2023-03-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1057 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2-B | B To D / 2X To 4X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1058 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | B To E / 3 To 4X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-20 | 2023-03-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1059 | PVC Protection – Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | B To E / 3 To 4X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-20 | 2023-03-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1060 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1061 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-16 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1062 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1 To 3 / C To D | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-16 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1063 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1 To 3 / C To D | FDN | N/A | N/A | 2023-03-16 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1064 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 11 To 16 / L To SY | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1065 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To E / 1X To 3X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-16 | 2023-03-19 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1066 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C4 | 34 To 35 / RY To TX | FDN To L.G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1067 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B5 & B4 | 22X To 20 / L To RX | L.G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1068 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 & C1 | M To PX / V To WY | L.G To G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1069 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 44 / Y To WY | L.G To G.F | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1070 | Reinforced Concrete Walls Reinforcement to Level “72.75” | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | A / 9 To 9X | S.B To L.G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0094 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / H To G | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-22 | 2023-03-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1071 | Backfilling Layer ( 1 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 13X / RY To J | FDN | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-18 | 2023-03-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1072 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4-B & B2-B | 31 To 23 / RY To SY | FDN | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1073 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1074 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-18 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1075 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | ZY To 37 / 40 To 39 | L.G To G.F | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1076 | Reinforced Concrete Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | VX To ZY / 47 To 47X | G.F | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1077 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 22X / RX To L | L.G To G | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1078 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B4-A | 22X / RX To L | L.G To G | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1079 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B4-A | 23 To 26 / L To R | L.G To G | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-21 | 2023-03-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1080 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 24 / H | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1081 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1082 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-19 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1083 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1X To 3X / 9Y To 10 | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1084 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 33 To 37 / RX To PX | L.G | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1085 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 22X / L | L.G To G | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1086 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47 To 47X / ZY To V | G.F | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-22 | 2023-03-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1087 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C3 | 33 To 36 / RY | L.G | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1088 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 33 To 30 / G To H | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1089 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 29 To 33 / G To H | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1090 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B4 & B6 | 20 To 24 / RY To S | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1091 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 13X / RY To J | FDN | N/A | N/A | 2023-03-19 | 2023-03-22 | 2023-03-25 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1092 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-20 | 2023-03-23 | 2023-03-25 | 2023-03-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1093 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-21 | 2023-03-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1094 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 16 / RY To J | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-25 | 2023-03-22 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1094 | Backfilling Layer ( 2 ) Level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 16 / RY To J | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1095 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 11 To 16 / RY To T | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-20 | 2023-03-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1096 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-20 | 2023-03-23 | 2023-03-25 | 2023-03-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1097 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | RX / 37 To 35 | L.G To G | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-20 | 2023-03-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0095 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | 22X To 28X / M To G | FDN | N/A | N/A | 2023-03-20 | 2023-03-22 | 2023-03-22 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1098 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | EY To A / 2X To 6 | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-21 | 2023-03-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1099 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | D To C / 3X To 2 | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-21 | 2023-03-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1100 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | D To C / 3X To 2 | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-22 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1101 | Backfilling Layer ( 1 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1102 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-25 | 2023-03-28 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1103 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1104 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-25 | 2023-03-25 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1105 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3 To 2 / D To E | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1106 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C3 | 33 To 36 / RY | L.G | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1107 | PVC Protection - Surface Preparation Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3X To 2 / C To D | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1108 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | X To Y / 39 | L.G | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1109 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3 To 2 / D To EY | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-22 | 2023-03-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0096 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28X / J To G | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-22 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0097 | Walls Opening Sleeves Locations as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | RY / 28 To 32X | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-25 | 2023-03-23 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0097 | Walls Opening Sleeves Locations as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | RY / 28 To 32X | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1110 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | RX / 37 To 35 | L.G To G | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1111 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B4-A | 23 To 26 / L To R | L.G To G.F | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1112 | Ground Slab Openings Coordinates Locations | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 43 To 47 / U To Z | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-25 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1113 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 11 / R To RY | S.B | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-25 | 2023-03-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1114 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3 To 2 / D To EY | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1115 | Reinforced Concrete Columns Reinforcement to L.G | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3 & A4 | 9Y To 10 / P To QZ | L.G | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1116 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | Q To RY / 38 | L.G To G.F | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1117 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | B To E / 4X To 6 | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1118 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 35 To 33 / 47X | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-26 | 2023-03-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1119 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | QZ / WX | L.G To G.F | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1120 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | 39 / 34 To 35 | L.G To G.F | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0098 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / K To H | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-29 | 2023-03-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1121 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-25 | 2023-03-25 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1122 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-27 | 2023-03-28 | 2023-03-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1123 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-25 | 2023-03-25 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1124 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-27 | 2023-03-28 | 2023-03-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1125 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 32X To 33 / RY To R | L.G To G | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1126 | Reinforced Concrete Walls Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | 34 To 28 / RY | L.G To G | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1127 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 24 To 26 / M To N | L.G To G | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1128 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 4 / B To EY | FDN | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1129 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | WY To YY / QX | L.G To G.F | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0099 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28X / J To G | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-04-06 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1130 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 12 To 11 / L To RY | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1131 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | SX To TX / 34 To 35 | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1132 | Reinforced Concrete Columns & Walls Piers Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | G To H / 30 To 32X | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0026 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 9 & 10 | B6 & B8 | 11 To 20 / RY To S | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-29 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1133 | Reinforced Concrete Columns Formwork up to L.G Level ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 | 6 To 8 / CY To B | S.B To L.G | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0100 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23 To 28 / J To H | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-27 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0101 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / J To G | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-27 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0102 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23X To 28 / G To H | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-27 | 2023-03-28 | DONE | B |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0102 | Test for Drainage Pipes | 01 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23X To 28 / G To H | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0102 | Test for Drainage Pipes | 02 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23X To 28 / G To H | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0103 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-04-06 | 2023-03-28 | DONE | B |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0103 | Test for Drainage Pipes | 01 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0103 | Test for Drainage Pipes | 02 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1134 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-28 | 2023-03-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1135 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1136 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-28 | 2023-03-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1137 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1138 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-28 | 2023-03-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1139 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-03-27 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1140 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 11 | N/A | 24 To 26 / M To N & 32X / RX | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-27 | 2023-03-29 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1141 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | QZ / WX | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-27 | 2023-03-29 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0027 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 15 | B1 | 27 To 31 / 45 To 47 | L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-10 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0028 | Installation and Fixation Duct Bank Conduits ( First Fix ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 5 | B5 | 9Y / 18 To 20 | L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-10 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1142 | Reinforced Concrete Piers and Walls Reinforcement to ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32X / G To H | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-30 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1143 | Reinforced Concrete Piers and Walls Formwork to ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32X / G To H | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1144 | Reinforced Concrete Walls Reinforcement to L.G Level ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Y To 11 / QX To S | S.B To L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1145 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 23 To 21 / RY To T | L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-28 | 2023-03-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1146 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX | L.G To G.F | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-29 | 2023-03-30 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1146 | Reinforced Concrete Walls Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX | L.G To G.F | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-08 | 2023-04-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0104 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 26 To 28 / H To N | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-04-05 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1147 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 23 To 28 / N To TY | L.G To G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-29 | 2023-03-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1148 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1149 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1150 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1151 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1152 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 9X To 8 / A | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1153 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1154 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1155 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1156 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1157 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 14 / K To H | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1158 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 14 / K To H | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-03 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1159 | Reinforced Concrete Walls Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 24 To 26 / R | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-29 | 2023-03-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1160 | Reinforced Concrete Walls Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 25 To 26 / N To P | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0029 | Electrical Cables SLeeves locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 3 | A4 | 11 / RY To S | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1161 | Ground Slab Formwork Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 42 To 45 / U To Z | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-30 | 2023-03-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1162 | Reinforced Concrete Ground Slab formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 45 To 43 / Z TO V | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-30 | 2023-03-31 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1162 | Reinforced Concrete Ground Slab formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 45 To 43 / Z TO V | G.F | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-01 | 2023-04-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1163 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-A | 23 To 26 / QX To RX | L.G To G.F | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-03-30 | 2023-04-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1164 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1165 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-03 | 2023-04-03 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1166 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1167 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-03 | 2023-04-03 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1168 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 9Y To 9 / A | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1169 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To H | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1170 | Reinforced Concrete Slab Bottom Layer and Beams Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 47 To 45 / VX To ZY | L.G | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0105 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | 25 To 28 / J To G | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0106 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | 22X To 28 / G To J | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-12 | 2023-04-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1171 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | RX To Q / 38 | L.G To G.F | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1172 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 20 To 28 / RY To SY | L.G | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1173 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | 4X To 6 / A To EY | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1174 | PVC Protection – Cartmode – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 9Y To 9 / A | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1175 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | N/A | 11 To 14 / TX | S.B To L.G | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1176 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | 4X To 6 / A To EY | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0107 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 15 To 16 / L To PX | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-06 | 2023-04-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1177 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1178 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-05 | 2023-04-06 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1179 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1180 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-05 | 2023-04-06 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1181 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 22 To 28 / RY To T | L.G | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | B | L |  |  | Wafaa Adly & Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1182 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Y To 12 / SX To QX | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-05 | 2023-04-04 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1182 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Y To 12 / SX To QX | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0108 | Installation and Test for Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 14 To 16 / L To Q | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-05 | 2023-04-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1183 | Construction Joint injectable Hose installation at A2 Raft | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / E To A | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1184 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-04 | 2023-04-04 | 2023-04-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1185 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-07 | 2023-04-06 | 2023-04-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1186 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-04 | 2023-04-04 | 2023-04-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1187 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-07 | 2023-04-06 | 2023-04-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1188 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1189 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1190 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1191 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1192 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1193 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1194 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1195 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1196 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 45 To 43 / V To Y | G.F | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-05 | 2023-04-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1197 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1198 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1199 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1200 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1201 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1202 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1203 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1204 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1205 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-B | 20 To 28 / RY To SY | L.G | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1206 | Reinforced Concrete Walls Formwork to Level "-0.85" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 28 To 33 / RY | L.G To G | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-08 | 2023-04-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1207 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1208 | Reinforced Concrete Walls Formwork to Level "-0.875" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B3-A | 32X To 33 / RY To R | L.G | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1209 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-B | 10Y To 11 /QX | L.G | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1210 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 25 To 26 / PX To N | L.G | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1211 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 2 To 4X / B To EY | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1212 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 15 / RY To S | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1213 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1214 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-08 | 2023-04-16 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1215 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1216 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-08 | 2023-04-16 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1217 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | PX TO QZ / 38 | L.G | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-09 | 2023-04-09 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1218 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A2 | EY / 2X To 2 | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1219 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | G To H / 26 To 28 | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-09 | 2023-04-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1220 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9 To 9X / 9Y | S.B To L.G | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1221 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10 / RY | S.B To L.G | N/A | N/A | 2023-04-08 | 2023-04-12 | 2023-04-12 | 2023-04-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0109 | Installation for Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / H To J | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-12 | 2023-04-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0110 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-08 | 2023-04-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1222 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-08 | 2023-04-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1223 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-08 | 2023-04-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1224 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3 | 10X / RY | L.G | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-08 | 2023-04-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1225 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1226 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1227 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 36 To 38 / 45 To 43 | G.F | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-09 | 2023-04-10 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1227 | Reinforced Concrete Slab Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 36 To 38 / 45 To 43 | G.F | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-11 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1228 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1229 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 16 To 18 / RY To L | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1230 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1231 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1232 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To E / 1X To 4 | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-09 | 2023-04-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0111 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / H To J | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-12 | 2023-04-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1233 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1234 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1235 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1236 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1237 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 16 To 18 / RY To L | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1238 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1239 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0112 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 33 To 35 / TX To RY | FDN | N/A | N/A | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0113 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B8 | 13 To 21 / RY To S | FDN | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0114 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | N/A | N/A | Zone 12 | C2 | 34 To 38 / RY To RX | L.G | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-12 | 2023-04-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1240 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 41 To 42 / 38 | FDN | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-11 | 2023-04-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1241 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | 11 To 14 / TX | FDN | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-11 | 2023-04-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-EL-0030 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 15 | B1 | 23 To 27 / 46X | L.G | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-05-10 | 2023-04-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1242 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-12 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1243 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-15 | 2023-04-18 | 2023-04-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1244 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1245 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-15 | 2023-04-18 | 2023-04-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1246 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 4 to 2X / A To C | FDN | N/A | N/A | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-04-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1247 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 31 To 33 / RY To SY | L.G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1248 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 28 To 33 / RY To SY | L.G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0115 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B6 & B8 | 16 To 18 / S To RY | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-15 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1249 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 28 To 33 / RY To SY | L.G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1250 | Slab ( Boundaries - Levels & Offset For Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | J To P / 33 To 38 | G.F | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-18 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0116 | Ground Slab Openings Pointes Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C1 | J To P / 33 To 38 | G.F | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1251 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1252 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1253 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1254 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1255 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B8 & B7 | 16 To 18 / RY To L | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1256 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | V To VX / 47 | L.G To G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1257 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X / RY | S.B To L.G | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1258 | PVC Protection – Cartmode to Level ( -4.775 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 & 9 | A4-B | 10 / 13X | S.B To L.G | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1259 | RC Walls Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 3 | A4 | SX To Q / 10Y To 11 | FDN | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1260 | Reinforced Concrete Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 43 To 47 / V To ZY | G.F | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-15 | 2023-04-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1261 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1X To 4X / 1Z To EY | FDN | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1262 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | CY To EY / 2 To 4X | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-15 | 2023-04-17 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1263 | Construction Joint injectable Hose installation at A1 Raft | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 | 4X To 5 / E To A | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-15 | 2023-04-17 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1264 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 22X To 28X / G To L | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1265 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 22X To 28X / G To L | FDN | N/A | N/A | 2023-04-15 | 2023-04-18 | 2023-04-18 | 2023-04-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1266 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22X To 28X / G To L | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1267 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10 / RY | S.B To L.G | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1268 | Plain Concrete Foundation Top Level & Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 23 To 25 / H To J | FDN | N/A | N/A | 2023-04-16 | 2023-04-17 | 2023-04-16 | 2023-04-18 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1269 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 & B8 | 15 To 21 / RY To T | FDN | N/A | N/A | 2023-04-16 | 2023-04-17 | 2023-04-16 | 2023-04-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1270 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | SY To TX / 13X To 14 | FDN | N/A | N/A | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1271 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-16 | 2023-04-18 | 2023-04-18 | 2023-04-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1272 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 28 To 33 / SY To RY | L.G | N/A | N/A | 2023-04-17 | 2023-04-18 | 2023-04-18 | 2023-04-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1273 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | B1 | 33 To 35 / 47 To 46X | FDN | N/A | N/A | 2023-04-29 | 2023-04-30 | 2023-04-29 | 2023-05-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1274 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-04-29 | 2023-04-30 | 2023-04-29 | 2023-05-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1275 | RC Stair Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 12 To 13X / M To N | FDN | N/A | N/A | 2023-04-29 | 2023-04-30 | 2023-04-30 | 2023-05-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1276 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | B1 | 32X To 35 / 45 To 47 | FDN | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-02 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1277 | PVC Protection – Cartmode – Vertical to Level “-4.155” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 41 To 42 / 38 | FDN | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1278 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1279 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-01 | 2023-05-04 | 2023-05-04 | 2023-05-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1280 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5-B & B4-B | RY To SY / 16 To 22 | L.G | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1281 | RC Walls Waterproofing Bitumen to "-4.775" | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | SY To RY / 11 To 13 | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1282 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 33 To 38 / G To P | G.F | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1283 | Reinforced Concrete Walls Reinforcement to Level "-0.075" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 34 To 38 / RY To RX | L.G To G | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1284 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 11 To 12 / K To RY | FDN | N/A | N/A | 2023-05-01 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1285 | Reinforced Concrete Stair Pedestal Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 12 To 13 / M | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1286 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To EY / 1 To 5 | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1287 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | B7 & A3 | 10 To 11 / M To K | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1288 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | B7 & A3 | 10 To 11 / M To K | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1289 | RC Manholes Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B2-B & B4-B | 22 To 32X / RY To S | L.G | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1290 | Reinforced Concrete Walls & Columns Reinforcement to Level "-5.825" | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / A To B | FDN | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1291 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1292 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-06 | 2023-05-08 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1293 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1294 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-06 | 2023-05-08 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1295 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 23 To 28 / RX To QZ | L.G To G.F | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-06 | 2023-05-04 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1296 | RC Lower Ground Slab Reinforcement Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RX To RY | L.G | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1297 | Reinforced Concrete Columns Formwork to L.G Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X / RY | S.B To L.G | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-05-04 | 2023-05-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1298 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-05 | 2023-05-03 | 2023-05-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1299 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1300 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-05-03 | 2023-05-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1301 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1302 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 | N/A | 16 To 18 / K To RY | L.G | N/A | N/A | 2023-05-03 | 2023-05-07 | 2023-05-08 | 2023-05-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1303 | Reinforced Concrete Stair Pedestal Formwork to Level "-4.775" | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 12 To 13 / M | FDN To L.G | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-05-04 | 2023-05-05 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1304 | Reinforced Concrete Columns Reinforcement to Level "-6.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | B To E / 5 | L.G | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-06 | 2023-05-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1305 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | Y To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-08 | 2023-05-07 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1305 | Reinforced Concrete Walls Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | Y To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1306 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1X To 3 / 10X To 10 | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1307 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1308 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1309 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1310 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-07 | 2023-05-09 | 2023-05-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1311 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-07 | 2023-05-09 | 2023-05-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1312 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-06 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1313 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-06 | 2023-05-10 | 2023-05-09 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1314 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-06 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1315 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | B To E / 5 | FDN | N/A | N/A | 2023-05-06 | 2023-05-07 | 2023-05-06 | 2023-05-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1316 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 34 To 35 / SX To TX | FDN | N/A | N/A | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1317 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-06 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1318 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-07 | 2023-05-10 | 2023-05-09 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1319 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1320 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-07 | 2023-05-10 | 2023-05-09 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0117 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C2-A | 35 To 37 / RY To S | L.G | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0031 | Installation and Fixation Conduits for Earthing System (First Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 15 | B1 | 27 To 28 | L.G | N/A | N/A | 2023-05-07 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0032 | Installation and Fixation UPVC FOR Duct Bank Conduits ( First Fix ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 9 | B8 | 16 TO 18 / SX To TX | L.G | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-11 | 2023-05-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0033 | Installation and Fixating Earthion Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 14 | B1 | 22X To 23 / G To H | L.G | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-10 | 2023-05-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1321 | Reinforced Concrete Stair Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10Z / SY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1322 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1323 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1324 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | E To EY / 2 To 4X | FDN To L.G | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1325 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1326 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1327 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1328 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0118 | Water Supply Pipes Locations ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 14 | B1 | 22X To 25 / H To G | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1329 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1330 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1331 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | V To Z / 43 To 47 | G.F To 1st | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-13 | 2023-05-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1332 | Reinforced Concrete Walls & Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | S To SY / 23 To 32X | L.G To G | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1333 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1334 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1335 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | 6 To 7 / C To D | S.B To L.G | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-13 | 2023-05-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1336 | Reinforced Concrete Stair Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Z To 10X / RY To S | S.B | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1337 | Reinforced Concrete Stair Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Z To 10X / RY To S | S.B | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1338 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1339 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1340 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / G To H | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0034 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 9 | B6 | 16 To 18 / RY To S | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0035 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 11 | A1-A & A1-B | 1 To 6 / A & EY | L.G | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0036 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 8 | C1 & C2 | U To Z / 43 & 47 | G To MEZZ | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0037 | Installation and Fixation Conduits and Boxes for Access Control System (Second Fix) | 00 | MEP | Elec | Elec | Access Control | Zone 2 & 10 & 12 | A3 & B4 & C4 | (10X To 11 / RY To QX) (27 To 28 / RX) (T To QX / 38) | L.G | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1341 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | 13X To 14 / SY To TX | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1342 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1343 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-10 | 2023-05-14 | 2023-05-11 | 2023-05-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1344 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 34 To 38 / RX To RY | L.G | N/A | N/A | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1345 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | 13X To 14 / SY To TX | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-13 | 2023-05-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1346 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1347 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-14 | 2023-05-13 | 2023-05-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1348 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1349 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-14 | 2023-05-13 | 2023-05-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1350 | Reinforced Concrete Lower Ground Slab Axis and Boundaries Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Z / 9 To 9X | L.G | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1351 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 | N/A | L To RY / 18 To 16 | L.G | N/A | N/A | 2023-05-11 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1352 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | E To EY / 2 To 4X | FDN To L.G | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1353 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1-B | E To EY / 4 To 5 | FDN | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0119 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A3-B | 10 To 10Y / Q To RY | L.G | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-15 | 2023-05-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1354 | Reinforced Concrete Duct Bank Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 | 20 To 16 / RY | FDN | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-13 | 2023-05-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1355 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | Q To QZ / 37 To 38 | L.G To G.F | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1356 | Reinforced Concrete Columns Formwork to L.G Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | S To 23 / 32X | L.G To G | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1357 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 3 | A4 & A1 | E To EY / 4 To 5 | FDN | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1358 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9 To 9X / A To C | L.G | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1359 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 14 & 15 | N/A | 23 To 28 / G To K | L.G | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-16 | 2023-05-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1360 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 3 | A4 & A1 | E To EY / 4 To 5 | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1361 | Reinforced Concrete Walls Reinforcement to Level "-1.80 | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5 | 16 To 18 / SY To TX | L.G To G.F | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1362 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A3 | C To EY / 2 To 4X | S.B To L.G | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-15 | 2023-05-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1363 | Underlayment Layer - Geotextile to Level ( -7.86 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / A | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1364 | Waterproofing PVC Layer to Level ( -7.86 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / A | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-16 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1365 | PVC Protection – Cartmode to Level ( -7.86 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / A | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-17 | 2023-05-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1366 | Reinforced Concrete Lower Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 | B5-A | K To RY / 16 To 21 | L.G | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-15 | 2023-05-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1367 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 23 To 16 / RY To SY | L.G | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-15 | 2023-05-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1368 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1369 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1370 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1371 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1372 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1373 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1374 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-16 | 2023-05-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1375 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-17 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0120 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 1 & 2 | A1 | 2X To 4X / B | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0121 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 1 & 2 | A1 | 2X To 4X / B | FDN | N/A | N/A | 2023-05-15 | 2023-05-22 | 2023-05-23 | 2023-05-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0122 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | T To TX / 38 | L.G | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1376 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B3 | 23 To 25 / G To H | L.G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1377 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-05-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1378 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-05-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1379 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3 | RX To QX / 10 To 10Y | L.G To G.F | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1380 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1381 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1382 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1383 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1384 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | S To RX / 33 To 35 | L.G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1385 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | RY To S / 35 To 38 | L.G To G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1386 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-17 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1387 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-17 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0123 | Water Supply Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 4 & 5 | B5-A | 16 To 18 / RY To P | L.G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1388 | Reinforced Concrete Foundation ( Starter Bar ) Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | A To E / CZ To 5 | FDN | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1389 | Reinforced Concrete Walls & Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | TX To RY / 38 | L.G To G | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-05-18 | 2023-05-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0038 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 2 | A1 | A To B / 3X To 4 | FDN | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-05-18 | 2023-05-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1390 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1-A | CZ To 4X / E To A | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1391 | Reinforced Concrete Lower Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5-B | SY To RY / 16 To 22 | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1392 | Ground Slab Formwork Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 35 To 38 / RY To M | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-18 | 2023-05-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1393 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5-B | RY To SY / 23 To 16 | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-18 | 2023-05-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1394 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1395 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1396 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1397 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-22 | 2023-05-20 | 2023-05-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1398 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-22 | 2023-05-20 | 2023-05-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1399 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-22 | 2023-05-20 | 2023-05-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1400 | Reinforced Concrete Slab Reinforcement ( Shrinkage Strep ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 27 To 28 / M To RY | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-22 | 2023-05-21 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1400 | Reinforced Concrete Slab Reinforcement ( Shrinkage Strep ) | 01 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 27 To 28 / M To RY | L.G | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-30 | 2023-05-31 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0124 | Ground Slab Opening Locations as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 12 | C2 | 34 To 38 / RY To K | G.F | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-18 | 2023-05-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1401 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | Y To W / 45 To 46 | G.F | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-21 | 2023-05-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1402 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-21 | 2023-05-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1403 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1404 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-21 | 2023-05-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1405 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1406 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10Y / RX To QX | S.B To L.G | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-23 | 2023-05-22 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1406 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10Y / RX To QX | S.B To L.G | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0125 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 1 | A1 | A To E / 1 To 4 | FDN | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-23 | 2023-05-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0126 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 1 | A1 | A To E / 1 To 4 | FDN | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1407 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-A | CZ To 4 / E To A | FDN | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1408 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B5-A & B5-B | 16 To 22 / J To T | L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-21 | 2023-05-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1409 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | 2X To 4X / 1 To CY | FDN | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-21 | 2023-05-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1410 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A | 23 To 28 / G To K | L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-27 | 2023-05-23 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1410 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A | 23 To 28 / G To K | L.G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1411 | Reinforced Concrete Walls Reinforcement to Level "-0.85" | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | 23 To 33 / T To SY | L.G To G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1412 | Underlayment Layer - Geotextile for Wall and Corbel | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN To L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1413 | Waterproofing PVC Layer for Wall and Corbel | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN To L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1414 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | 41 / Z | L.G To G.F | N/A | N/A | 2023-05-22 | 2023-05-23 | 2023-05-22 | 2023-05-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1415 | Reinforced Concrete Walls & Columns Formwork to Level "-1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 28 To 33 / T To TX | L.G To G.F | N/A | N/A | 2023-05-22 | 2023-05-23 | 2023-05-23 | 2023-05-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0127 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0128 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 33 To 35 / SX To TX | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0129 | Water Supply Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 11 | B4 | 34 To 35 / SY To TX | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0130 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1416 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1417 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1418 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1419 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1420 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1421 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1422 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1423 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1424 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1425 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1426 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1427 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1428 | Reinforced Concrete Walls Formwork Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1429 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1430 | Reinforced Concrete Lower Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 14 & 15 | N/A | 23 To 28 / M To G | FDN | N/A | N/A | 2023-05-24 | 2023-05-25 | 2023-05-27 | 2023-05-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1431 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 43 To 47 / V To ZY | G.F To 1st | N/A | N/A | 2023-05-24 | 2023-05-25 | 2023-05-25 | 2023-05-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0131 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 32X To 35 / RY To TY | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0039 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 11 & 12 | B4 | 33 To 34 / S To TX | FDN | N/A | N/A | 2023-05-24 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1432 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 43 To 39 / Z To X | G.F | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-25 | 2023-05-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1433 | Reinforced Concrete Lower Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1434 | Reinforced Concrete Lower Ground Slab Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9 To 9X / 9Y To 10X | L.G | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1435 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1436 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1437 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1438 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1439 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1440 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-25 | 2023-05-29 | 2023-05-27 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1441 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-27 | 2023-05-30 | 2023-05-29 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1442 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-27 | 2023-05-30 | 2023-05-29 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1443 | Reinforced Concrete Piers & Walls Coordintes | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 4 /A To E | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1444 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | N/A | 22 To 18 / M To S | L.G To G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-27 | 2023-05-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1445 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1446 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-27 | 2023-05-30 | 2023-05-29 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1447 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1448 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1449 | Construction joint fuko hose Injection | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3-A & A3-B | 49 To 11 & 5 To 9X | FDN To L.G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | C | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1450 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | H To G / 29 To 32 | L.G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1451 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-29 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1452 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-06-01 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1453 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 35 To 38 / L To RY | G.F | N/A | N/A | 2023-05-28 | 2023-05-29 | 2023-05-31 | 2023-05-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1454 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-29 | 2023-05-31 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1455 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-30 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1456 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-29 | 2023-05-31 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1457 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-29 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1458 | Reinforced Concrete Lower Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / SX To TX | L.G | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1459 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1460 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1461 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1462 | Backfilling Layer ( 14 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1463 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1464 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1465 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1466 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1467 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9X To 9 / A To C | L.G | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-30 | 2023-05-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1468 | Reinforced Concrete Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 | N/A | 30 To 35 / K To RX | G.F | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1469 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-29 | 2023-06-12 | 2023-06-15 | 2023-06-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1470 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1471 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1472 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1473 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1474 | Ground Slab Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | N/A | 30 To YY / 43 To S | G.F | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1475 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1476 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1477 | Reinforced Concrete Ground Slab Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10 To 11 / TX To SX | L.G | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1478 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 31 To 36 / J To S | G.F | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1479 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1480 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1481 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1482 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1483 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1484 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1485 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-05-31 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1486 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-01 | 2023-06-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1487 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RY To TX | L.G To G.F | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1487 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RY To TX | L.G To G.F | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-03 | 2023-06-04 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1488 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 | N/A | M To RY / 18 | L.G To G.F | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1489 | Reinforced Concrete Walls Formwork to Level (-108) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 16 To 18 / SY To TX | FDN To L.G | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1490 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-B | T To SY / 23 To 28 | L.G | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-05 | 2023-06-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1491 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-04 | 2023-06-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1492 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-06 | 2023-06-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1493 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-06 | 2023-06-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1494 | Wall Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4 | 25 To 28 / RY | FDN | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1495 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 16 / RY To S | FDN | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-04 | 2023-06-04 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1496 | Reinforced Concrete Walls Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4 | 23 To 24 / RY | L.G To G.F | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-04 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1497 | Reinforced Concrete Columns Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 36 To 32 / TX To T | L.G To G.F | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-04 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0132 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 9 | B7 & B8 & A4 | 10Y To 14 / PX To RY | FDN | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-08 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1498 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-06-01 | 2023-06-05 | 2023-06-06 | 2023-06-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1499 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-06-01 | 2023-06-12 | 2023-06-13 | 2023-06-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1500 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 11 / SX To RY | L.G | N/A | N/A | 2023-06-03 | 2023-06-04 | 2023-06-04 | 2023-06-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1501 | Reinforced Concrete Lower Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Z To 11 / SX To RY | L.G | N/A | N/A | 2023-06-03 | 2023-06-04 | 2023-06-04 | 2023-06-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1502 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | TX To RY / 38 | L.G To G.F | N/A | N/A | 2023-06-03 | 2023-06-04 | 2023-06-04 | 2023-06-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0133 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 9 | B7 & B8 & A4 | 10Y To 14 / PX To RY | FDN | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-08 | 2023-06-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1503 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-04 | 2023-06-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1504 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-04 | 2023-06-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1505 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-07 | 2023-06-06 | 2023-06-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1506 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-07 | 2023-06-06 | 2023-06-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1507 | Reinforced Concrete Walls and Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | SY To RY / 23 To 16 | L.G To G.F | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-05 | 2023-06-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1508 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | S To RY / 38 | FDN To L.G | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-05 | 2023-06-06 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1509 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | D To A / 1X To 3X | FDN To L.G | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-07 | 2023-06-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1510 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | D To A / 1X To 3X | FDN To L.G | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-07 | 2023-06-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0134 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-06-04 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0135 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-10 | 2023-06-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0136 | Wall Opening Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B5-B | 16 To 18 / RY To SY | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1511 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B5-B | RX To PX / 18 | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-06-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1512 | Ground Slab Openings Points Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 37 To 38 / L To QX | G.F | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1513 | Reinforced Concrete Ground Slab ( Boundaries - Levels & Offset For Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 35 To 38 / L To QX | G.F | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1514 | Reinforced Concrete Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 35 To 38 / L To QX | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1515 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-06-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1516 | Backfilling Layer ( 15 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1517 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-06-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1518 | Backfilling Layer ( 16 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1519 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9 To 9X / A To C | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-08 | 2023-06-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1520 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1521 | Reinforced Concrete Duct Bank Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B7 & B8 | 11 To 16 / RY To S | FDN | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-06-06 | 2023-06-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1522 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9 To 9X / A To C | L.G | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-06-07 | 2023-06-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0137 | Test After Concrete Pouring for the Drainage Network | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0138 | Puddle Flange Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A2 & A3 | A To EY / 5 To QY | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0138 | Puddle Flange Locations & Levels ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A2 & A3 | A To EY / 5 To QY | FDN | N/A | N/A | 2023-06-19 | 2023-06-21 | 2023-06-20 | 2023-06-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1523 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | N/A | G To L / 24 To 27 | L.G To G | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-07 | 2023-06-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1524 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1525 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1526 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1527 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1528 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 23 / L | L.G | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1529 | Plan Concrete Duct Bank Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 15 To 16 / RY To S | FDN | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1530 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 14 | B3 | 22X To 28 / G To M | L.G | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1531 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 22 To 18 / QX To S | L.G To G | N/A | N/A | 2023-06-10 | 2023-06-11 | 2023-06-11 | 2023-06-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1532 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 37 To S / 36 To S | FDN | N/A | N/A | 2023-06-10 | 2023-06-11 | 2023-06-13 | 2023-06-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0139 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B8 | 11 To 16 / RY To T | FDN | N/A | N/A | 2023-06-10 | 2023-06-11 | 2023-06-11 | 2023-06-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0140 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-06-11 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0141 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B8 | 11 To 16 / RY To T | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-20 | 2023-06-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1533 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1534 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1535 | Reinforced Concrete Oil Interceptor pit ( Slab & Walls ) Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 34 To 35 / SX To SY | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-12 | 2023-06-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0142 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 9 | B7 & B8 & A4 | 10Y To 14 / PX To RY | FDN | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-20 | 2023-06-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1536 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 18 To 23 / RY | L.G To G.F | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1537 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | N/A | 30 To 36 / N To G | L.G | N/A | N/A | 2023-06-12 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1538 | Reinforced Concrete Oil Interceptor pit Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 33 To 34 / RY To S | FDN | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1539 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Z To 11 / RY To SX | L.G | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-13 | 2023-06-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1540 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-12 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1541 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-12 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1542 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | M To RY / 35 To 38 | G.F | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1543 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / Z | L.G | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1544 | Wall Openings Location & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | B2-B | RY To TX / 35 | L.G | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1544 | Wall Openings Location & Level | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | B2-B | RY To TX / 35 | L.G | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1545 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 / L | FDN | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-17 | 2023-06-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1546 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 24 To 26 / G To L | L.G To G.F | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1547 | Backfilling Layer ( 17 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1548 | Backfilling Layer ( 18 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1549 | Backfilling Layer ( 17 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-15 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1550 | Backfilling Layer ( 18 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-15 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1551 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 11 To 17 / RY To SY | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-14 | 2023-06-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1552 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1553 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | RY To RX / 38 | FDN To L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-14 | 2023-06-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1554 | Reinforced Concrete Lower Ground Slab Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 10Y / SX To RY | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1555 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 11 / RY To SX | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1556 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 36 To 37 / RY To S | L.G To G.F | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-14 | 2023-06-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1557 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1558 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1559 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1560 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1561 | Reinforced Concrete Walls & Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 23 To 28 / RY | L.G To G.F | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1562 | Reinforced Concrete Lower Ground Slab Reinforcement ( Shrinkage Strip ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B2-A | 27 To 28 / RY To SY | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1563 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1564 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1565 | Reinforced Concrete Walls Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 11 / TX To T | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-18 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1566 | Construction Joint injectable Hose installation for Sub_basement Walls | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | A / 4X To 6 | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-17 | 2023-06-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1567 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2-A | A / 4X To 6 | FDN To LG | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-17 | 2023-06-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1568 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 11 / RY To S | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1569 | Reinforced Concrete Slab Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 10Y / RY To S | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-15 | 2023-06-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0040 | Duct Bank Pipes locations & Levels ( Survey Inspection ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 9 & 10 & 11 | B4 | 11 To 35 / RX To S | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-15 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0041 | Installation of Electrical Cables Conduits | 00 | MEP | Elec | Elec | Power | Zone 2 | A1 | A To B / 3X To 4 | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0042 | Installation of Electrical Cables Conduits | 00 | MEP | Elec | Elec | Power | Zone 11 & 12 | B4 | 33 To 34 / S To TX | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0043 | Installation of Duct Bank Conduits | 00 | MEP | Elec | Elec | Duct Bank | Zone 9 & 10 & 11 | B4 | 11 To 35 / RX To S | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0044 | Installation and Fixating Earthion Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | L / 11 | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0045 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | N / 12 | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0046 | Installation and Fixation Conduits for Access Control System | 00 | MEP | Elec | Elec | Access Control | Zone 12 | C4 | T To S / 35 To 36 | S.B To L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1570 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | RY To RX / 38 | FDN To L.G | N/A | N/A | 2023-06-17 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1571 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-06-17 | 2023-06-18 | 2023-06-20 | 2023-06-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0047 | Duct Bank Manhole Location & Level ( Survey Inspection ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 11 & 12 | B3 | 34 To 35 / RY To S | L.G | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-18 | 2023-06-20 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1572 | Reinforced Concrete Slab Bottom Layer Reinforcement & Beams | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 36 To 31 / RY To K | G.F | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-21 | 2023-06-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1573 | Reinforced Concrete Columns Reinforcement to Level "-1.11" | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 / K | L.G To G.F | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-18 | 2023-06-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1574 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9Y To 10Z / 9X To 9 | L.G | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1575 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1576 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0143 | Test After Concrete Pouring for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0144 | Test After Concrete Pouring for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 32 / H To G | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1577 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-19 | 2023-06-22 | 2023-06-21 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1578 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-19 | 2023-06-22 | 2023-06-21 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1579 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 26 To 28 / QY To RY | L.G To G.F | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-19 | 2023-06-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1580 | Reinforced Concrete Duct Bank Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 35 / S To RX | FDN | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-20 | 2023-06-21 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1581 | Reinforced Concrete Walls Reinforcement from "74.95" To "76.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9Y To 10X / T To TX | L.G To G.F | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-24 | 2023-06-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1582 | Reinforced Concrete Columns Reinforcement to Level "-1.11" | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 16 / K To J | L.G To G.F | N/A | N/A | 2023-06-20 | 2023-06-21 | 2023-06-20 | 2023-06-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1583 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | 3 / C To D | FDN | N/A | N/A | 2023-06-20 | 2023-06-21 | 2023-06-20 | 2023-06-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0048 | Wall & Slab Openings Location & Level ( Survey Inspection ) | 00 | MEP | Elec | Elec | Light Current | Zone 8 | B1-A | 47 To 47X / U To V | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0145 | Installation for Puddle Flange as per Highlighted | 00 | MEP | Mech | Tanks | N/A | Zone 2 & 3 | A2 & A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-25 | 2023-06-23 | DONE | D |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0145 | Installation for Puddle Flange as per Highlighted | 01 | MEP | Mech | Tanks | N/A | Zone 2 & 3 | A2 & A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-07-30 | 2023-07-31 | 2023-07-31 | 2023-08-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0146 | Test After Concrete Pouring for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 8 & 15 | B1 & C1 | 28 To 37 / G To N | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-24 | 2023-06-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1584 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 36 / S | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-25 | 2023-06-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1585 | Reinforced Concrete Walls Formwork ( Duct Bank Manholes ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | RY To S / 27 To 32X | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1586 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1587 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1588 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | B1-A | 30 To 36 / N To G | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1589 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 18 To 11 / RY To SY | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1590 | Reinforced Concrete Wall Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B3 | 22X To 23 / J To H | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1591 | Reinforced Concrete Duct Bank Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 11 / RY To S | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1592 | Backfilling Layer ( 14 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-22 | 2023-06-26 | 2023-06-23 | 2023-06-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1593 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-22 | 2023-06-26 | 2023-06-23 | 2023-06-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1594 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | B1-A | 30 To 34 / G To M | L.G | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-23 | 2023-06-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1595 | Reinforced Concrete Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 31 To 36 / J To RY | G.F | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-23 | 2023-06-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1596 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 18 / L | L.G | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-23 | 2023-06-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1597 | Reinforced Concrete Slab ( Boundaries - Levels & Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 30 To 36 / RY To K | L.G | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-25 | 2023-06-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1598 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 11 To 20 / RY To T | L.G | N/A | N/A | 2023-06-23 | 2023-07-05 | 2023-07-05 | 2023-07-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1599 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 18 To 11 / RY To SY | L.G | N/A | N/A | 2023-06-23 | 2023-06-24 | 2023-06-24 | 2023-06-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1600 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 18 To 11 / RY To SY | L.G | N/A | N/A | 2023-06-23 | 2023-06-24 | 2023-06-24 | 2023-06-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1601 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | B1-A | N To G / 30 To 36 | L.G | N/A | N/A | 2023-06-24 | 2023-06-25 | 2023-06-25 | 2023-06-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1602 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A & A4-B | TX To RY / 10X To 11 | L.G To G.F | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-08 | 2023-07-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1603 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 | B3-A | RY To K / 32 To 36 | G.F | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-08 | 2023-07-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1604 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-06 | 2023-07-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1605 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-06 | 2023-07-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1606 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 25 To 28 / RY To QY | L.G | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-08 | 2023-07-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1607 | Backfilling Layer ( 15 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-06 | 2023-07-10 | 2023-07-13 | 2023-07-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1608 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-06 | 2023-07-10 | 2023-07-13 | 2023-07-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1609 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 36 To 37 / S | S.B To L.G | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-06 | 2023-07-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1610 | Reinforced Concrete Grease Interceptor pit Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 34 To 35 / SX To TX | FDN | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-08 | 2023-07-09 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1610 | Reinforced Concrete Grease Interceptor pit Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 34 To 35 / SX To TX | FDN | N/A | N/A | 2023-07-08 | 2023-07-09 | 2023-07-09 | 2023-07-10 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1611 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-10 | 2023-07-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1612 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-07-06 | 2023-07-10 | 2023-07-12 | 2023-07-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1613 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | N/A | 32 To 34 / G To M | L.G To G.F | N/A | N/A | 2023-07-08 | 2023-07-09 | 2023-07-12 | 2023-07-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1614 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | N/A | 35 To 38 / RX To S | FDN | N/A | N/A | 2023-07-09 | 2023-07-10 | 2023-07-12 | 2023-07-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1615 | Reinforced Concrete Columns formwork ( Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 / K | L.G To G.F | N/A | N/A | 2023-07-09 | 2023-07-10 | 2023-07-10 | 2023-07-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1616 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 18 / K | L.G To G.F | N/A | N/A | 2023-07-09 | 2023-07-10 | 2023-07-10 | 2023-07-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1617 | Reinforced Concrete Walls Reinforcement to Level "-5.825" | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / A To B | FDN To G.F | N/A | N/A | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-12 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1617 | Reinforced Concrete Walls Reinforcement to Level "-5.825" | 01 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / A To B | FDN To G.F | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1618 | Reinforced Concrete Walls Reinforcement to Level "-1.585" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 35 / RY To TX | L.G To G.F | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | B |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1618 | Reinforced Concrete Walls Reinforcement to Level "-1.585" | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 35 To 36 / RY To TX | L.G To G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1619 | Reinforced Concrete Wall Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B5-A | QX To R / 18 | L.G | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1620 | Reinforced Concrete Ground Slab ( Boundaries - Levels & Opening Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | B5-A | 16 To 23 / S To J | L.G | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1621 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1622 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1623 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | B5-A | 22X To 18 / L To RY | G.F | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-07-15 | 2023-07-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1624 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-07-13 | 2023-07-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1625 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-07-13 | 2023-07-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1626 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 13 / Q To RY | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1627 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 13 / Q To RY | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1628 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1629 | Backfilling Layer ( 16 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0147 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 1 | A1 | A To D / 1X To 2X | FDN | N/A | N/A | 2023-07-13 | 2023-07-15 | 2023-07-17 | 2023-07-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1630 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 13 To 16 / SX To S | L.G To G.F | N/A | N/A | 2023-07-13 | 2023-07-15 | 2023-07-15 | 2023-07-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1631 | Reinforced Concrete Ground Slab ( Boundaries - Axis - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 17 To 20 / J To M | G.F | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-15 | 2023-07-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1632 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 13 To 16 / S | L.G | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-16 | 2023-07-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1633 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 17 To 20 / J To M | G.F | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1634 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | N/A | 32 To 34 / G To M | L.G To G.F | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1635 | Reinforced Concrete Walls and Columns Reinforcement to Level " -1.90" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 13 To 18 | L.G To G.F | N/A | N/A | 2023-07-16 | 2023-07-17 | 2023-07-19 | 2023-07-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1636 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 33 To 35 / RY To TX | L.G | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-20 | 2023-07-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1637 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | B1-A | 32 To 34 / G To J | L.G | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-17 | 2023-07-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1638 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-18 | 2023-07-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1639 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0148 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 11 To 15 / PX To N | FDN | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-22 | 2023-07-20 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1640 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | 35 To 32 / 46 To 42X | L.G To G.F | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-18 | 2023-07-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1641 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1642 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1643 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-19 | 2023-07-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1644 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1645 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 | N/A | 32 To 38 / L To QY | G.F To 1st | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-19 | 2023-07-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1646 | Reinforced Concrete Walls and Column Reinforcement to Level " -1.10" | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B3 | 23 To 26 / J To H | L.G | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-22 | 2023-07-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1647 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 13 To 16 / PX To RY | L.G | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-20 | 2023-07-21 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1648 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 13 To 16 / PX To RY | L.G | N/A | N/A | 2023-07-19 | 2023-07-23 | 2023-07-22 | 2023-07-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1649 | Plane Concrete Lower Ground Slab Level & Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 13 To 16 / PX To RY | L.G | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-23 | 2023-07-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0149 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 11 To 15 / PX To N | FDN | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-22 | 2023-07-21 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1650 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 35 / TX To R | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-20 | 2023-07-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1651 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 13X To 16 / K To PX | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-24 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1652 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 13X To 16 / K To PX | L.G | N/A | N/A | 2023-07-20 | 2023-07-24 | 2023-07-22 | 2023-07-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1653 | Plane Concrete Lower Ground Slab Level & Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 13X To 16 / K To PX | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-20 | 2023-07-23 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1654 | Reinforced Concrete Lower Ground Slab Boundaries Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 35 / TX To RX | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-20 | 2023-07-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1655 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 35 / TX To RX | L.G | N/A | N/A | 2023-07-20 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1656 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 2 / A To D | FDN | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1657 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | 35 To 32 / 46 To 42X | L.G To G.F | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-23 | 2023-07-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1658 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4-B | 11 To 14 / SY To TX | L.G To G.F | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-23 | 2023-07-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1659 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B5-A | 23 To 18 / K To RX | G.F | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1660 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2-A | 6 To 4 / A | FDN To L.G | N/A | N/A | 2023-07-22 | 2023-07-23 | 2023-07-22 | 2023-07-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1661 | Backfilling Layer ( 11 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1662 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-25 | 2023-07-24 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1663 | Backfilling Layer ( 12 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1664 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-25 | 2023-07-24 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1665 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 32 To 38 / N To RX | G.F To 1ST | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1666 | Reinforced Concrete Walls Formwork from "74.95" To "76.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9Y To 10X / T To TX | L.G To G.F | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1667 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 23 To 15 / T To SY | L.G To G.F | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1668 | Lower Ground Slab Plain Concrete Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 10Y To 15 / RY To Q | FDN | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-24 | 2023-07-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0049 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 7 & 8 & 11 & 12 | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-25 | 2023-07-26 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0050 | Horizontal Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 10 | B6-B | N/A | G.F | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-31 | 2023-07-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0150 | Test After Concrete Pouring for Drainage Pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 7 & 8 & 11 & 12 & 15 | B1 & B2 & B3 & C1 & C2 & C3 | 28 To 38 / G To TX | FDN | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-27 | 2023-07-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1669 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 | N/A | L To QY / 32X To 35 | G.F To 1ST | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1670 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1671 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-08-01 | 2023-08-01 | 2023-08-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1672 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1673 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-08-01 | 2023-08-01 | 2023-08-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1674 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 36 / RY To TX | L.G | N/A | N/A | 2023-07-24 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1675 | Reinforced Concrete Doors & FHC Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 46X / ZY To Y | G.F | N/A | N/A | 2023-07-24 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1676 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | S / 36 To 37 | L.G To G.F | N/A | N/A | 2023-07-24 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1677 | Reinforced Concrete Ground Slab ( Boundaries, Opening, Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 10 & 11 | B4-A | 31 To 27 / S To L | G.F | N/A | N/A | 2023-07-24 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0051 | Vertical Earthing Conduits in Columns Coordinates | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 7 & 8 & 11 & 12 | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-26 | 2023-07-29 | 2023-07-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1678 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5 -A | 23 To 18 / QY To RY | G.F | N/A | N/A | 2023-07-25 | 2023-07-26 | 2023-07-26 | 2023-07-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1679 | Reinforced Concrete Wall Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 22X To 26 / J To G | L.G | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0052 | Horizontal Earthing Conduits Level | 00 | MEP | Elec | Elec | Earthing | Zone 10 | B6 | N/A | G.F | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-31 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0053 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 8 & 12 | C1 & C2 & C4 | N/A | G.F To 1ST & G.F To MEZZ | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1680 | Reinforced Concrete Stair Core Reinforcement to Level " +3.00" | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 45 To 46X / Y To ZY | G.F To MEZZ | N/A | N/A | 2023-07-27 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1681 | Reinforced Concrete Water Tank Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 | 6 To 9 / A To B | FDN To L.G | N/A | N/A | 2023-07-27 | 2023-07-29 | 2023-07-30 | 2023-07-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1682 | Reinforced Concrete Walls Reinforcement to Level " -1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 32X To 35 / T To TX | L.G To G.F | N/A | N/A | 2023-07-27 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1683 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | N/A | 26 To 31 / L To RY | G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-30 | 2023-07-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1684 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 32X To 34 / RY | L.G To G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-29 | 2023-07-31 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1685 | Reinforced Concrete Ground Slab ( Boundaries, Levels, Sleeves, Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 & 10 | B5-A | 16 To 23 / J To S | G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-07-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1686 | Reinforced Concrete Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 & 10 | B5-A | 16 To 23 / J To S | G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-08-01 | 2023-07-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1687 | Reinforced Concrete Wall Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 11 To 14 / SY To T | L.G | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-07-31 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1688 | Reinforced Concrete Water Tank Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3 | 7 To 9 / A To B | S.B To L.G | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-08-01 | 2023-07-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1689 | Reinforced Concrete Walls Reinforcement to Level " -1.1" | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 22X To 27 / G To J | L.G To G.F | N/A | N/A | 2023-07-30 | 2023-07-31 | 2023-07-31 | 2023-08-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1690 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 39X To 40 / 32X To 37 | L.G To G.F | N/A | N/A | 2023-07-30 | 2023-07-31 | 2023-07-31 | 2023-08-01 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0151 | Test for Drainage Pipes After Concrete Pouring | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-02 | 2023-08-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1691 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 11 To 18 / K To RY | L.G | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1692 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-02 | 2023-08-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1693 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-08-01 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1694 | Plane Concrete Lower Ground Slab Level & Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-A | 11 To 13 / L To PX | L.G | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-02 | 2023-08-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1695 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | B5-A | 16 To 23 / S To J | G.F | N/A | N/A | 2023-08-02 | 2023-08-03 | 2023-08-05 | 2023-08-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1696 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | S / 36 | L.G To G.F | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-03 | 2023-08-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1697 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | T To SY / 30 To 32X | G.F | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-03 | 2023-08-06 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1698 | Backfilling Layer ( 17 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1699 | Backfilling Layer ( 17 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-07 | 2023-08-08 | 2023-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1700 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1701 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-07 | 2023-08-08 | 2023-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1702 | Reinforced Concrete Beam Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 11 To 12 / T To TX | L.G | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1703 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 33 To 34 / S | L.G To G.F | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-06 | 2023-08-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1704 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 34 To 37 / WY To YY | G.F To 1ST | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1705 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | T To SY / 30 To 32X | L.G To G.F | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-06 | 2023-08-07 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1706 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 37 To ZY / 46X To 45 | G.F To MEZZ | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-06 | 2023-08-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1707 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | N/A | 32X To 37 / RX To QZ | G.F To 1ST & MEZZ | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-06 | 2023-08-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1708 | Reinforced Concrete Ground Slab ( Boundaries, Opening, Drop panls, Beams, Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 | B4-A | L To S / 22X To 28 | G.F | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-08 | 2023-08-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1709 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | N/A | 5 To 8 / B To EY | FDN To L.G | N/A | N/A | 2023-08-06 | 2023-08-07 | 2023-08-06 | 2023-08-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1710 | Reinforced Concrete Beam Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 11 To 12 / SY To TX | L.G | N/A | N/A | 2023-08-06 | 2023-08-07 | 2023-08-06 | 2023-08-08 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1711 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 27 To 30 | L.G To G.F | N/A | N/A | 2023-08-06 | 2023-08-07 | 2023-08-06 | 2023-08-08 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1712 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 11 To 15 / Q To K | L.G | N/A | N/A | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1713 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 22X To 28 / L To RY | G.F | N/A | N/A | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1714 | R.C Stair Case Formwork Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-A | 24 To 28 / QX To RY | L.G | N/A | N/A | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1715 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | T To SY / 30 To 32X | L.G To G.F | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-08 | 2023-08-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1716 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 39 To 44 / WY To YY | G.F To 1ST | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1717 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 39X To 40 / VX To Z | G.F To 1ST | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0152 | Test After Concrete Pouring for Sanitary Drainage Pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 5 & 9 & 10 & 14 | B1 & B5 & B6 & B7 & B8 | 10 To 27 / G To RY | FDN | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1718 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1719 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-08 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1720 | Waterproofing PVC Layer to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 27 To 30 | G.F | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1721 | PVC Protection – Cartmode to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 27 To 30 | G.F | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0153 | Installation and Test for Drainage Pipes as per attached | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B4 | 24 To 26 / RY To R | FDN | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0054 | Vertical Earthing Conduits in Columns Beteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 | B5 | 18 To L | G.F | N/A | N/A | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-08-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0055 | Vertical Earthing Conduits in Columns Beteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 10 | B4 & B5 | N/A | 1ST | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-29 | 2023-08-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1722 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | N/A | 22X To 20 / K To CX | G.F To 1ST | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1723 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1724 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-16 | 2023-08-16 | 2023-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1725 | Backfilling Layer ( 18 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1726 | Backfilling Layer ( 18 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-16 | 2023-08-16 | 2023-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1727 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | T To TX / 11 To 16 | L.G To G.F | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-10 | 2023-08-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1728 | Reinforced Concrete Lower Ground Slab ( Boundaries, Drops Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 11 To 17 / K To S | L.G | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1729 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 11 To 18 / L To RY | L.G | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1730 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 33 To 37 / S | G.F | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0154 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | Q To QX / 10Y To 11 | FDN | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-10 | 2023-08-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0056 | Vertical Earthing Conduits in ColumnsBeteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 12 | B5 & C3 | N/A | 1ST | N/A | N/A | 2023-08-12 | 2023-08-13 | 2023-08-29 | 2023-08-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1731 | Reinforced Concrete Columns & Shear Wall Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 42X To 45 / VX To WY | G.F To MEZZ | N/A | N/A | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1732 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 12 To 16 / K To RY | L.G | N/A | N/A | 2023-08-13 | 2023-08-15 | 2023-08-14 | 2023-08-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1733 | Reinforced Concrete Columns & Shear Wall Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 & 11 | N/A | 32X To 36 / 45 To QY | G.F To MEZZ | N/A | N/A | 2023-08-13 | 2023-08-15 | 2023-08-14 | 2023-08-16 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1734 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | T To SY / 27 To 24 | L.G | N/A | N/A | 2023-08-13 | 2023-08-14 | 2023-08-14 | 2023-08-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1735 | Underlayment Layer - Geotextile to Level "74.9" | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | TX / 36 To 38 | L.G | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-14 | 2023-08-16 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1736 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | Q To RX / 18 To 22X | G.F To 1ST | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-17 | 2023-08-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1737 | Plain Concrete Foundation Top Level & Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 38 / TX To RX | L.G | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2023-08-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0057 | Vertical Earthing Conduits in Columns ( Level & Location ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 12 | N/A | N/A | 1st | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2023-08-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0058 | Vertical Earthing Conduits in Columns ( Level & Location ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 10 | N/A | N/A | 1st | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2023-08-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1738 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | QZ To PX / 38 | G.F To 1ST | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-08-15 | 2023-08-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1739 | Reinforced Concrete Ground Slab ( Boundaries, Drops, Beams Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | 22X To 31 / SY To RY | G.F | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1740 | Reinforced Concrete Lower Ground Slab Boundaries, Drops, Openings & Beams ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / RY To Q | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1741 | Waterproofing PVC Layer to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | T To SY / 27 To 24 | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1742 | PVC Protection – Cartmode to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | T To SY / 27 To 24 | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1743 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | N/A | 23 To 37 / G To J | L.G To G.F | N/A | N/A | 2023-08-16 | 2023-08-20 | 2023-08-21 | 2023-08-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1744 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | X To W / 47 | G.F To 1ST | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-19 | 2023-08-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1745 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | RY To Q / B To EY | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1746 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 To 23 / K To RY | G.F To 1ST | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1747 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4-B | 23 To 31 / SY To RY | G.F | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1748 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 13 To 16 / T To SY | L.G To G.F | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-19 | 2023-08-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1749 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1750 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-21 | 2023-08-19 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1751 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1752 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-21 | 2023-08-19 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1753 | Plain Concrete Slab Top Level & Coordinates and Formwork | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | N/A | 36 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1754 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 16 To 12 / L To R | L.G To G.F | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1755 | Reinforced Concrete Columns formwork ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 16 / K | L.G To G.F | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-20 | 2023-08-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1756 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | N/A | 18 To 22X / M To R | G.F To 1ST | N/A | N/A | 2023-08-19 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1757 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 12 To 16 / K To QX | L.G To G.F | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1758 | Reinforced Concrete Wall Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 37 To 38 / S To RY | L.G To G.F | N/A | N/A | 2023-08-19 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0059 | Vertical Earthing Conduits in Columns ( L.G To G.F ) | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | N / 14 To 16 | L.G | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-29 | 2023-08-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0060 | Vertical Earthing Conduits in Columns Beteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 7 | C2 | ( Z / 45 ) ( 38 / RZ ) | G.F | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-29 | 2023-08-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1759 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-20 | 2023-08-21 | 2023-08-21 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1760 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-20 | 2023-08-21 | 2023-08-21 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1761 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-08-20 | 2023-08-21 | 2023-08-21 | 2023-08-22 | DONE | C |  |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1761 | Underlayment Layer - Geotextile | 01 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-06 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1762 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 45 To 46X / ZY To Y | G.F | N/A | N/A | 2023-08-21 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1763 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 12 To 14 / L To R | L.G To G.F | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-21 | 2023-08-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1764 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-21 | 2023-08-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1765 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-21 | 2023-08-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1766 | Reinforced Concrete Depressed Slab formwork ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1767 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1768 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1769 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1770 | Reinforced Concrete Walls Reinforcement to Level "-0.85" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 12 To 21 / RY | L.G To G.F | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1771 | Reinforced Concrete Depressed Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1772 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | N/A | 23 To 31 / S To L | G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1773 | Underlayment Layer - Geotextile from Level "-3.05"to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 24 To 30 | L.G To G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1774 | Waterproofing PVC Layer from Level "-3.05"to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 24 To 30 | L.G To G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1775 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-23 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1776 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-23 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1777 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-23 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1778 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 45 To 46X / ZY To Y | G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-27 | 2023-08-25 | DONE | C | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1779 | Reinforced Concrete Walls Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 32X To 36 / TX To T | L.G | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1780 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 12 / N To RX | L.G To G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1781 | Reinforced Concrete Columns Location and Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | W To X / 47 | G.F To 1ST | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-27 | 2023-08-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1782 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1783 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1784 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX / 37 To 38 | L.G | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1785 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / TX To RY | L.G | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-28 | 2023-08-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1786 | Reinforced Concrete Stair Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | R To RY / 27 To 28 | L.G To G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-27 | 2023-08-27 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1786 | Reinforced Concrete Stair Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | R To RY / 27 To 28 | L.G To G.F | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1787 | Reinforced Concrete Walls Openings ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | RY To SX / 35 To 36 | L.G To G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1788 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1789 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-28 | 2023-08-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1790 | Reinforced Concrete Slab formwork Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 18 To 22X / TX To RY | G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-27 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1791 | Surface Preparation for Tank Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / B To C | FDN To L.G | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-27 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1792 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1793 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1794 | PVC Protection – Cartmode from Level "-3.05"to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 24 To 30 | L.G To G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1795 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | W To X / 47 | G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-30 | 2023-08-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1796 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | N/A | 24 To 21 / T To SY | FDN | N/A | N/A | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-28 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1797 | Reinforced Concrete Walls Openings ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 11 To 12 / RY | L.G To G.F | N/A | N/A | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0155 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | N/A | 37 To 38 / RY To RX | FDN | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-30 | 2023-08-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1798 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-28 | 2023-08-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1799 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-28 | 2023-08-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1800 | Reinforced Concrete Depressed Slab Bottom, Top Layers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | A To C / 8 To 9 | L.G | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-28 | 2023-08-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1801 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 18 To 23 / RX To TX | G.F | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-30 | 2023-08-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1802 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-B | L To M / 12 | L.G To G.F | N/A | N/A | 2023-08-27 | 2023-09-02 | 2023-09-02 | 2023-09-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1803 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 11 To 18 / RY | L.G | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1804 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 13X To 14 / L | L.G To G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1805 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9Y To 11 / TX To RY | L.G To G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1806 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9 To 9X / A | L.G | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1807 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1808 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1809 | Reinforced Concrete Slab formwork Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B5-A | 17 To 21 / T To TX | G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0061 | Installation Earthing Conduits and Cables for Earthing System | 00 | MEP | Elec | Elec | Earthing | Zone 4 & 5 & 10 & 11 | B2 & B3 & B5 & B6 | N/A | G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-29 | 2023-08-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0156 | Installation for Pluming Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | RX To RY / 37 To 38 | L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-08-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0157 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | T To TX / 38 | L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-09-02 | 2023-08-31 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1810 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2-A | 5 To 7 / CX To 10Y | S.B To L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-09-02 | 2023-08-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1811 | Waterproofing PVC Layer to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | N/A | 24 To 21 / T To SY | FDN To L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-08-30 | 2023-08-31 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0158 | Gravity Test for Pluming Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | RX To RY / 37 To 38 | L.G | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-31 | 2023-09-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1812 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 / N | G.F To 1ST | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-30 | 2023-09-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1813 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-A | 2 To 16 / N | L.G To G.F | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-30 | 2023-09-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1814 | Reinforced Concrete Stair Landing Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / S To T | L.G | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-30 | 2023-09-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1815 | PVC Protection – Cartmode to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | N/A | 24 To 21 / T To SY | FDN To L.G | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-31 | 2023-09-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1816 | Reinforced Concrete Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | N/A | 22X To 31 / S To L | G.F | N/A | N/A | 2023-08-30 | 2023-09-04 | 2023-09-05 | 2023-09-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1817 | Reinforced Concrete Walls Openings ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | R To QX / 16 | L.G To G.F | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-09-02 | 2023-09-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1818 | Reinforced Concrete Walls Reinforcement to Level "-1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 16 / QX To RX | L.G To G.F | N/A | N/A | 2023-08-31 | 2023-09-02 | 2023-09-03 | 2023-09-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1819 | Reinforced Concrete Ground Slab ( Boundaries, Levels, Sleeves, Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | N/A | 22X To 31 / L To S | G.F | N/A | N/A | 2023-08-31 | 2023-09-02 | 2023-09-05 | 2023-09-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1820 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | G.F To 1st | QX To N / 18 To 22X | G.F | N/A | N/A | 2023-09-02 | 2023-09-03 | 2023-09-03 | 2023-09-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1821 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-A | 18 / L | L.G | N/A | N/A | 2023-09-02 | 2023-09-03 | 2023-09-05 | 2023-09-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1822 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | QZ To RX / 38 | G.F To 1ST | N/A | N/A | 2023-09-02 | 2023-09-03 | 2023-09-03 | 2023-09-04 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1823 | Reinforced Concrete Depressed Slab ( Boundaries, Drops, Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-09-03 | 2023-09-04 | 2023-09-04 | 2023-09-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1824 | Reinforced Concrete Columns Formwork ( Location ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 16 / L | L.G To G.F | N/A | N/A | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1825 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 4 & 9 | N/A | 9Y To 12 / RY To QZ | L.G | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-04 | 2023-09-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1826 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 23 / RX To TX | G.F | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-05 | 2023-09-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1827 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-05 | 2023-09-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1828 | Surface Preparation for Tank Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9 / A To C | FDN To L.G | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-06 | 2023-09-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1829 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 36 To 38 / S To RX | L.G | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-05 | 2023-09-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1830 | Reinforced Concrete Beams Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 18 To 21 / A To C | G.F | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1831 | Reinforced Concrete Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 18 To 21 / A To C | G.F | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-06 | 2023-09-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1832 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 18 / L | G.F To 1ST | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-05 | 2023-09-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0159 | Puddle Flange Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 | A3 | K To QX / B To EY | FDN | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1833 | Surface Preparation for Tank Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | N/A | 6 / A To C | FDN To L.G | N/A | N/A | 2023-09-06 | 2023-09-10 | 2023-09-10 | 2023-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1834 | Reinforced Concrete Walls Formwork ( Top Levels on Attachment ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / TX To RY | L.G To Ramp | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-09 | 2023-09-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1835 | Wall opening ( Knock out ) Coordinates & level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | A / 9X | L.G | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-07 | 2023-09-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1836 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9Y To 10X / SX To TX | L.G To G.F | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-09 | 2023-09-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1837 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | QX To RX / 10 To 10Z | FDN To L.G | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-07 | 2023-09-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0062 | Horizontal Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 9 & 10 | B5-B | N/A | G.F | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-12 | 2023-09-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0063 | Installation of Earthing Cable and Clamp as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 9 | B5-B | SY To TX / 18 To 20 | G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-12 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0160 | Installation of Puddle Flange in Treated Water Tank | 00 | MEP | Mech | Pluming | Drainage | Zone 2 | A3 | K To QX / B To EY | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-07 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1838 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1839 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1840 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | TX To SY / A | L.G | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-07 | 2023-09-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1841 | Reinforced Concrete Walls Formwork to Level "-1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 16 / QX To RX | L.G To G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-10 | 2023-09-10 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1842 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | J To QZ / 37 To 38 | G.F To MEZZ | N/A | N/A | 2023-09-07 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1843 | Reinforced Concrete Walls Formwork Coordinates & level to Level "-1.1" | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 23 To 27 / H To G | L.G To G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-11 | 2023-09-10 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1843 | Reinforced Concrete Walls Formwork Coordinates & level to Level "-1.1" | 01 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 23 To 27 / H To G | L.G To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1844 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1845 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1846 | Reinforced Concrete Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | B4-A | 23 To 32 / L To S | G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1847 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 / TX To RY | L.G | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-10 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1848 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 1 | N/A | 2 To 3 / A To D | FDN | N/A | N/A | 2023-09-09 | 2023-09-10 | 2023-09-10 | 2023-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1849 | RC Raft Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 1 | N/A | 1 To 4 / A To D | FDN | N/A | N/A | 2023-09-09 | 2023-09-10 | 2023-09-10 | 2023-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1850 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1851 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0064 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 6 | B4-A | N/A | G.F To 1st | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0065 | Horizontal Earthing Conduits Level | 00 | MEP | Elec | Elec | Earthing | Zone 9 & 10 | B5-B | N/A | G.F | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0066 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 6 | B4-A | N/A | G.F To 1st | N/A | N/A | 2023-09-10 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0067 | Earthing Cable and Clamp Level as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 9 | B5-B | SY To TX / 18 To 20 | G.F | N/A | N/A | 2023-09-10 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1852 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1853 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1854 | Reinforced Concrete Ground Slab ( Boundaries, Starter bar Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 23 / RX To TX | G.F | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1855 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 35 To 38 / S To RX | L.G | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1856 | Reinforced Concrete Lower Ground Slab ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 35 To 38 / S To RX | L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1857 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 4 & 9 | A4 | 9Y To 12 / RY To QZ | L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1858 | Reinforced Concrete Lower Ground Slab ( Boundaries, Starter bar Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-B | 9Y To 12 / RY To QZ | L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1859 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2023-09-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1860 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2023-09-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1861 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 23 / RX To TX | G.F | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1862 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | QX To QY / 10Z To 10 | S.B To L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1863 | Reinforced Concrete Mezzanine Slab Formwork ( Boundaries - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | V To Z / 44 To 46X | MEZZ | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1864 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | N/A | 32X To 33 / T To TX | FDN To L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1865 | Reinforced Concrete Mezzanine Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | VX To ZY / 44 To 45 | MEZZ | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0068 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 6 | B4-A | N/A | G.F | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0069 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 6 | B4-A | N/A | G.F | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0070 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B3-A | 28 / QY | G.F | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-17 | 2023-09-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0071 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B3-A | 28 / QY | G.F | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-17 | 2023-09-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1866 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | N/A | 26 To 30 / M To QY | G.F To 1st | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1867 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 to 39/ RY To TX | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1868 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1869 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1870 | Waterproofing PVC Layer for Wall to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | N/A | 32X To 33 / T To TX | FDN To L.G | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1871 | PVC Protection – Cartmode for Wall to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | N/A | 32X To 33 / T To TX | FDN To L.G | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-13 | 2023-09-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1872 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-13 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1873 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-13 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1874 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1875 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1876 | Reinforced Concrete foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 38 To 39 / RY To TX | FDN To L.G | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1877 | Reinforced Concrete Walls Formwork To Level "- 0.875" | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | L To M / 12 | L.G To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1878 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1879 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1880 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1881 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1882 | Underlayment Layer - Geotextile to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | 24 To 22 / T To SY | FDN To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1883 | Waterproofing PVC Layer to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | 24 To 22 / T To SY | FDN To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1884 | PVC Protection – Cartmode to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | 24 To 22 / T To SY | FDN To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1885 | Reinforced Concrete Wall Starter bars Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 / RY To TX | L.G | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1886 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 22 To 26 / J To G | L.G To G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1887 | Reinforced Concrete Ground Slab Formwork ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1888 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | J To QZ / 37 To 38 | G.F To MEZZ | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1889 | Reinforced Concrete Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-B | Q To S / 9Y To 12 | L.G | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1890 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-14 | 2023-09-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1891 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-14 | 2023-09-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1892 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 / RY To TX | L.G | N/A | N/A | 2023-09-14 | 2023-09-16 |  | 2023-09-17 | -22 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1893 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0072 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B4-A | 23 / QY | G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0073 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B4-A | 23 / QY | G.F | N/A | N/A | 2023-09-16 | 2023-09-17 |  | 2023-09-18 | -21 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1894 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | N/A | M To PX / 30 | G.F To 1st | N/A | N/A | 2023-09-16 | 2023-09-17 | 2023-09-17 | 2023-09-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1895 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 | 2023-09-17 | 2023-09-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1896 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1897 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | N/A | 23 To 30 / M To QY | G.F To 1st | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1898 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | N/A | 32 To 35 / 46X To 47 | L.G To G.F | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1899 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3-B | 6 To 7 / B To C | L.G | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1900 | Underlayment Layer - Geotextile to Level "-5.50" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 & 12 | N/A | 33 To 36 / TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1901 | Waterproofing PVC Layer to Level "-5.50" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 & 12 | N/A | 33 To 36 / TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1902 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 31 To 33 / SY To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1903 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 31 To 33 / SY To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1904 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 33 / T To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-20 |  | 2023-09-21 | -18 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1905 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 33 / T To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-20 |  | 2023-09-21 | -18 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1906 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | N/A | 6 To 7 / B To C | FDN To L.G | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1907 | PVC Protection – Cartmode to Level "-5.50" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 & 12 | N/A | 33 To 36 / TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Shield
Formulas:
Inspection Date = [Issued Date]+1
Date limit to issue response = [Inspection Date]+1
Overdue = IF([Actual Response Dates]>0,"DONE",[Date limit to issue response]-TODAY())
Overdue = IF([Actual Response Dates, row above]>0,"DONE",[Date limit to issue response]-TODAY())

## MAIN CONTRACTOR IR LOG
IR No. | Description | Rev. | Discipline | Sub-Discipline | System | Sub-System | Zone | Part/Building | Grid Line | Level | Space No. | Space Func. | Issued Date | Inspection Date | Actual Response Dates | Date limit to issue response | Overdue | Status | Last Ref. | Root Cause | Remarks | SUB | Status
P0020-ATR-SIR-IET-00001 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 4 & 5 & 13 & 14 | N/A | 14 to 20/J to Qx | FDN | N/A | N/A | 2022-01-21 | 2022-01-22 | 2022-01-21 | 2022-01-23 | DONE | B | L
P0020-ATR-SIR-IET-00002 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-24 | 2022-01-25 | 2022-01-24 | 2022-01-26 | DONE | B | L
P0020-ATR-SIR-IET-00003 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-25 | 2022-01-26 | 2022-01-25 | 2022-01-27 | DONE | B | L
P0020-ATR-SIR-IET-00004 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-26 | 2022-01-27 | 2022-01-26 | 2022-01-28 | DONE | B | L
P0020-ATR-SIR-IET-00005 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-01-26 | 2022-01-27 | 2022-01-26 | 2022-01-28 | DONE | B | L
P0020-ATR-SIR-IET-00006 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place |  | N/A |  | FDN | N/A | N/A | 2022-01-27 | 2022-01-28 | 2022-01-27 | 2022-01-29 | DONE | B | L
P0020-ATR-SIR-IET-00007 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | N/A | 20 to 26/M to Qx | FDN | N/A | N/A | 2022-02-06 | 2022-02-07 | 2022-02-06 | 2022-02-08 | DONE | B | L
P0020-ATR-SIR-IET-00008 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 6 & 14 & 15 | N/A | 20 to 32x/G to R | FDN | N/A | N/A | 2022-02-06 | 2022-02-07 | 2022-02-06 | 2022-02-08 | DONE | B | L
P0020-ATR-SIR-IET-00009 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00010 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00011 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-08 | 2022-02-10 | DONE | B | L
P0020-ATR-SIR-IET-00012 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-09 | 2022-02-10 | 2022-02-09 | 2022-02-11 | DONE | B | L
P0020-ATR-SIR-IET-00013 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-10 | 2022-02-12 | DONE | B | L
P0020-ATR-SIR-IET-00014 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-10 | 2022-02-11 | 2022-02-10 | 2022-02-12 | DONE | B | L
P0020-ATR-SIR-IET-00015 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00016 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation |  | N/A |  | FDN | N/A | N/A | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-10 | DONE | A | L
P0020-ATR-SIR-IET-00017 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-12 | 2022-02-13 | 2022-02-12 | 2022-02-14 | DONE | B | L
P0020-ATR-SIR-IET-00018 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-13 | 2022-02-14 | 2022-02-13 | 2022-02-15 | DONE | B | L
P0020-ATR-SIR-IET-00019 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-14 | 2022-02-15 | 2022-02-14 | 2022-02-16 | DONE | B | L
P0020-ATR-SIR-IET-00020 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-02-17 | 2022-02-18 | 2022-02-17 | 2022-02-19 | DONE | B | L
P0020-ATR-SIR-IET-00021 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place |  | N/A |  | FDN | N/A | N/A | 2022-01-21 | 2022-01-22 | 2022-01-22 | 2022-01-23 | DONE | A | L
P0020-ATR-SIR-IET-00022 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place |  | N/A |  | FDN | N/A | N/A | 2022-02-22 | 2022-02-23 | 2022-02-23 | 2022-02-24 | DONE | A | L
P0020-ATR-SIR-IET-00023 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A | 18 to 32x/G to Qz | FDN | N/A | N/A | 2022-02-23 | 2022-02-24 | 2022-02-24 | 2022-02-25 | DONE | B | L
P0020-ATR-SIR-IET-00024 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A |  | FDN | N/A | N/A | 2022-02-24 | 2022-02-25 | 2022-02-25 | 2022-02-26 | DONE | B | L
P0020-ATR-SIR-IET-00025 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 2 & 3 | A3 / A4 | H To S / 13 To 9Y | FDN | N/A | N/A | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-10 | DONE | C |  | Not following approved SD |  | Al-Abrar | open
P0020-ATR-SIR-IET-00025 | Excavation for Bottom level & Coordinate | 01 | Civil | Civil | Earthwork | Excavation | Zone 2 & 3 | A3 / A4 | H To S / 13 To 9Y | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-28 | DONE | B | L |  |  | Al-Abrar
P0020-ATR-SIR-IET-00026 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 6 & 7 & 8 | N/A | 32x to 38/G to Qx | FDN | N/A | N/A | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-10 | DONE | B | L
P0020-ATR-SIR-IET-00027 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 & 8 | N/A | 32x to 38/G to Qx | FDN | N/A | N/A | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-10 | DONE | B | L
P0020-ATR-SIR-IET-00028 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | N/A | 23 to 27/N to QX | FDN | N/A | N/A | 2022-03-12 | 2022-03-13 | 2022-03-12 | 2022-03-14 | DONE | A | L
P0020-ATR-SIR-IET-00029 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | N/A | 23 to 27/N to QX | FDN | N/A | N/A | 2022-03-12 | 2022-03-13 | 2022-03-12 | 2022-03-14 | DONE | B | L
P0020-ATR-SIR-IET-00030 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 8 | N/A | Z/46 to 47X | FDN | N/A | N/A | 2022-03-13 | 2022-03-14 | 2022-03-13 | 2022-03-15 | DONE | B | L
P0020-ATR-SIR-IET-00031 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 8 | N/A | Z/46 to 47X | FDN | N/A | N/A | 2022-03-13 | 2022-03-14 | 2022-03-13 | 2022-03-15 | DONE | B | L
P0020-ATR-SIR-IET-00032 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-16 | DONE | B | L
P0020-ATR-SIR-IET-00033 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-14 | 2022-03-15 | 2022-03-14 | 2022-03-16 | DONE | B | L
P0020-ATR-SIR-IET-00034 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-17 | 2022-03-18 | 2022-03-17 | 2022-03-19 | DONE | B | L
P0020-ATR-SIR-IET-00035 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-17 | 2022-03-18 | 2022-03-17 | 2022-03-19 | DONE | B | L
P0020-ATR-SIR-IET-00036 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-18 | 2022-03-19 | 2022-03-18 | 2022-03-20 | DONE | B | L
P0020-ATR-SIR-IET-00037 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-18 | 2022-03-19 | 2022-03-18 | 2022-03-20 | DONE | A | L
P0020-ATR-SIR-IET-00038 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-19 | 2022-03-20 | 2022-03-19 | 2022-03-21 | DONE | A | L
P0020-ATR-SIR-IET-00039 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A | (U-Z)(39:47) | FDN | N/A | N/A | 2022-03-19 | 2022-03-20 | 2022-03-19 | 2022-03-21 | DONE | B | L
P0020-ATR-SIR-IET-00040 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | (U-Z)(40:47) | FDN | N/A | N/A | 2022-03-21 | 2022-03-22 | 2022-03-21 | 2022-03-23 | DONE | A | L
P0020-ATR-SIR-IET-00041 | Plain Concrete Top Level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | (U-Z)(40:47) | FDN | N/A | N/A | 2022-03-21 | 2022-03-22 | 2022-03-21 | 2022-03-23 | DONE | A | L
P0020-ATR-SIR-IET-00042 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 13 & 14 | N/A | AXJ/A16 to 22X | FDN | N/A | N/A | 2022-03-24 | 2022-03-25 | 2022-03-24 | 2022-03-26 | DONE | B | L
P0020-ATR-SIR-IET-00043 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 13 & 14 | N/A | AXJ/A16 to 22X | FDN | N/A | N/A | 2022-03-25 | 2022-03-26 | 2022-03-25 | 2022-03-27 | DONE | A | L
P0020-ATR-SIR-IET-00044 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-25 | 2022-03-26 | 2022-03-25 | 2022-03-27 | DONE | A | L
P0020-ATR-SIR-IET-00045 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-26 | 2022-03-27 | 2022-03-26 | 2022-03-28 | DONE | B | L
P0020-ATR-SIR-IET-00046 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | B | L
P0020-ATR-SIR-IET-00047 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-03-26 | 2022-03-27 | 2022-03-26 | 2022-03-28 | DONE | A | L
P0020-ATR-SIR-IET-00048 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 & 12 | N/A | 32x to 38/J to Rx | FDN | N/A | N/A | 2022-03-26 | 2022-03-27 | 2022-03-26 | 2022-03-28 | DONE | C |  | Not following approved SD
P0020-ATR-SIR-IET-00048 | Excavation for Bottom level & Coordinate | 01 | Civil | Civil | Earthwork | Excavation | Zone 7 & 12 | N/A | 32x to 38/J to Rx | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00049 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 & 12 | N/A | 32x to 38/J to Rx | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | B | L
P0020-ATR-SIR-IET-00050 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A |  | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | B | L
P0020-ATR-SIR-IET-00051 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | 44 & 41 | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | A | L
P0020-ATR-SIR-IET-00052 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | X/QY 46X /49X | FDN | N/A | N/A | 2022-03-27 | 2022-03-28 | 2022-03-27 | 2022-03-29 | DONE | B | L
P0020-ATR-SIR-IET-00053 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment |  | N/A |  | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | A | L
P0020-ATR-SIR-IET-00054 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | X/Z & 41/46X | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | A | L
P0020-ATR-SIR-IET-00055 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | X/Z & 41/46X | FDN | N/A | N/A | 2022-03-28 | 2022-03-29 | 2022-03-28 | 2022-03-30 | DONE | A | L
P0020-ATR-SIR-IET-00056 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 | N/A | 39 to 41/W to Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00057 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 | N/A | 39 to 41/W to Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00058 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | X/QY 46X /49X | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00059 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | WY/ZY & 44/40 | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | A | L
P0020-ATR-SIR-IET-00060 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | 46X/39 & VX/Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | A | L
P0020-ATR-SIR-IET-00061 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | 46X/39 & VX/Z | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00062 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | W9/Z9 & 44/40 | FDN | N/A | N/A | 2022-03-29 | 2022-03-30 | 2022-03-29 | 2022-03-31 | DONE | B | L
P0020-ATR-SIR-IET-00063 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 13 & 14 | N/A | 16-23 / J-K | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | A | L
P0020-ATR-SIR-IET-00064 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | W/Z & 41-39 | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | A | L
P0020-ATR-SIR-IET-00065 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | W/Z & 39-46 | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | A | L
P0020-ATR-SIR-IET-00066 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 13 & 14 | N/A | 16/23 & J/K | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | B | L
P0020-ATR-SIR-IET-00067 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | U/Z &39-46 | FDN | N/A | N/A | 2022-03-31 | 2022-04-01 | 2022-03-31 | 2022-04-02 | DONE | B | L
P0020-ATR-SIR-IET-00068 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | W/Z & 41-39 | FDN | N/A | N/A | 2022-04-01 | 2022-04-02 | 2022-04-01 | 2022-04-03 | DONE | B | L
P0020-ATR-SIR-IET-00069 | Plain concrete top level & Coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 13 & 14 | N/A | J/K & 18/22X | FDN | N/A | N/A | 2022-04-06 | 2022-04-07 | 2022-04-06 | 2022-04-08 | DONE | B | L
P0020-ATR-SIR-IET-00070 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | N/A | 18 to 32x G to Qz | FDN | N/A | N/A | 2022-04-06 | 2022-04-07 | 2022-04-06 | 2022-04-08 | DONE | B | L
P0020-ATR-SIR-IET-00071 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-11 | 2022-04-12 | 2022-04-11 | 2022-04-13 | DONE | A | L
P0020-ATR-SIR-IET-00072 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-11 | 2022-04-12 | 2022-04-11 | 2022-04-13 | DONE | B | L
P0020-ATR-SIR-IET-00073 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-12 | 2022-04-13 | 2022-04-12 | 2022-04-14 | DONE | A | L
P0020-ATR-SIR-IET-00074 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | PX/QX & 34/37 | FDN | N/A | N/A | 2022-04-12 | 2022-04-13 | 2022-04-12 | 2022-04-14 | DONE | B | L
P0020-ATR-SIR-IET-00075 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | 1v/1z & 46/39 | FDN | N/A | N/A | 2022-04-19 | 2022-04-20 | 2022-04-19 | 2022-04-21 | DONE | B | L
P0020-ATR-SIR-IET-00076 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 7 | N/A | WY/ZY & 44/41 | FDN | N/A | N/A | 2022-04-19 | 2022-04-20 | 2022-04-19 | 2022-04-21 | DONE | B | L
P0020-ATR-SIR-IET-00077 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | V to Y/40 to 46 | FDN | N/A | N/A | 2022-04-20 | 2022-04-21 | 2022-04-20 | 2022-04-22 | DONE | B | L
P0020-ATR-SIR-IET-00078 | Plain concete top level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A |  | FDN | N/A | N/A | 2022-04-20 | 2022-04-21 | 2022-04-20 | 2022-04-22 | DONE | B | L
P0020-ATR-SIR-IET-00079 | Soil Replacement level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 & 8 | N/A |  | FDN | N/A | N/A | 2022-04-24 | 2022-04-25 | 2022-04-24 | 2022-04-26 | DONE | A | L
P0020-ATR-SIR-IET-00080 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A |  | FDN | N/A | N/A | 2022-04-25 | 2022-04-26 | 2022-04-26 | 2022-04-27 | DONE | B | L
P0020-ATR-SIR-IET-00081 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | Z to Y/46 to 42 | FDN | N/A | N/A | 2022-04-25 | 2022-04-26 | 2022-04-25 | 2022-04-27 | DONE | A | L
P0020-ATR-SIR-IET-00082 | Plain concete top level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | Z/Y &46/42 | FDN | N/A | N/A | 2022-04-25 | 2022-04-26 | 2022-04-25 | 2022-04-27 | DONE | A | L
P0020-ATR-SIR-IET-00083 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | N/A | 39 to 42/TX to Q Z | FDN | N/A | N/A | 2022-05-17 | 2022-05-18 | 2022-05-18 | 2022-05-19 | DONE | B | L
P0020-ATR-SIR-IET-00084 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 12 | N/A | TX/33 to 38 | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00085 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | N/A | 26 to 33/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00086 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | N/A | 26 to 33/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00087 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | N/A | 16 to 26/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00088 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | N/A | 16 to 26/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00089 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | N/A | 16 to 26/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00090 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | N/A | 26 to 33/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00091 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | N/A | 26 to 33/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00092 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | N/A | 26 to 33/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00093 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | 33 to 38/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00094 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | 33 to 38/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00095 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | 33 to 38/ J to QZ | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00096 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 8 | N/A | 33 to 38/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00097 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 8 | N/A | 33 to 38/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00098 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 8 | N/A | 33 to 38/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00099 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | N/A | 23 to 26/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00100 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | N/A | 23 to 26/ G to J | FDN | N/A | N/A | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-26 | DONE | B | L
P0020-ATR-SIR-IET-00101 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | N/A | 23 to 26/ G to J | FDN | N/A | N/A | 2022-05-25 | 2022-05-26 | 2022-05-26 | 2022-05-27 | DONE | B | L
P0020-ATR-SIR-IET-00102 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | N/A | 26 to 33/ G to J | FDN | N/A | N/A | 2022-05-25 | 2022-05-26 | 2022-05-26 | 2022-05-27 | DONE | B | L
P0020-ATR-SIR-IET-00103 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 33 to 38/ 46x to 47 | FDN | N/A | N/A | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00104 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | 33 to 38/ 42 to 46x | FDN | N/A | N/A | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00105 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | N/A | S To TX /36 To 38 | FDN | N/A | N/A | 2022-05-26 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00106 | Reinforced Concrete Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 33 to 38/ 46x to 47 | FDN | N/A | N/A | 2022-05-31 | 2022-05-28 | 2022-05-28 | 2022-05-29 | DONE | B | L
P0020-ATR-SIR-IET-00107 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 23 to27 /G to l | FDN | N/A | N/A | 2022-05-31 | 2022-06-01 | 2022-06-01 | 2022-06-02 | DONE | B | L
P0020-ATR-SIR-SCG-00001 | Installation and Gravity Test for Drainage Pipes | 00 | MEP | Mech | pluming | Drainage | Zone 7 | N/A | X Lines 45 - QZ y Lines 4 - Z | FDN | N/A | N/A | 2022-06-02 | 2022-06-05 | 2022-06-09 | 2022-06-06 | DONE | C |  | Lack of Construction Supervision
P0020-ATR-SIR-SCG-00001 | Installation and Gravity Test for Drainage Pipes | 01 | MEP | Mech | pluming | Drainage | Zone 6 & 7 & 8 | N/A | X Lines 45 - QZ y Lines 4 - Z | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-21 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00108 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | N/A | QZ TOTX /36 TO 38 | FDN | N/A | N/A | 2022-06-01 | 2022-06-02 | 2022-06-02 | 2022-06-03 | DONE | B | L
P0020-ATR-SIR-IET-00109 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | U TO Z / 46 to 42 | FDN | N/A | N/A | 2022-06-01 | 2022-06-02 | 2022-06-02 | 2022-06-03 | DONE | B | L
P0020-ATR-SIR-IET-00110 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-02 | 2022-06-04 | 2022-06-04 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00111 | Soil Replacement Layer (1) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-02 | 2022-06-04 | 2022-06-04 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00112 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 6 | N/A | 24 To 26 /Q ToN | FDN | N/A | N/A | 2022-06-02 | 2022-06-04 | 2022-06-07 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00113 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundries and Starter Bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 32x To 38/47 To 45 | FDN | N/A | N/A | 2022-06-04 | 2022-06-04 | 2022-06-04 | 2022-06-05 | DONE | B | L
P0020-ATR-SIR-IET-00114 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | A | L
P0020-ATR-SIR-IET-00115 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00116 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00117 | Soil Replacement Layer (2) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | A | L
P0020-ATR-SIR-IET-00118 | Compaction work layer (1) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00119 | Compaction work layer (2) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-11 | 2022-06-12 | 2022-06-11 | 2022-06-13 | DONE | B | L
P0020-ATR-SIR-IET-00120 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00121 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00122 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00123 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 36 To 38 / TX To QX | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00124 | Soil Replacement Layer (3) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00125 | Soil Replacement Layer (4) level & Coordinate | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | A | L
P0020-ATR-SIR-IET-00126 | Compaction work layer (3) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00127 | Compaction work layer (4) | 00 | Civil | Civil | Earthwork | Compaction | Zone 12 | N/A | 34 To 37 / RY To S | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | B | L
P0020-ATR-SIR-IET-00128 | Excavation for Bottom level & Coordinate - (Tower Crane - 02 ) | 00 | Civil | Civil | Earthwork | Excavation | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-12 | 2022-06-13 | 2022-06-13 | 2022-06-14 | DONE | D
P0020-ATR-SIR-IET-00128 | Excavation for Bottom level & Coordinate - (Tower Crane - 02 ) | 01 | Civil | Civil | Earthwork | Excavation | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-13 | 2022-06-14 | 2022-06-13 | 2022-06-15 | DONE | B | L
P0020-ATR-SIR-SCG-00002 | MEP Work Release for R.C. Foundation TO level -4.775 | 00 | Civil | Mech | Concrete | Cast In Place | Zone 8 | N/A | V to Z / 46 × to 47 | FDN | N/A | N/A | 2022-06-15 | 2022-06-16 | 2022-06-21 | 2022-06-17 | DONE | B | L
P0020-ATR-SIR-IET-00129 | Reinforced Concrete Piers and Walls ( Reinforcement and Foemwork ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | V To Y/47 To 46x | FDN | N/A | N/A | 2022-06-14 | 2022-06-15 | 2022-06-15 | 2022-06-16 | DONE | B | L
P0020-ATR-SIR-IET-00130 | Plain concrete top level & coordinate | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | QX To TX / 35 To 38 | FDN | N/A | N/A | 2022-06-14 | 2022-06-15 | 2022-06-14 | 2022-06-16 | DONE | B | L
P0020-ATR-SIR-IET-00131 | Plain Concrete Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | QX To TX / 35 To 38 | FDN | N/A | N/A | 2022-06-14 | 2022-06-15 | 2022-06-14 | 2022-06-16 | DONE | B | L
P0020-ATR-SIR-IET-00132 | Reinforced Concrete Foemwork for Walla & Piers | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | V to Z/46x To 47 | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-16 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00133 | Soil Replacement and Compaction work layer ( 1 ) level & Coordinate for Sump-pit | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | N/A | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-16 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00134 | Soil Replacement and Compaction work layer ( 1 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-16 | 2022-06-18 | 2022-06-16 | 2022-06-19 | DONE | B | L
P0020-ATR-SIR-IET-00135 | Soil Replacement and Compaction work layer ( 2 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-18 | 2022-06-19 | 2022-06-18 | 2022-06-20 | DONE | B | L
P0020-ATR-SIR-IET-00136 | Soil Replacement and Compaction work layer ( 3 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 30 To 32 / J | FDN | N/A | N/A | 2022-06-18 | 2022-06-19 | 2022-06-19 | 2022-06-20 | DONE | B | L
P0020-ATR-SIR-IET-00137 | Drainage Pipes Location & Level To ( -5.325 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | U to Z/42 To 46x | FDN | N/A | N/A | 2022-06-20 | 2022-06-21 | 2022-06-21 | 2022-06-22 | DONE | B | L
P0020-ATR-SIR-SCG-00003 | MEP Work Release for R.C. Foundation TO level -5.325 | 00 | MEP | Mech | Concrete | Cast In Place | Zone 7 | C2 | U to Z / 42 to 46x | FDN | N/A | N/A | 2022-06-20 | 2022-06-21 | 2022-06-21 | 2022-06-22 | DONE | C |  | Lack of Construction Supervision
P0020-ATR-SIR-SCG-00003 | MEP Work Release for R.C. Foundation TO level -5.325 | 01 | Civil | Mech | Concrete | Cast In Place | Zone 7 | C2 | U to Z / 42 to 46x | FDN | N/A | N/A | 2022-06-22 | 2022-06-23 |  | 2022-06-24 | -472 | open | L
P0020-ATR-SIR-IET-00138 | Soil Replacement and Compaction work layer ( 4 ) level & Coordinate for TC-02 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 15 | N/A | 31 To 32 / J | FDN | N/A | N/A | 2022-06-20 | 2022-06-21 | 2022-06-20 | 2022-06-22 | DONE | B | L
P0020-ATR-SIR-IET-00139 | Soil Replacement and Compaction work layer ( 2 ) level & Coordinate for Sump-pit | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B5 | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-06-22 | 2022-06-23 | 2022-06-22 | 2022-06-24 | DONE | B | L
P0020-ATR-SIR-IET-00140 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | B1 | 31 To 32 / J | FDN | N/A | N/A | 2022-06-22 | 2022-06-23 | 2022-06-22 | 2022-06-24 | DONE | B | L
P0020-ATR-SIR-IET-00141 | Soil Replacement and Compaction work layer ( 3 ) level & Coordinate for Sump-pit | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B5 | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-23 | 2022-06-26 | DONE | B | L
P0020-ATR-SIR-IET-00142 | Reinforced Concrete Top Layer Reinforcement & Formwork Boundries & Starter bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 46× To 41 / Z To U | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-25 | 2022-06-26 | DONE | B | L
P0020-ATR-SIR-IET-00143 | Permanent Shutter Strep Footing ( Reinforcement , Formwork , Top Level & Location ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-23 | 2022-06-26 | DONE | B | L
P0020-ATR-SIR-IET-00144 | Construction Joint Injectable Hose Installation - Between C1 & C2 | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 & C2 | 46× / Z To V | FDN | N/A | N/A | 2022-06-23 | 2022-06-25 | 2022-06-25 | 2022-06-26 | DONE | B | L |  |  | Shield
P0020-ATR-SIR-IET-00145 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | B1 | 31 to 32 X / G to J | FDN | N/A | N/A | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-28 | DONE | B | L |  |  | Shield
P0020-ATR-SIR-IET-00146 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 15 | B1 | 31 to 32 X / G to J | FDN | N/A | N/A | 2022-06-26 | 2022-06-27 | 2022-06-28 | 2022-06-28 | DONE | B | L |  |  | Shield
P0020-ATR-SIR-IET-00147 | Plain Concrete Top Level & coordinate and Formwork for TC - 02 | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 30 To 32 / J | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-29 | 2022-06-30 | DONE | B | L |  |  | Al-khaleej
P0020-ATR-SIR-IET-00148 | Excavation for Bottom level & Coordinate | 00 | Civil | Civil | EarthWork | Excavation | Zone 5 | C3 | 35 To 38 / QZ To RY | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-06-30 | DONE | B | L |  |  | Al-Abrar
P0020-ATR-SIR-IET-00149 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 46x To 47 / V To Z | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-29 | 2022-06-30 | DONE | B | L |  |  | Al-khaleej
P0020-ATR-SIR-IET-00150 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | C2 | 46x To 47 / V To Z | FDN | N/A | N/A | 2022-06-28 | 2022-06-29 | 2022-06-29 | 2022-06-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0001 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 28 / G To J | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-06-30 | 2022-07-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0002 | Reinforced Concrete Reinforcement Piers & Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 46x To 41 / Z To U | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-06-30 | 2022-07-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0003 | Reinforced Concrete Formwork Piers & Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 46x To 41 / Z To U | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-07-02 | 2022-07-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0004 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 28 / G To J | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-07-03 | 2022-07-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0005 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | C1 | 45 To 47 / V To Z | FDN | N/A | N/A | 2022-06-30 | 2022-07-02 | 2022-06-30 | 2022-07-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0006 | Mass Concrete Mockup | 00 | Civil | Civil | Concrete | Cast in place | Zone 13 | N/A | 12 To 14 / 3× To 4× | FDN | N/A | N/A | 2022-07-03 | 2022-07-06 | 2022-07-18 | 2022-07-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0007 | Modified Traverse Points | 00 | Civil | Civil | Surveying | Traverse | General | N/A | All Project | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0008 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 42 To 46x / Z To WX | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0009 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C2 | 42 To 46x / Z To WX | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0010 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0011 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0012 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | Q To N / 24 To 26 | FDN | N/A | N/A | 2022-07-03 | 2022-07-04 | 2022-07-04 | 2022-07-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0013 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-04 | 2022-07-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0014 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B2 | M To QX / 23 To 28 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-04 | 2022-07-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0015 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | K To Q / 22× To 28 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-04 | 2022-07-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0016 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-05 | 2022-07-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0017 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-04 | 2022-07-05 | 2022-07-05 | 2022-07-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0018 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-05 | 2022-07-06 | 2022-07-06 | 2022-07-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0019 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work “ Sand “ | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | S To TX /35 To 36 | FDN | N/A | N/A | 2022-07-05 | 2022-07-06 | 2022-07-06 | 2022-07-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0020 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 12 | C4 | 34 To 36 | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0021 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 12 | C4 | TX / 35 To 36 | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-21 | 2022-07-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0022 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0023 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-18 | 2022-07-19 | 2022-07-18 | 2022-07-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0024 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-07-28 | 2022-07-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0025 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-07-28 | 2022-07-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0026 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-06-20 | 2022-07-22 | DONE | C |  | Consultant request extra documents and materials |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0026 | Soil Replacement Layer ( 1 ) Level & Coordinates & Compaction Work | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0027 | Soil Replacement Layer ( 2 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-20 | 2022-07-21 | 2022-07-23 | 2022-07-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0028 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0029 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C4 | 34 To 37 / RY To TX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0030 | Soil Replacement Layer ( 3 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0031 | Soil Replacement Layer ( 4 ) Level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-21 | 2022-07-22 | 2022-07-28 | 2022-07-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0032 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28× TO 33 / H TO J | FDN | N/A | N/A | 2022-07-23 | 2022-07-24 | 2022-07-23 | 2022-07-25 | DONE | C |  | Using Improper Material |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0032 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28× TO 33 / H TO J | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0001 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C2 | 46x To 45 / WY To U | FDN | N/A | N/A | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-26 | DONE | C |  | Not following approved SD |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0001 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C2 | 46x To 45 / WY To U | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-25 | 2022-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0033 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 33 To 38 / 42 To 46x | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0034 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 33 To 38 / 42 To 46x | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0035 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 6 | B2 | 22x TO 28 / J TO QZ | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0036 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 6 | B2 | 22x TO 28 / J TO QZ | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0037 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 7 | C3 | 37 To 38 / PX To QX | FDN | N/A | N/A | 2022-07-26 | 2022-07-27 | 2022-07-27 | 2022-07-28 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0038 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0039 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0040 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 10 | B4 | 22x TO 28 / QX TO TX | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0041 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 11 | B3 | 28x TO 34 / QY TO TX | FDN | N/A | N/A | 2022-07-27 | 2022-07-28 | 2022-07-28 | 2022-07-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0042 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 34 To 37 | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-30 | 2022-07-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0043 | PVC Protection - Screed & Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 6 | B2 | 22x TO 28 / J TO QZ | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-30 | 2022-07-31 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0044 | Soil Replacement Layer ( 5 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-28 | 2022-07-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0045 | Soil Replacement Layer ( 6 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-28 | 2022-07-30 | 2022-07-28 | 2022-07-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0046 | Existing Piles Record | 00 | Civil | Civil | Earthwork | Demolishing | Zone 10 | N/A | N/A | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-08-03 | 2022-08-01 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0047 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundries and Starter Bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22x To 32x / H To J | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-08-04 | 2022-08-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0048 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work to Level 72.075 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-07-31 | 2022-08-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0049 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work to Level 72.325 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-30 | 2022-07-31 | 2022-07-31 | 2022-08-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0050 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-08-03 | 2022-08-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0051 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-08-03 | 2022-08-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0052 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work to Level 72.575 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-07-31 | 2022-08-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0053 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work to Level 72.825 | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 35 To 38 / QX To RY | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-07-31 | 2022-08-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0054 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 35 To 38 / PX To RY | FDN | N/A | N/A | 2022-07-31 | 2022-08-01 | 2022-07-31 | 2022-08-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0055 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 & 12 | C3 | PX To RY / 38 To 36 | FDN | N/A | N/A | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-03 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0056 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 & 12 | C3 | PX To RY / 38 To 36 | FDN | N/A | N/A | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-03 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0057 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-02 | 2022-08-03 | 2022-08-07 | 2022-08-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0058 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 32x / PX To N | FDN | N/A | N/A | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0059 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | RY To TX / 35 To 38 | FDN | N/A | N/A | 2022-08-03 | 2022-08-04 | 2022-08-07 | 2022-08-05 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0060 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 & 12 | C3 | PX To RY / 38 To 36 | FDN | N/A | N/A | 2022-08-03 | 2022-08-04 | 2022-08-07 | 2022-08-05 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0061 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-04 | 2022-08-05 | 2022-08-07 | 2022-08-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0062 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-04 | 2022-08-05 | 2022-08-07 | 2022-08-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0063 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0064 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0065 | Existing Piles Record | 00 | Civil | Civil | Earthwork | Demolishing | Zone 5 | N/A | N/A | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0066 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0067 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0068 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0069 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 & 12 | B4 | 35 To 33 / RX To S | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0070 | Soil Replacement Layer ( 1 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0071 | Soil Replacement Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0072 | Soil Replacement Layer ( 3 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0073 | Soil Replacement Layer ( 4 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 12 | C3 | 34 To 36 / QZ To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0074 | Soil Replacement Layer ( 5 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0075 | Soil Replacement Layer ( 6 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / TX To RY | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0076 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-07 | 2022-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0077 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | C3 & B4 | TX To QZ / 33 To 36 | FDN | N/A | N/A | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0078 | Dead Shutering Location | 00 | Civil | Civil | Concrete | Block Work | Zone 11 & 12 | C3 & B4 | TX To QZ / 33 To 39 | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0079 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | L To QZ / 22x To 33 | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-10 | 2022-08-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0080 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0081 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-07 | 2022-08-08 | 2022-08-08 | 2022-08-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0082 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-08 | 2022-08-10 | DONE | C |  | Reference coordinates not correct |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0082 | Soil Replacement Layer ( 1 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0083 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0084 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 | A4 | 3X To TX / 14 To15 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0085 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0086 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-11 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0087 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-09 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0088 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0089 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-14 | 2022-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0090 | Reinforced Concrete Foundation Boundries and Starter Bars Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22x To 28x / J To L | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-10 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0091 | Reinforced Concrete Foundation Reinforcement and formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22x To 28x / J To L | FDN | N/A | N/A | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-10 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0092 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-10 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0093 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0094 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-09 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0095 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-10 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0096 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0097 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-09 | 2022-08-10 | 2022-08-14 | 2022-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0098 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-14 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0099 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-15 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0100 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-21 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0101 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C1 | V To Y / 47 To 45 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-22 | 2022-08-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0102 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-16 | 2022-08-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0103 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 | B3 | 27 To 23 / Qx To RY | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-18 | 2022-08-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0104 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 & C3 | QX To TX / 35 To 38 | FDN | N/A | N/A | 2022-08-10 | 2022-08-11 | 2022-08-11 | 2022-08-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0105 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-11 | 2022-08-13 | 2022-08-15 | 2022-08-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0106 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-11 | 2022-08-13 | 2022-08-18 | 2022-08-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0107 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-14 | 2022-08-15 | 2022-08-15 | 2022-08-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0108 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-14 | 2022-08-15 | 2022-08-18 | 2022-08-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0109 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | QX To TX / 34 To 38 | FDN | N/A | N/A | 2022-08-14 | 2022-08-15 | 2022-08-21 | 2022-08-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0110 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-15 | 2022-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0111 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-18 | 2022-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0112 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 33 / H To J | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-18 | 2022-08-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0113 | Reinforced Concrete Piers Reinforcement & formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 33 / J To H | FDN | N/A | N/A | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0002 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | 24 To 25 / N To Q | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0114 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-16 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0115 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0116 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-16 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0117 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 5 | B6 & B5 | QX To RY / 22x To 18 | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0118 | Existing Piles Record | 00 | Civil | Civil | Earthwork | Demolishing | Zone 2 & 3 | A2 & A3 & A4 | 9Y To 13 / 3 To 9X | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 |  | 2022-08-18 | -417 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0119 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B3 & B5 | 16 & 27 / QX To RY | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-18 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0120 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 | 2022-08-21 | 2022-08-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0121 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-16 | 2022-08-17 | 2022-08-22 | 2022-08-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0003 | Installation and Gravity Test of Drainage Pipe lines as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | 24 To 25 / N To Q | FDN | N/A | N/A | 2022-08-18 | 2022-08-20 | 2022-08-21 | 2022-08-21 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0122 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-21 | 2022-08-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0123 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0124 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0125 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-23 | 2022-08-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0004 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | R To TX/ QY To S | FDN | N/A | N/A | 2022-08-15 | 2022-08-17 | 2022-08-22 | 2022-08-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0126 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0127 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 6 & 11 | B3 | QZ To RY /32 To 27 | FDN | N/A | N/A | 2022-08-20 | 2022-08-21 | 2022-08-23 | 2022-08-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0005 | Drainage Pipes Location & Level as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To V / N To Q | FDN | N/A | N/A | 2022-08-20 | 2022-09-01 | 2022-09-03 | 2022-09-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0128 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-21 | 2022-08-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0129 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-22 | 2022-08-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0130 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0131 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 35 To 33 / TX To T | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0132 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B3 | 31 To 32x / QY To RY | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0133 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B3 | 31 To 32x / QY To RY | FDN | N/A | N/A | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0134 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 & 12 | B3 & B4 & C3 | QX To S / 26 To 34 | FDN | N/A | N/A | 2022-08-22 | 2022-08-24 | 2022-08-25 | 2022-08-25 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0135 | Soil Replacement Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-08-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0136 | Soil Replacement Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-08-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0137 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 10 | B3 | QX To RY / 18 To 26 | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-23 | 2022-08-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0138 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 & 15 | B5 | J To L / 16 To 23 | FDN | N/A | N/A | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0139 | Soil Replacement Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0140 | Soil Replacement Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 11 | B4 | 32x To 34 / QY To T | FDN | N/A | N/A | 2022-08-23 | 2022-08-24 | 2022-08-27 | 2022-08-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0141 | Reinforced Concrete Piers formwork & Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32X / H To J | FDN | N/A | N/A | 2022-08-23 | 2022-08-24 | 2022-08-27 | 2022-08-25 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0142 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 10 | B3 | QZ To RY / 18 To 26 | FDN | N/A | N/A | 2022-08-24 | 2022-08-25 | 2022-08-25 | 2022-08-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0006 | Installation for drainage and Electrical pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | R To TX /38 To 35 | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-08-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0007 | Gravity test for Drainage pipes only | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | R To TX /38 To 35 | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-08-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0143 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX To RY | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-27 | 2022-08-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0144 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RX To TX | FDN | N/A | N/A | 2022-08-25 | 2022-08-27 | 2022-08-29 | 2022-08-28 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0145 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 & 15 | B5 | J To L / 16 To 23 | FDN | N/A | N/A | 2022-08-27 | 2022-08-28 | 2022-08-28 | 2022-08-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0146 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 & 15 | B5 | J To L / 16 To 23 | FDN | N/A | N/A | 2022-08-27 | 2022-08-28 | 2022-08-28 | 2022-08-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0147 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 & 10 | B3 | QX To RY / 18 To 26 | FDN | N/A | N/A | 2022-08-27 | 2022-08-28 | 2022-08-28 | 2022-08-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0148 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B3 | QX To RY / 26 To 36 | FDN | N/A | N/A | 2022-08-28 | 2022-08-29 | 2022-08-28 | 2022-08-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0149 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B3 | QX To RY / 26 To 36 | FDN | N/A | N/A | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-08-31 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0150 | Reinforced Concrete Boundries Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 & B5 | PX To K / 18 To 26 | FDN | N/A | N/A | 2022-08-29 | 2022-08-30 | 2022-08-29 | 2022-08-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0151 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | K To QX / 18 To 27 | FDN | N/A | N/A | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-08-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0152 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B3 | QX To RY / 26 To 36 | FDN | N/A | N/A | 2022-08-30 | 2022-08-31 | 2022-08-31 | 2022-09-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0153 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-08-31 | 2022-09-01 | 2022-09-04 | 2022-09-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0154 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-08-31 | 2022-09-01 | 2022-09-04 | 2022-09-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0155 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | RY To T / 32X To 34 | FDN | N/A | N/A | 2022-08-31 | 2022-09-01 | 2022-09-03 | 2022-09-02 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0156 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-09-01 | 2022-09-03 | 2022-09-04 | 2022-09-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0157 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | TX To RX / 33 To 35 | FDN | N/A | N/A | 2022-09-01 | 2022-09-03 | 2022-09-04 | 2022-09-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0008 | Installation and gravity test for drainage pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To V / N To Q | FDN | N/A | N/A | 2022-09-01 | 2022-09-04 | 2022-09-14 | 2022-09-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0009 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | QX To N/ 18 To 21 | FDN | N/A | N/A | 2022-09-01 | 2022-09-03 | 2022-09-03 | 2022-09-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0010 | Installation and gravity test for drainage pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B5 | QX To N/ 18 To 21 | FDN | N/A | N/A | 2022-09-03 | 2022-09-04 | 2022-09-06 | 2022-09-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0158 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 3 | A4 | 13X To 9Y / TX To S | FDN | N/A | N/A | 2022-09-04 | 2022-09-05 | 2022-09-04 | 2022-09-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0159 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-07 | 2022-09-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0160 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-11 | 2022-09-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0161 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 22X To 18 / QZ To K | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-10 | 2022-09-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0162 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 22X To 18 / QZ To K | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-08 | 2022-09-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0163 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-07 | 2022-09-08 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0164 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-06 | 2022-09-07 | 2022-09-11 | 2022-09-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0165 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 32X To 34 / RY To T | FDN | N/A | N/A | 2022-09-07 | 2022-09-08 | 2022-09-10 | 2022-09-09 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0166 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | 32X To 34 / RY To T | FDN | N/A | N/A | 2022-09-07 | 2022-09-08 | 2022-09-10 | 2022-09-09 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0167 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-07 | 2022-09-08 | 2022-09-07 | 2022-09-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0168 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To V / M To PX | FDN | N/A | N/A | 2022-09-08 | 2022-09-10 | 2022-09-08 | 2022-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0011 | Mechanical (Installation and gravity test for drainage pipes) & Survey Inspection (Drainage Pipes Location & Level) as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 | 46X To 44X / 33 To 34 | FDN | N/A | N/A | 2022-09-08 | 2022-09-10 | 2022-09-08 | 2022-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0169 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 26 To 33 / J To H | FDN | N/A | N/A | 2022-09-08 | 2022-09-10 | 2022-09-10 | 2022-09-11 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0170 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 33 / K To QZ | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0171 | PVC Protection cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B4 | 32 To 34 / RY To T | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0172 | PVC Protection Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B4 | 32 To 34 / RY To T | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0012 | Mechanical (Installation and gravity test for FFD Pipes line which added as per attached RFI ) & Survey (Drainage Pipes Location & Level) as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | PX To Q / 30 To 31 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-14 | 2022-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0173 | Wood Planks Extending for Berlin Shoring system | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 | A4 | 8 To TX / 9Y To 15 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0174 | Construction Joint Injectable Hose Installation Between B5a- B5b | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 5 | B5a & B5b | 8 To 20 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-11 | 2022-09-12 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0013 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 & 6 | B2 | M ToQX/ 24 To 28 | FDN | N/A | N/A | 2022-09-10 | 2022-09-11 | 2022-09-13 | 2022-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0175 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0176 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-11 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0177 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-12 | 2022-09-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0178 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0179 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0180 | RC Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C3 | 32X To 38 / 39X To 42X | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-17 | 2022-09-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0181 | Construction Joint Injectable Hose Installation Between B5(B) & B2(A) | 00 | Civil | Civil | Waterproofing | PVC | Zone 5 | B5 & B2 | 22X To 23 / QX To K | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0182 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 26 To 30 / J To H | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0183 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-12 | 2022-09-13 | 2022-09-13 | 2022-09-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0184 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-22 | 2022-09-15 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0185 | Reinforced Concrete piers Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 & C2 | X To Y / 41 TO 44 | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-14 | 2022-09-15 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0014 | Installation and Water test for Drainage Pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 5 & 6 | B2 | M To QZ / 24 To 28 | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-13 | 2022-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0186 | Reinforced Concrete Foundation Boundaries Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | RY To PX / V To 38 | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-17 | 2022-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0187 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0188 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-13 | 2022-09-14 | 2022-09-22 | 2022-09-15 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0189 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-14 | 2022-09-15 | 2022-09-21 | 2022-09-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0190 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-14 | 2022-09-15 | 2022-09-17 | 2022-09-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0191 | Construction Joint Injectable Hose Installation Between B2(A) & B2(B) | 00 | Civil | Civil | Waterproofing | PVC | Zone 6 | B2 | 28 / L To Q | FDN | N/A | N/A | 2022-09-15 | 2022-09-16 | 2022-09-19 | 2022-09-17 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0192 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0193 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-15 | 2022-09-16 | 2022-09-22 | 2022-09-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0194 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 32X To 35 / TX To RY | FDN | N/A | N/A | 2022-09-17 | 2022-09-18 | 2022-09-17 | 2022-09-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0195 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 32X To 35 / TX To RY | FDN | N/A | N/A | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0196 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 22X / K To QZ | FDN | N/A | N/A | 2022-09-18 | 2022-09-19 | 2022-09-19 | 2022-09-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0015 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 12 | C3 | 33 To 38 / RY To 43 | FDN | N/A | N/A | 2022-09-18 | 2022-09-19 | 2022-09-19 | 2022-09-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0197 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 41 To 45 / U To YY | FDN | N/A | N/A | 2022-09-19 | 2022-09-20 | 2022-09-19 | 2022-09-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0198 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 2 | A2 & A3 | 4X To 9 / A To E | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-20 | 2022-09-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0199 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 22X / K To QZ | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-24 | 2022-09-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0200 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 8 | C2 | 41 To 45 / U To YY | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0016 | Installation and gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 12 | C3 | 33 To 38 / RY To 43 | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-25 | 2022-09-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0201 | Underlayment Layer - Geotextile - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0202 | Waterproofing PVC Layer - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0203 | PVC Protection cartmode - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 37 To 38 / TX | FDN | N/A | N/A | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0204 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 3 | A4 | 10X To 12 / Q To S | FDN | N/A | N/A | 2022-09-21 | 2022-09-22 | 2022-09-26 | 2022-09-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0017 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 | 45 To 47 / Z To Y | FDN | N/A | N/A | 2022-09-21 | 2022-09-22 | 2022-09-25 | 2022-09-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0205 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 | A2 & A3 | 8 / 4X | FDN | N/A | N/A | 2022-09-21 | 2022-09-22 | 2022-09-24 | 2022-09-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0206 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-24 | 2022-09-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0207 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-25 | 2022-09-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0208 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 10 & 11 | B4 | 22X To 33 / RY To TX | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-24 | 2022-09-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0209 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 32X To 38 / RY To 42 | FDN | N/A | N/A | 2022-09-22 | 2022-09-24 | 2022-09-25 | 2022-09-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0210 | Reinforced Concrete Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C3 | 32X To 38 / RY To 42 | FDN | N/A | N/A | 2022-09-24 | 2022-09-25 | 2022-09-27 | 2022-09-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0211 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C3 | 32X To 38 / RY To 42 | FDN | N/A | N/A | 2022-09-24 | 2022-09-25 | 2022-09-27 | 2022-09-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0212 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 34 / RY To Q | FDN | N/A | N/A | 2022-09-24 | 2022-09-25 | 2022-09-29 | 2022-09-26 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0213 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-26 | 2022-09-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0214 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-25 | 2022-09-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0215 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0216 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-29 | 2022-09-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0217 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0218 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | 22 To 34 / RY To TX | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0219 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 32X / K To QZ | FDN | N/A | N/A | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0018 | Installation and gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 | 45 To 47 / Z To Y | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2022-09-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0220 | Reinforced Concrete Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 To 35 / RY To TX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-10-03 | 2022-09-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0221 | Soil Replacement Layer ( 1 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0222 | Soil Replacement Layer ( 2 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0223 | Soil Replacement Layer ( 3 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-26 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0224 | Soil Replacement Layer ( 4 ) level & Coordinates Gravel | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-28 | DONE | C |  | Reference level not correct |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0224 | Soil Replacement Layer ( 4 ) level & Coordinates Gravel | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / S To PX | FDN | N/A | N/A | 2022-09-29 | 2022-10-01 | 2022-10-01 | 2022-10-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0225 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0226 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0227 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0228 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 32X / H To J | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-10-05 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0229 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-27 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0230 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-26 | 2022-09-27 | 2022-09-29 | 2022-09-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0231 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44 To 45 / Z ToV | FDN | N/A | N/A | 2022-09-27 | 2022-09-28 | 2022-09-27 | 2022-09-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0232 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | 22 To 34 / RY To TX | FDN | N/A | N/A | 2022-09-27 | 2022-09-28 | 2022-10-02 | 2022-09-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0233 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 23 To 32X / K To QZ | FDN | N/A | N/A | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0234 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | 22 To 34 / RY To TX | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-03 | 2022-09-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0235 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 28 To 32X / J To L | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0236 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 | B5 | 17 To 22X / K To QZ | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0237 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-01 | 2022-09-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0238 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-03 | 2022-09-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0239 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-01 | 2022-09-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0240 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-09-29 | 2022-09-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0241 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-09-28 | 2022-09-29 | 2022-10-01 | 2022-09-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0242 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 | C1 | 44X To 47 / Y To Z | FDN | N/A | N/A | 2022-09-29 | 2022-10-01 | 2022-10-02 | 2022-10-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0019 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 28 To 34 / RY To QX | FDN | N/A | N/A | 2022-09-29 | 2022-10-01 | 2022-10-06 | 2022-10-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0243 | Construction Joint injectable Hose installation Between B2(B) & C3(A) / C4 & C3(B) / C3(A) & C3(B) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | B2 & C3 & C4 | U To V / 39 To 42 & Y To X / 39 To 42 & 38 To RY | FDN | N/A | N/A | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0244 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 28 To 32X / J To L | FDN | N/A | N/A | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0245 | RC Foundation Waterproofing Bitumen ( 3 Coats ) | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 | B5 | 18 To 22X / K To QS | FDN | N/A | N/A | 2022-10-02 | 2022-10-03 | 2022-10-05 | 2022-10-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0246 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-02 | 2022-10-03 | 2022-10-03 | 2022-10-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0247 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 9 & 10 | B6 & B8 | 15 To 22X / RY To TX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0248 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-04 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0249 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0250 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0251 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-04 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0252 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0253 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-10 | 2022-10-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0020 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B3A & B6B | 22X To 27 / Q To RY | FDN | N/A | N/A | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0254 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0255 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0256 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0257 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 33 / L To H | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0258 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 33 / TX To RY | FDN | N/A | N/A | 2022-10-04 | 2022-10-05 | 2022-10-05 | 2022-10-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0259 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0260 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0261 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-10 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0262 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0263 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-10 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0264 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-08 | 2022-10-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0265 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-05 | 2022-10-06 | 2022-10-10 | 2022-10-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0266 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-08 | 2022-10-09 | 2022-10-13 | 2022-10-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0267 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A2 & A3 & A4 | 4X To TX / A To B | FDN | N/A | N/A | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0268 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | SX To TX / B To E | FDN | N/A | N/A | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0269 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 24 To 34 / RY To TX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0270 | Construction Joint injectable Hose installation Between B2/B3 & C3/B3 | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 & B3 & C3 | 23 To 35 / Q To RY | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-13 | 2022-10-11 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0271 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0272 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0273 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-13 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0274 | Reinforced Concrete Piers & Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 33 To 38 / RY To M | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0021 | Installation and gravity test for drainage pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 28 To 34 / RY To QX | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0021 | Installation and gravity test for drainage pipes as per Highlighted | 01 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 28 To 34 / RY To QX | FDN | N/A | N/A | 2022-10-12 | 2022-10-13 | 2022-10-13 | 2022-10-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0275 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 10 | B6 | 21 To 22 / RY To SY | FDN | N/A | N/A | 2022-10-09 | 2022-10-10 | 2022-10-10 | 2022-10-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0276 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 27 To W / RY To QZ | FDN | N/A | N/A | 2022-10-10 | 2022-10-11 | 2022-10-13 | 2022-10-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0022 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 33 To 34 / RY To RY | FDN | N/A | N/A | 2022-10-10 | 2022-10-11 | 2022-10-13 | 2022-10-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0023 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 43 To 25 / K To 41 | FDN | N/A | N/A | 2022-10-10 | 2022-10-11 | 2022-10-17 | 2022-10-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0277 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0278 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-17 | 2022-10-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0279 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B3-B | 34 To 28 / QX To RY | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-16 | 2022-10-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0280 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0281 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0282 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0283 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-12 | 2022-10-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0284 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0285 | Reinforced Concrete Piers and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | C3 | W To Y / RY To 41 | FDN | N/A | N/A | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0286 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 4 | A3 & B7 | 10X To 11 / K To Q | FDN | N/A | N/A | 2022-10-12 | 2022-10-13 | 2022-10-12 | 2022-10-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0287 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 8 | C2 | 42 To 44 / U To YY | FDN | N/A | N/A | 2022-10-15 | 2022-10-16 | 2022-10-16 | 2022-10-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0288 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10Y / RY To QX | FDN | N/A | N/A | 2022-10-12 | 2022-10-13 | 2022-10-12 | 2022-10-14 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0289 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 38 To 31X / N To RX | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-16 | 2022-10-16 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0290 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-13 | 2022-10-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0291 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-13 | 2022-10-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0292 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-16 | 2022-10-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0024 | Installation and Water Leakage test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B3A & B6B | 22X To 27 / Q To RY | FDN | N/A | N/A | 2022-10-13 | 2022-10-15 | 2022-10-15 | 2022-10-17 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0024 | Installation and Water Leakage test for drainage pipes as per Highlighted | 01 | MEP | Mech | Pluming | Drainage | Zone 10 | B3A & B6B | 22X To 27 / Q To RY | FDN | N/A | N/A | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0293 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 23 To 28 / QX To RY | FDN | N/A | N/A | 2022-10-16 | 2022-10-17 | 2022-10-17 | 2022-10-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0294 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 23 To 28 / QX To RY | FDN | N/A | N/A | 2022-10-16 | 2022-10-17 | 2022-10-19 | 2022-10-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0295 | Construction Joint injectable Hose installation Between B3(B) & B3(A) | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B3 | 28 / QX To RY | FDN | N/A | N/A | 2022-10-17 | 2022-10-18 | 2022-10-17 | 2022-10-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0296 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-17 | 2022-10-18 | 2022-10-17 | 2022-10-19 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0297 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-17 | 2022-10-24 | 2022-10-24 | 2022-10-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0298 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-18 | 2022-10-19 | 2022-10-19 | 2022-10-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0299 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-19 | 2022-10-20 | 2022-10-23 | 2022-10-21 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0300 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 24 To 32X / L To Q | FDN | N/A | N/A | 2022-10-19 | 2022-10-20 | 2022-10-23 | 2022-10-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0301 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 32 / M To Q | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0302 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 12 / TX To SX | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0303 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 32 To 35 / M To QX | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0304 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 & 4 & 9 | B7 & B8 & A4 | 11 To 13 / K To S | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-23 | 2022-10-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0305 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 11 To 10X / QX To SX | FDN | N/A | N/A | 2022-10-20 | 2022-10-21 | 2022-10-24 | 2022-10-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0306 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | 11 To 10X / QX To SX | FDN | N/A | N/A | 2022-10-20 | 2022-10-31 | 2022-10-31 | 2022-11-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0307 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-25 | 2022-10-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0308 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 & 10 | B6 & B8 | 15 To 22 / TX To R | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-25 | 2022-10-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0309 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 4 | A3 & B7 | 10X To 11 / K To Q | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-23 | 2022-10-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0310 | Reinforced Concrete Walls Reinforcement to level -4.775 | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 40X To 42 / 36 To 38 | FDN | N/A | N/A | 2022-10-22 | 2022-10-23 | 2022-10-23 | 2022-10-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0311 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 & B8 | 16 To 22 / TX To QX | FDN | N/A | N/A | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0312 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 & A2 | 2 To 6 / CX To 10Y | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-25 | 2022-10-26 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0313 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 & A2 | 3 To 4X / A To C | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-25 | 2022-10-26 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0314 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 35 / RY To TX | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-27 | 2022-10-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0025 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 29 To 31 / M To L | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0026 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 36 To 38 / RY To QY | FDN | N/A | N/A | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0315 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 24 To 35 / RY To SY | FDN | N/A | N/A | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0316 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0317 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-10-27 | 2022-10-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0318 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-10-30 | 2022-10-28 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0319 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-10-27 | 2022-10-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0027 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 41 To 44 / U To X | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-11-01 | 2022-10-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0001 | Duct Bank Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | 38 To 35 / QX To PX | FDN | N/A | N/A | 2022-10-26 | 2022-10-27 | 2022-11-01 | 2022-10-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0320 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 25 To 32X / M To QX | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-30 | 2022-10-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0321 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-30 | 2022-10-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0322 | Soil Replacement Layer ( 1 & 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-11-01 | 2022-10-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0323 | Soil Replacement Layer ( 1 & 2 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-31 | 2022-10-30 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0324 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 33 To 38 / N To RY | FDN | N/A | N/A | 2022-10-27 | 2022-10-29 | 2022-10-30 | 2022-10-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0325 | Soil Replacement Layer ( 2 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-10-30 | 2022-10-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0326 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0327 | Soil Replacement Layer ( 3 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0328 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-10-31 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0329 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 3 & 9 | A4 & B8 | 11 To 15 / TX To RY | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0330 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 9 | B8 | 13 To 16 / TX To RY | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0331 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 4 & 9 & 13 | B7 & B8 | 12 To 14 / H To S | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | C |  | Survey Supervision |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0331 | Excavation for Bottom Level & Coordinate | 01 | Civil | Civil | Earthwork | Excavation | Zone 4 & 9 & 13 | B7 & B8 | 12 To 14 / H To S | FDN | N/A | N/A | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-07 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0332 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-29 | 2022-10-30 | 2022-11-01 | 2022-10-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0333 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0334 | Construction Joint injectable Hose installation Between B3 & B6 | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B3 | 22X To 23 / QZ To RY | FDN | N/A | N/A | 2022-10-30 | 2022-10-31 | 2022-11-02 | 2022-11-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0335 | Soil Replacement Layer ( 4 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0336 | Soil Replacement Layer ( 2 & 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0337 | Soil Replacement Layer ( 2 & 3 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-10-31 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0338 | Soil Replacement Layer ( 3 & 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0339 | Soil Replacement Layer ( 3 & 4 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-10-31 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0340 | Soil Replacement Layer ( 4 & 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0341 | Soil Replacement Layer ( 4 & 5 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-10-31 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0342 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 25 To 32X / M To Q | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0343 | Reinforced Concrete Piers and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 33 / RY To QZ | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0344 | Soil Replacement Layer ( 5 & 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0345 | Soil Replacement Layer ( 5 & 6 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-05 | 2022-11-06 | 2022-11-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0346 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-01 | 2022-11-01 | 2022-11-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0347 | Soil Replacement Layer ( 6 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | PX To S / 10X To 12 | FDN | N/A | N/A | 2022-10-31 | 2022-11-05 | 2022-11-06 | 2022-11-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0348 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | S To Q / 9Y To 12 | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0349 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 3 | A4 | S To Q / 9Y To 12 | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0350 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0351 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0352 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 | A To B / 3X To 4 | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-02 | 2022-11-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0353 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 23 / TX To Z | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-01 | 2022-11-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0028 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B6 | 20 To 22X / RY To QZ | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-02 | 2022-11-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0029 | Sleeve Pipes Location & Level as per Highlighted ( Survey Inspection ) and Mechanical Installation | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | RY To 32X | FDN | N/A | N/A | 2022-11-01 | 2022-11-02 | 2022-11-06 | 2022-11-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0030 | Installation and Water Leakage test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 41 To 44 / U To X | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-06 | 2022-11-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0354 | Reinforced Concrete Piers and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 28X / H To 47X | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0355 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-02 | 2022-11-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0356 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-02 | 2022-11-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0357 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 35 / QX To RY | FDN | N/A | N/A | 2022-11-03 | 2022-11-04 | 2022-11-07 | 2022-11-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0358 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0359 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 & 3 | A3 & A4 | 11 To B/ S To K | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0360 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 & 4 | A3 & A4 | 12 To 9Y / TX To M | FDN | N/A | N/A | 2022-11-02 | 2022-11-03 | 2022-11-03 | 2022-11-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0361 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0362 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 23 / QX To TX | FDN | N/A | N/A | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0363 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3 & A4 & B7 | 9Y To 12 / TX To M | FDN | N/A | N/A | 2022-11-06 | 2022-11-09 | 2022-11-10 | 2022-11-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0364 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 3 & 9 | A4 & B8 | TX / 12 To 16 | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-09 | 2022-11-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0365 | "Stair 11" To Level (-5.875) Level and Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / RX To QX | S.B | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0031 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C6 | 37 / RX To QZ | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0032 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B6 | 20 To 22X / RY To QZ | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0366 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 4 & 9 & 13 | B7 & B8 | 14 To 16 / RY To J | FDN | N/A | N/A | 2022-11-06 | 2022-11-07 | 2022-11-07 | 2022-11-08 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0367 | Reinforced Concrete Piers Formwork & Walls To Level ( -4.775 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0368 | Reinforced Concrete Piers Formwork To Level ( -4.775 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 25 To 23X / Q To M | FDN | N/A | N/A | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0369 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX To RY | FDN | N/A | N/A | 2022-11-07 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0033 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 5 | B2 | 27 / M | FDN | N/A | N/A | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0370 | Reinforced Concrete Walls Formwork for H Vac Opening | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 42 / X To YY | FDN | N/A | N/A | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0371 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0372 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-08 | 2022-11-09 | 2022-11-09 | 2022-11-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0373 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-13 | 2022-11-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0374 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-13 | 2022-11-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0034 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 21 / QX To RY | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-10 | 2022-11-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0375 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3 & A4 & B7 | 9Y To 12 / TX To M | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-10 | 2022-11-11 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0376 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 | A1 | A To B / 1 To 3 | FDN | N/A | N/A | 2022-11-09 | 2022-11-10 | 2022-11-10 | 2022-11-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0377 | Reinforced Concrete Piers and Walls Reinforcement to Level (-4.775) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 25 To 35 / TX To RY | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0378 | Underlayment Layer - Geotextile (Walls) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 9Y To 11 / TX To QX | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0379 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0380 | Soil Replacement Layer ( 1 ) Compaction Work ( Sand + Gravel ) | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0381 | PVC Screed Protection - Surface Protection | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3 & A4 & B7 | 9Y To 12 / TX To M | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0382 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0383 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0384 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-10 | 2022-11-11 | 2022-11-13 | 2022-11-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0385 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0386 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-16 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0387 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0388 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-16 | 2022-11-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0389 | Wood Planks Extending for Berlin Wall Shoring System | 00 | Civil | Civil | Shoring | Berlin Wall | Zone 1 | A1 | 2X / 4 To A | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0390 | Waterproofing PVC Layer ( for Walls ) – to Level ( -6.25 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 9Y To 10Y / TX | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0391 | PVC Protection & Cartmode – to Level ( -6.25 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 9Y To 10Y / TX | FDN | N/A | N/A | 2022-11-12 | 2022-11-13 | 2022-11-13 | 2022-11-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0392 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-13 | 2022-11-14 | 2022-11-13 | 2022-11-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0393 | Underlayment Layer - Geotextile ( Sump Walls & Floor ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 10Y / QX To RX | FDN | N/A | N/A | 2022-11-13 | 2022-11-14 | 2022-11-14 | 2022-11-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0394 | Waterproofing PVC Layer ( Sump Walls & Floor ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 10Y / QX To RX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0395 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0396 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0397 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0398 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0399 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-17 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0400 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0401 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 42 To 45 / V To Y | L.G | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0402 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / V To Z | L.G | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-15 | 2022-11-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0403 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 25 To 27 / M To PX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0404 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 25 To 27 / M To PX | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-17 | 2022-11-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0405 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-15 | 2022-11-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0406 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0407 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0408 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0409 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0410 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 3 To 4X | FDN | N/A | N/A | 2022-11-14 | 2022-11-20 | 2022-11-21 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0411 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 | C3 | PX To QY / Z To U | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0412 | Reinforced Concrete Sub Basement Bottom Layer Reinforcement to Level ( -5.875 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / RY To QS | S.B | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0413 | Reinforced Concrete Sub Basement Top Layer Reinforcement to Level ( -5.875 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / RY To QS | S.B | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0414 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 24 / QX To SY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0415 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A1 & A2 & A3 | N To TX / A To EY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-16 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0035 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22 / R To RY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-19 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0036 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B6 | 16 To 18 / QZ To RY | FDN | N/A | N/A | 2022-11-15 | 2022-11-16 | 2022-11-19 | 2022-11-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0416 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 16 To 24 / TX To S | FDN | N/A | N/A | 2022-11-16 | 2022-11-17 | 2022-11-16 | 2022-11-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0417 | PVC Protection - Surface Preparation Screed & Cartmode ( Sump Walls & floor ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10X To 10Y / QX To RX | FDN | N/A | N/A | 2022-11-16 | 2022-11-17 | 2022-11-17 | 2022-11-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0418 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B3 & B4 | 23 To 34 / QX To TX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-20 | 2022-11-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0419 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22X To 28X / H To G | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-17 | 2022-11-20 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0419 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 01 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22X To 28X / H To G | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0002 | Installation of Duct Bank Pipe Lines | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | 38 To 35 / QX To PX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-21 | 2022-11-20 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0002 | Installation of Duct Bank Pipe Lines | 01 | MEP | Elec | Elec | Power | Zone 7 | C3 | 38 To 35 / QX To PX | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-10 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0420 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-20 | 2022-11-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0421 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-17 | 2022-11-19 | 2022-11-21 | 2022-11-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0422 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-23 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0423 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-22 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0424 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-22 | 2022-11-21 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0425 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-23 | 2022-11-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0426 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-24 | 2022-11-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0426 | RC Foundation Waterproofing Bitumen | 01 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 | B2 | 23 To 33 / L To QZ | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0427 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-24 | 2022-11-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0427 | RC Foundation Waterproofing Bitumen | 01 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B3 | 23 To 33 / QX To RY | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0428 | Reinforced Concrete Foundation Bottom Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 9Y To 10Z / TX To 9 | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0428 | Reinforced Concrete Foundation Bottom Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 9Y To 10 / TX To 9 | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-22 | 2022-11-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0037 | Installation of drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0037 | Installation of pluming Network as per Highlighted | 01 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-05 | 2022-12-08 | 2022-12-08 | 2022-12-09 | DONE | B | L
1176-FSL-CP01-CN-AT-CIR-ST-0429 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 12 | C3 & C4 | 33 To 38 / N To RX | FDN | N/A | N/A | 2022-11-19 | 2022-11-20 | 2022-11-20 | 2022-11-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0430 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-23 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0431 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 13 To 14 / J To S | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0432 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | A4 & B8 | 13 To 15 / SX To TX | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-21 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0433 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0434 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-21 | 2022-11-22 | 2022-11-22 | 2022-11-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0435 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-23 | 2022-11-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0436 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-27 | 2022-11-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0437 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0438 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-22 | 2022-11-23 | 2022-11-27 | 2022-11-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0439 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A4-B & A3-A | A To 10Y / 6 To TX | FDN | N/A | N/A | 2022-11-23 | 2022-11-24 | 2022-11-24 | 2022-11-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0440 | Soil Replacement Layer( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To D / 2X To 4X | FDN | N/A | N/A | 2022-11-23 | 2022-11-24 | 2022-11-24 | 2022-11-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0038 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | SX To TX / 9Y To 10 | FDN | N/A | N/A | 2022-11-23 | 2022-11-27 | 2022-11-30 | 2022-11-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0441 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0442 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | A To D / 1 To 3 | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0443 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-24 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0444 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 4 & 9 | B7 & B8 | 14 To 18 / J To TX | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0445 | Soil Replacement Layer( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0446 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 4 & 9 | B7 & B8 & A2 | 10X To 17 / J To TX | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0447 | Soil Replacement Layer( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To C / 2X To 4X | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-28 | 2022-11-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0448 | Soil Replacement Layer( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 | A To D / 2X To 4X | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-29 | 2022-11-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0449 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 17 To 23 / TX To S | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0450 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | S/31 To 33 | FDN | N/A | N/A | 2022-11-24 | 2022-11-26 | 2022-11-27 | 2022-11-27 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0039 | Installation and survey inspection of sleeve pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | T To Sy / 38 | FDN | N/A | N/A | 2022-11-26 | 2022-11-29 | 2022-12-01 | 2022-11-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0451 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S / 37 | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0452 | Reinforced Concrete Cloumns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 35 / RY To 4X | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-27 | 2022-11-29 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0453 | Construction Joint injectable Hose installation Between B5 & B6 | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B5 & B6 | 16 To 23 / Q To QX | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-28 | 2022-11-29 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0454 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 12 To 15 / TX To RX | FDN | N/A | N/A | 2022-11-27 | 2022-11-28 | 2022-11-27 | 2022-11-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0455 | Reinforced Concrete Walls Reinforcement to Level ( -4.775 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / QX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0456 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 15 To 24 / RY To TX | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0457 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 12 To 15 / TX To RX | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-28 | 2022-11-30 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0458 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10 To 9Y / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-11-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0459 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0460 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-12-03 | 2022-11-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0461 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-28 | 2022-11-29 | 2022-11-29 | 2022-11-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0462 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 12 To 15 / TX To RX | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-29 | 2022-12-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0463 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | 1X To 5 / A To 9Y | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-29 | 2022-12-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0464 | Plain Concrete Foundation Top level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 4 | A3 & B7 | K To N / 10Y To D | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-29 | 2022-12-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0465 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 9Y To 10 / TX To 9 | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-11-30 | 2022-12-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0466 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-29 | 2022-11-30 | 2022-12-03 | 2022-12-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0467 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 16 / TX To RX | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0468 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0469 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-03 | 2022-12-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0470 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0471 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-03 | 2022-12-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0472 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QZ / 17 To 27 | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-01 | 2022-12-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0473 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QZ / 17 To 27 | FDN | N/A | N/A | 2022-11-30 | 2022-12-01 | 2022-12-03 | 2022-12-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0474 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22X / RY To QZ | FDN | N/A | N/A | 2022-12-01 | 2022-12-03 | 2022-12-05 | 2022-12-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0475 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 16 / TX To RX | FDN | N/A | N/A | 2022-12-01 | 2022-12-03 | 2022-12-03 | 2022-12-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0476 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 35 / TX | FDN | N/A | N/A | 2022-12-01 | 2022-12-03 | 2022-12-03 | 2022-12-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0040 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 17 To 23 / RY To QX | FDN | N/A | N/A | 2022-12-03 | 2022-12-04 | 2022-12-08 | 2022-12-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0477 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4-B & B8-A | 11 To 14 / RY To TX | FDN | N/A | N/A | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-05 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0477 | Reinforced Concrete Foundation Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4-B & B8-A | 11 To 14 / RY To TX | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-11 | 2022-12-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0478 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 16 / TX To RX | FDN | N/A | N/A | 2022-12-03 | 2022-12-04 | 2022-12-04 | 2022-12-05 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0479 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4-B | 11 To 13X / TX To S | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-04 | 2022-12-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0480 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0481 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-12 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0482 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0483 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / SY To RY | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-12 | 2022-12-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0484 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0484 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | FDN | N/A | N/A | 2022-12-05 | 2022-12-06 | 2022-12-06 | 2022-12-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0485 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 TO 16 / RY To RX | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-08 | 2022-12-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0486 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B3 | QZ To RY / 23 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0487 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B3 | QZ To RY / 23 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0488 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 | B2 | L To QZ / 27 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-05 | 2022-12-05 | 2022-12-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0489 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 | B2 | L To QZ / 27 To 33 | FDN | N/A | N/A | 2022-12-04 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0490 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 & 3 | B7 & A1 & A2 | A To D / 1 To 4 & L To P / 10 To 12 | FDN | N/A | N/A | 2022-12-05 | 2022-12-06 | 2022-12-06 | 2022-12-07 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0491 | Exhaust Duct Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 43 To 41 / X To XY | FDN | N/A | N/A | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-07 | DONE | C |  |  |  | N/A
1176-FSL-CP01-CN-AT-CIR-ST-0491 | Exhaust Duct Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 43 To 41 / X To XY | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | N/A
1176-FSL-CP01-CN-AT-CIR-ST-0492 | Reinforced Concrete Foundation Bottom Layer Reinforcement & Columns Starter bars & Grade Beams Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | S To T / 11 To 13X | FDN | N/A | N/A | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0493 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 11 To 15 / K To RY | FDN | N/A | N/A | 2022-12-06 | 2022-12-07 | 2022-12-07 | 2022-12-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0041 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 32 To 33 / S To SY | FDN | N/A | N/A | 2022-12-06 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0494 | Reinforced Concrete Columns &Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4 & B8 | 10 To 14 / TX To SX | FDN | N/A | N/A | 2022-12-07 | 2022-12-08 | 2022-12-08 | 2022-12-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0495 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B8 | TX / 33 To 35 | FDN | N/A | N/A | 2022-12-07 | 2022-12-08 | 2022-12-07 | 2022-12-09 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0496 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 & 4 | A1 & A2 & B7 | 2X To 5 / A To C & M To PX / 10X To 12 | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0497 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-08 | 2022-12-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0498 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0499 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-12 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0500 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0501 | Soil Replacement Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-11 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0502 | Soil Replacement Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0503 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-11 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0504 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-13 | 2022-12-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0505 | Reinforced Concrete Tie Beams Foundation Top Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | S To RX / 36 To 37 | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-15 | 2022-12-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0506 | Reinforced Concrete Grade Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | RY To TX / 35 To 24 | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-11 | 2022-12-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0507 | Planted Steel Bars in Column | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S / 36 | L.G | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-18 | 2022-12-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0042 | Gravity Test for Drainage Network as Attached | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-08 | 2022-12-10 | 2022-12-10 | 2022-12-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0003 | Duct Bank Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 35 To 36 | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-13 | 2022-12-12 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0003 | Duct Bank Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 01 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 39 To 40 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-22 | 2022-12-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0508 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 & 4 | A1 & A2 & B7 | 2X To 4X / A To C & K To PX / 10 To 13 | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-13 | 2022-12-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0509 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 | 3X To 4 / A To B | FDN | N/A | N/A | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0510 | Soil Replacement Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0511 | Soil Replacement Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0512 | Soil Replacement Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0513 | Soil Replacement Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0514 | Soil Replacement Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0515 | Soil Replacement Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-14 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0516 | Soil Replacement Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0517 | Soil Replacement Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0518 | Soil Replacement Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0519 | Soil Replacement Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0520 | Soil Replacement Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0521 | Soil Replacement Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0522 | Soil Replacement Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0523 | Soil Replacement Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0524 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22X / RY To QZ | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0525 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | RY To TX / 9Y To 10 | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-11 | 2022-12-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0043 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4-B | 10 To 11 / RY To TX | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0004 | Installation of Duct Bank Pipes as Highlighted | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 35 To 36 | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-13 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0004 | Installation of Duct Bank Pipes as Highlighted | 01 | MEP | Elec | Elec | Power | Zone 7 & 10 & 11 | C3 & B4 | RY To P / 20 To 33 | L.G | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0005 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 & 12 | C1 & C2 & C3 | 42 To 47 / U To Z | FDN | N/A | N/A | 2022-12-10 | 2022-12-14 | 2022-12-14 | 2022-12-15 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0526 | Reinforced Concrete Piers and Walls Tie beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22X / RY To QZ | FDN | N/A | N/A | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-14 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0044 | Installation and Gravity Test for pluming network as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4-B | 10 To 11 / RY To TX | FDN | N/A | N/A | 2022-12-11 | 2022-12-12 | 2022-12-15 | 2022-12-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0006 | Installation of Access Control Conduit as Highlighted | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | S To 35 | FDN | N/A | N/A | 2022-12-12 | 2022-12-13 | 2022-12-15 | 2022-12-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0527 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 TO 16 / TX To RX | FDN | N/A | N/A | 2022-12-12 | 2022-12-13 | 2022-12-13 | 2022-12-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0528 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 1 To 2X / A To CX | FDN | N/A | N/A | 2022-12-13 | 2022-12-14 | 2022-12-14 | 2022-12-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0529 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 22X To 27/ H To G | FDN | N/A | N/A | 2022-12-13 | 2022-12-20 | 2022-12-21 | 2022-12-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0530 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 1 To 2X / A To CX | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0531 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4 -B1 | 10 To 14 / S To T | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0532 | Reinforced Concrete Foundation Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 13X / S To T | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0533 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 To 16 / RY To S | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-15 | 2022-12-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0534 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 & B7 | 13 To 16 / RX To S | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-15 | 2022-12-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0045 | Gravity Test for Drainage Network after concrete pouring as Attached | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-27 | 2022-12-16 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0045 | Gravity Test for Drainage Network after concrete pouring as Attached | 01 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | 35 To 38 / RY To TX | FDN | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-09 | 2023-08-07 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0046 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 32 / H To K | FDN | N/A | N/A | 2022-12-14 | 2022-12-15 | 2022-12-18 | 2022-12-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0535 | Reinforced Concrete Lower Ground Slab Reinforcement Bottom Layer | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 47 To 42X / Z To V | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0536 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28 To 31 / H To G | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-15 | 2022-12-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0537 | Lower Ground Slab Coordinates & Top Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 47 To 42X / U To Z | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0538 | Plain Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 | 3 To 6 / A To B | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0539 | Construction Joint injectable Hose installation Between A4-B & A4-A | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 10 To 10X / TX To RY | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0540 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0541 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0542 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | U To Z / 47 To 42 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-18 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0543 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / 34 | FDN | N/A | N/A | 2022-12-15 | 2022-12-17 | 2022-12-21 | 2022-12-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0544 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 3 / A To CY | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0545 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0546 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0547 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32 / G To K | FDN | N/A | N/A | 2022-12-17 | 2022-12-21 | 2022-12-24 | 2022-12-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0548 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32 / G To K | FDN | N/A | N/A | 2022-12-17 | 2022-12-21 | 2022-12-24 | 2022-12-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0549 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-17 | 2022-12-18 | 2022-12-18 | 2022-12-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0550 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47 To 46X / Z To V | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0551 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0552 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 18 / J To RY | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0553 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 18 / J To RY | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-20 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0554 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 32X / J To G | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0555 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 & 11 | B2 & B3 | 33 To 27 / RY To L | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-19 | 2022-12-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0556 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0557 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 11 To 18 / J To RY | FDN | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-20 | 2022-12-21 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0558 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 6 & 11 | B2 & B3 | 33 To 27 / RY To L | FDN | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0559 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0560 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 42 To 46 / U To Z | L.G | N/A | N/A | 2022-12-19 | 2022-12-20 | 2022-12-20 | 2022-12-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0561 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0562 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0563 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B4 | 33 To 25 / RY To SY | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0564 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 & 10 | B4 & B6 | 25 To 18 / RY To TX | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0565 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0566 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / Q To S | S.B | N/A | N/A | 2022-12-20 | 2022-12-21 | 2022-12-21 | 2022-12-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0567 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-21 | 2022-12-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0568 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0569 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B4 | 33 To 25 / RY To SY | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-21 | 2022-12-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0570 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 30 / G To L | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0571 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 4 & 9 | B7 & B8 | R To J / 14 To 16 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-21 | 2022-12-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0572 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 13 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0573 | PVC Protection - Surface Preparation Screed & Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | B8 | 13 To 16 / TX To RY | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0574 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 43 To 47 / V To Y | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0575 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0576 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0577 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 16 To 11 / J To RX | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0578 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | A To CY / 1 To 6 | FDN | N/A | N/A | 2022-12-21 | 2022-12-22 | 2022-12-24 | 2022-12-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0579 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S TO 36 | FDN | N/A | N/A | 2022-12-21 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0580 | Underlayment Layer - Geotextile – Vertical to Level “77.60” | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4-A | 9Y To 10 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0581 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0582 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | B To D / 5 To 7 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0583 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | S To QX / 38 | S.B To L.G | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-25 | 2022-12-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0584 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 & 10 | B4 & B6 | 25 To 18 / RY To TX | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0585 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To L | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0586 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To L | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0587 | Reinforced Concrete Stair Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | S To QX / 38 | S.B To L.G | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0588 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | QX To RY / 17 To 23 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0589 | Plain Concrete Foundation Top Level & Coordinates & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 & A4 | A To E / 5 To 8 | FDN | N/A | N/A | 2022-12-22 | 2022-12-24 | 2022-12-24 | 2022-12-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0590 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To H | L.G | N/A | N/A | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0591 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To 26 / J To H | L.G | N/A | N/A | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-26 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0007 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 | C1 | 42 To 47 / V To Z | FDN | N/A | N/A | 2022-12-24 | 2022-12-29 | 2022-12-31 | 2022-12-30 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0592 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-24 | 2022-12-25 | 2022-12-25 | 2022-12-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0593 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 9 | A4-B | 10Z To 14 / S To TX | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-26 | 2022-12-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0594 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0595 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 & 7 | B1 & B2 | 24 To 32 / PX To H | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-25 | 2022-12-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0596 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 5 & 6 & 7 | B1 & B2 | 24 To 32 / PX To H | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-26 | 2022-12-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0597 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 30 / G | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0598 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 30 / G | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0599 | Reinforced Concrete Grade Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 31 To 34 / RY To S | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0600 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0601 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-25 | 2022-12-26 | 2022-12-28 | 2022-12-27 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0601 | Backfilling Layer ( 1 ) Compaction Work | 01 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-28 | 2022-12-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0602 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0603 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0604 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0605 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0606 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 | B1 | 26 To 30 / H To G | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0607 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 | B1 | 26 To 30 / H To G | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0608 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 17 / RX To SY | FDN | N/A | N/A | 2022-12-26 | 2022-12-27 | 2022-12-27 | 2022-12-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0609 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28 To 30 / G | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2022-12-28 | 2022-12-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0610 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 28 To 30 / G | FDN | N/A | N/A | 2022-12-27 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0611 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 & A2 | 10Y To CX / 2 To 6 | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0047 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | K To G / 23 To 32 | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2023-01-01 | 2022-12-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0612 | Waterproofing PVC Layer – Vertical to Level “77.60” | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4-A | 9Y To 10 | FDN | N/A | N/A | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0613 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-27 | 2022-12-29 | 2022-12-31 | 2022-12-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0614 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 & A3 | C To E / 5 To 7 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-28 | 2022-12-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0615 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / Z | L.G | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0616 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 46 / W To X | L.G | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0617 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 15 To 16 / SX To TX | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0618 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 & A3 | C To E / 5 To 7 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-29 | 2022-12-30 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0619 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-28 | 2022-12-29 | 2022-12-31 | 2022-12-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0620 | PVC Protection – Cartmode _Vertical to Level “77.60” | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4-A | 9Y To 10 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0621 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 & A3 | C To E / 5 To 7 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0622 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | RY To QX / 16 To 13X | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-29 | 2023-01-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0623 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | Z To X / 41 To 44 | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0624 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0624 | Backfilling Layer ( 3 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0625 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0626 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 16 To 14 / S To TX | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0627 | Reinforced Concrete Walls Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 34 / SX To TX | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-01 | 2023-01-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0628 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 30 / G | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-03 | 2023-01-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0629 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0630 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0631 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2022-12-31 | 2023-01-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0632 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 & B6 | 21 To 28 / RY To T | FDN | N/A | N/A | 2022-12-29 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0048 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 & B3 | T To RX / 33 To 34 | FDN | N/A | N/A | 2022-12-29 | 2022-12-31 | 2023-01-03 | 2023-01-01 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0048 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 & B3 | T To RX / 33 To 34 | FDN | N/A | N/A | 2023-05-25 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0633 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0634 | Reinforced Concrete Piers and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B6 | 18 To 22x / QZ To RY | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0635 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 24 To 32 / G To J | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0636 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0637 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0638 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0639 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 28 / S To T | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-03 | 2023-01-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0640 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | A To 10 / 9 To SX | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0641 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 32 / G To J | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0642 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 18 To 31 / G | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0643 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 23 To 32 / G To J | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0644 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | A To CX / CZ To 3 | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0645 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | 31 To 35 / RY To SY | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-01 | 2023-01-02 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0646 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork Boundaries | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 2X / A To D | FDN | N/A | N/A | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0049 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | J To G / 22X To 33 | FDN | N/A | N/A | 2022-12-31 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0647 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 47 To 42X / Y To V | L.G To G.F | N/A | N/A | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0648 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 | 12 To 10Y / K To QX | FDN | N/A | N/A | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0649 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 & A3 | 2 To 8 / 11 To A | FDN | N/A | N/A | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-01-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0650 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | A To 10 / 9 To SX | S.B To L.G | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-03 | 2023-01-04 | DONE | B |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0650 | Reinforced Concrete Columns Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | A To 10 / 9 To SX | S.B To L.G | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0050 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To 34 / L To N | FDN | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-11 | 2023-01-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0651 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 12 To 18 / K To RY | FDN | N/A | N/A | 2023-01-02 | 2023-01-09 | 2023-01-09 | 2023-01-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0652 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | W / 43 | L.G To G.F | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-04 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0653 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | 31 To 35 / RY To SY | FDN | N/A | N/A | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0654 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S / 36 To 37 | S.B To L.G | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0655 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 22X To 26 / K To G | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-07 | 2023-01-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0656 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 22X To 26 / K To G | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-07 | 2023-01-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0657 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0658 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0659 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0660 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-09 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0661 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | 9Y To 10Y / QY To L | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-03 | 2023-01-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0008 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 | C1 | 44 To 47 / Y To VX | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-12 | 2023-01-05 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0662 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-04 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0663 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0664 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-04 | 2023-01-09 | 2023-01-09 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0665 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C2 & C3 | 41 To 44 / Z To X | FDN | N/A | N/A | 2023-01-04 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0666 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 12 | C3 | 33 To 37 / M To RX | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0667 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 12 | C3 | 33 To 37 / M To RX | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0668 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 | 24 To 28 / L To Q | FDN | N/A | N/A | 2023-01-04 | 2023-01-08 | 2023-01-08 | 2023-01-09 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0669 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 | 24 To 28 / L To Q | FDN | N/A | N/A | 2023-01-04 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0670 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | Y To X / 39 | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0671 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | Y To X / 39 | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0672 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 14 To 16 / TX To RY | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-05 | 2023-01-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0051 | Installation for pluming network as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To 34 / L To N | FDN | N/A | N/A | 2023-01-04 | 2023-01-05 | 2023-01-11 | 2023-01-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0673 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8-A | 13X To 18 / S To TX | FDN | N/A | N/A | 2023-01-05 | 2023-01-07 | 2023-01-07 | 2023-01-08 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0674 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / M To Q | FDN | N/A | N/A | 2023-01-05 | 2023-01-08 | 2023-01-08 | 2023-01-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0675 | Reinforced Concrete Columns & Walls Reinforcement to Level "-5.35" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX / 9Y To 10 | S.B To L.G | N/A | N/A | 2023-01-05 | 2023-01-07 | 2023-01-07 | 2023-01-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0676 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-05 | 2023-01-10 | 2023-01-11 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0677 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 & 10 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-05 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0678 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 To 41 / QX To RY | FDN | N/A | N/A | 2023-01-05 | 2023-01-07 | 2023-01-08 | 2023-01-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0679 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0680 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0681 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-10 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0682 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0683 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0684 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 24 To 30 / G To L | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0685 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-07 | 2023-01-08 | 2023-01-07 | 2023-01-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0686 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | W To Z / 45 To 47 | L.G To G.F | N/A | N/A | 2023-01-07 | 2023-01-10 | 2023-01-11 | 2023-01-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0687 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0688 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0689 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0690 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To T | FDN | N/A | N/A | 2023-01-08 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0691 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 11 To 14 / K To RY | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0692 | Reinforced Concrete Wall Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 | QX To R / 18 | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-08 | 2023-01-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0693 | Reinforced Concrete Wall Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 | QX To R / 18 | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0694 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / ZY | L.G To G.F | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-11 | 2023-01-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0695 | Reinforced Concrete GB Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 / RX To S | FDN | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-10 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0696 | "Stair 11" To Level (-4.25) Level and Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | 38 / Q To QY | S.B | N/A | N/A | 2023-01-08 | 2023-01-09 | 2023-01-16 | 2023-01-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0697 | Reinforced Concrete Columns & Walls Reinforcement from Level "73.75" to Level "74.95" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX / 9Y To 10 | S.B To L.G | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0698 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C4 & C3 | QX To TX / 37 To 38 | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0699 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0700 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0701 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0702 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0703 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0704 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0705 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-10 | 2023-01-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0706 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-09 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0707 | Reinforced Concrete Wall Reinforcement from Level "70.75" to Level "74.95" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX To 9X / 9Y | FDN To L.G | N/A | N/A | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0052 | Installation of Pipe Sleeves as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 45 To J / 22X To 26 | FDN | N/A | N/A | 2023-01-09 | 2023-01-18 | 2023-01-19 | 2023-01-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0053 | Installation and Survey Inspection of sleeves Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | G To J / 22X To 24 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0009 | Reinforced Concrete Duct Bank Coordinates | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 12 | C3 & C4 | X To Yy / 41 To S | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0708 | Reinforced Concrete Wall Reinforcement from Level "70.75" to Level "73.10" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9Y To B / 9X | FDN | N/A | N/A | 2023-01-10 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0709 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 | B6 | 18 To 22X / QX To RY | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-10 | 2023-01-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0710 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | RX To M / 12 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0711 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | RX To M / 12 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0712 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | RX To K / 12 To 13 | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0713 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | Q To QX / 38 | FDN | N/A | N/A | 2023-01-10 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0714 | Plain Concrete S.O.G Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 40 To 44 / X To Z | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0715 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 12 | C3 & C4 | 35 To 38 / QZ To S | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-14 | 2023-01-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0716 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / Z | FDN | N/A | N/A | 2023-01-10 | 2023-01-11 | 2023-01-11 | 2023-01-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0717 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 | 12 To 14 / K To RY | FDN | N/A | N/A | 2023-01-11 | 2023-01-12 | 2023-01-12 | 2023-01-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0718 | Reinforced Concrete Walls Reinforcement to L.G Slab | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 23 To 26 / G To J | FDN | N/A | N/A | 2023-01-11 | 2023-01-12 | 2023-01-12 | 2023-01-13 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0719 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-11 | 2023-01-12 | 2023-01-14 | 2023-01-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0720 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | RY To S / 28 To 33 | FDN | N/A | N/A | 2023-01-11 | 2023-01-14 | 2023-01-14 | 2023-01-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0721 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-15 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0722 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0723 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-15 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0724 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0725 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 44 / Z To Yy | L.G | N/A | N/A | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0726 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-17 | 2023-01-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0727 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0728 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-14 | 2023-01-18 | 2023-01-19 | 2023-01-19 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0729 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 28 To 30 / G To M | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0730 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-17 | 2023-01-16 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0731 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | B4 & B6 | 18 To 33 / RY To 7 | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0732 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-18 | 2023-01-19 | 2023-01-19 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0733 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0734 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-22 | 2023-01-22 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0735 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-14 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0736 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / K To QZ | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0737 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / QX To RX | FDN | N/A | N/A | 2023-01-14 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0738 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | 2X To 5 /EY | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-15 | 2023-01-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0739 | Underlayment Layer - Geotextile Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-14 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0054 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 32 To 38 / PX To P | FDN | N/A | N/A | 2023-01-14 | 2023-01-15 | 2023-01-18 | 2023-01-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0010 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 8 | C1 | 43 To 44 / Z To Y | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-17 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0740 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0741 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0742 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0743 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-15 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0744 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 44 / Z To Yy | L.G | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-16 | 2023-01-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0745 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-16 | 2023-01-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0055 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 | A3 | 7 To 8 / B To C | FDN | N/A | N/A | 2023-01-15 | 2023-01-16 | 2023-01-18 | 2023-01-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0011 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 6 | B2 | 28 To 24 / N To L | L.G | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-02-09 | 2023-01-18 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0746 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3-A | 9 To 6 / A To C | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0747 | Lower Ground Slab RC Coordinates & Top Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 41 To 44 / Z To Yy | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-16 | 2023-01-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0748 | Reinforced Concrete Stairs Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / 42 To QY | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0749 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / ZY | L.G To G | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0750 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 10 | B6 | 18 To 23 / QX To RY | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0751 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 10 | B6 | 18 To 23 / QX To RY | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-25 | 2023-01-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0752 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 22 To 25 / H To J | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0753 | Reinforced Concrete Walls & Columns Formwork to L.G Slab | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 23 To 26 / G To J | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0754 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 38 / 41 | FDN | N/A | N/A | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0755 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 38 / 41 | FDN | N/A | N/A | 2023-01-16 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0756 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | N To S / 12 To 13 | FDN | N/A | N/A | 2023-01-17 | 2023-01-18 | 2023-01-18 | 2023-01-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0056 | Gravity Test for pluming network as Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B2 | 30 To 34 / L To N | FDN | N/A | N/A | 2023-01-17 | 2023-01-18 | 2023-01-18 | 2023-01-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0012 | Electrical Cables Sleeves Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | Q To QX / 37 To 38 | FDN | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-19 | 2023-01-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0757 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C3 | QX To RY / 35 To 38 | FDN | N/A | N/A | 2023-01-18 | 2023-01-21 | 2023-01-22 | 2023-01-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0758 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-21 | 2023-01-20 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0759 | Reinforced Concrete Walls Reinforcement to Level "74.325" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 | S.B To L.G | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-21 | 2023-01-20 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0760 | Reinforced Concrete Walls Reinforcement to Level "72.70" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9 To 9X / A | S.B To L.G | N/A | N/A | 2023-01-18 | 2023-01-19 | 2023-01-21 | 2023-01-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0761 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / K To QZ | L.G | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0762 | Lower Ground Slab Plain Concrete Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 10 & 11 | B2 & B3 | 27 To 32X / RY To PX | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0763 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0763 | Backfilling Layer ( 1 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0764 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0765 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0765 | Backfilling Layer ( 2 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0766 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0767 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0767 | Backfilling Layer ( 5 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0768 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0769 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-19 | 2023-01-22 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0769 | Backfilling Layer ( 6 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0770 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-22 | 2023-01-23 | 2023-01-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0771 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 | 11 To 13 / N To R | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0772 | PVC Protection - Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0773 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47 / Z | L.G To G.F | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0774 | Reinforced Concrete Lower Ground Slab level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B2 | 24 To 30 / QZ To M | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0775 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | CZ To 2X / A To CY | FDN | N/A | N/A | 2023-01-19 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0776 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | TX To RY / 38 | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0777 | Reinforced Concrete Column Reinforcement to Level "72.10" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 / S | FDN | N/A | N/A | 2023-01-19 | 2023-01-21 | 2023-01-21 | 2023-01-22 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0778 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-26 | 2023-01-28 | 2023-01-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0779 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0780 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-26 | 2023-01-28 | 2023-01-27 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0781 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | RX To S / 36 To 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0782 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 11 To 12 / K To M | FDN | N/A | N/A | 2023-01-21 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0783 | Waterproofing PVC Layer - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | QX To RY / 38 | FDN | N/A | N/A | 2023-01-21 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0784 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0785 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0786 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0787 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B2 & B3 | L To RY / 23 To 26 | FDN | N/A | N/A | 2023-01-21 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0788 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A4 | CZ To 1 / B To C | FDN | N/A | N/A | 2023-01-21 | 2023-01-22 | 2023-01-24 | 2023-01-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0789 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0790 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / H To L | FDN | N/A | N/A | 2023-01-22 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0791 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX To 9X / 9Y To D | S.B To L.G | N/A | N/A | 2023-01-22 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0792 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | J To G / 22X To 27 | FDN | N/A | N/A | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0793 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | 10Y To B / 5 To 8 | FDN | N/A | N/A | 2023-01-23 | 2023-01-29 | 2023-01-30 | 2023-01-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0794 | PVC Protection – Cartmode - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | QX To RY / 38 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0795 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-24 | 2023-01-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0796 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-23 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0057 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 12 To 18 / RY To K | FDN | N/A | N/A | 2023-01-23 | 2023-01-26 | 2023-01-31 | 2023-01-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0797 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 16 To 18 / K To RY | FDN | N/A | N/A | 2023-01-23 | 2023-01-24 | 2023-01-26 | 2023-01-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0798 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | J To G / 22X To 27 | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-24 | 2023-01-26 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0799 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0800 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0801 | Reinforced Concrete Walls Reinforcement to Level "74.50" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S To RY / 35 | S.B To L.G | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0802 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0803 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0804 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0805 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-24 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0806 | Underlayment Layer - Geotextile Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | A To D / 1 & 2 | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-24 | 2023-01-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0807 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 & 11 | B4 & B6 | RY To SX / 33 To 34 | FDN | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0808 | Reinforced Concrete Stairs Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 & C4 | 38 / 42 To QX | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0809 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | A To D / 1 & 2 | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-28 | 2023-01-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0810 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | A To D / 1 & 2 | FDN | N/A | N/A | 2023-01-25 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0811 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0812 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-25 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0813 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-25 | 2023-01-26 | 2023-01-26 | 2023-01-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0814 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 16 To 14 / K To RY | FDN | N/A | N/A | 2023-01-25 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0815 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-01-26 | 2023-01-29 | 2023-01-29 | 2023-01-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0816 | Construction Joint injectable Hose installation Between B7-B8 & B5-B6 Foundation | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 & 9 | B7 & B8 | 16 To 18 / K To RY | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0817 | Reinforced Concrete Column Formwork to Level ( -4.775 / -7.00 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | K To S / 12 To 13 | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-28 | 2023-01-29 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0818 | Reinforced Concrete Foundation Sumpit Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B2 | QZ To RY / 11 To 10 Z | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-26 | 2023-01-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0819 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-28 | 2023-01-29 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0820 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 & 12 | B3 & C4 | 32X To 36 / Q To RY | FDN | N/A | N/A | 2023-01-26 | 2023-02-04 | 2023-02-04 | 2023-02-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0058 | Installation of Drainage Pipes & Gravity Test as highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 12 To 18 / RY To K | FDN | N/A | N/A | 2023-01-26 | 2023-01-28 | 2023-01-29 | 2023-01-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0059 | Drainage Pipes Locations & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 & 11 | B4 & B6 | 18 To 33 / RY To S | FDN | N/A | N/A | 2023-01-28 | 2023-01-29 | 2023-01-31 | 2023-01-30 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0059 | Drainage Pipes Locations & Level ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 & 11 | B4 & B6 | 18 To 33 / RY To S | FDN | N/A | N/A | 2023-02-14 | 2023-02-22 | 2023-02-23 | 2023-02-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0821 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | L To RY / 30 To 33 | FDN | N/A | N/A | 2023-01-28 | 2023-01-30 | 2023-01-31 | 2023-01-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0822 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A3 | 2X To 6 / 10X & 10Y | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-02-01 | 2023-01-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0013 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | 12 / N | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-02-09 | 2023-01-31 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ME-0060 | Drainage Pipes Locations & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A3 | 10X To 10 / RY To N | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-01-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0823 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-01-30 | 2023-01-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0824 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-29 | 2023-02-04 | 2023-02-04 | 2023-02-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0825 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-29 | 2023-01-30 | 2023-01-30 | 2023-01-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0826 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 24 To 28 / M To G | FDN | N/A | N/A | 2023-01-29 | 2023-02-08 | 2023-02-08 | 2023-02-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0061 | Installation For Tank Drain Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A3 | 9Y To 10 / RY To N | FDN | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-02-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0827 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 32X To 28 / Q To RY | L.G | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-02-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0828 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 11 | B6 | 17 To 24 / RY To Q | FDN | N/A | N/A | 2023-01-30 | 2023-01-31 | 2023-01-31 | 2023-02-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0829 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 & 11 | B6 | 17 To 24 / RY To Q | FDN | N/A | N/A | 2023-01-30 | 2023-02-04 | 2023-02-04 | 2023-02-05 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0830 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0831 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 & 4 | A3-B | C To EY / 6 To 8 | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0832 | Underlayment Layer - Geotextile to Level ( -5.675 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | B1 | 22X To 27 / G To K | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-01 | 2023-02-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0833 | Backfilling Layer ( 3 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-01 | 2023-02-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0834 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0835 | Backfilling Layer ( 4 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-01 | 2023-02-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0836 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0837 | Construction Joint injectable Hose installation Between A3-A | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A3-B | B To C / M To QX | FDN | N/A | N/A | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0838 | Waterproofing PVC Layer To Level ( -5.675 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | B1 | 22X To 27 / G To K | FDN | N/A | N/A | 2023-02-01 | 2023-02-02 | 2023-02-01 | 2023-02-03 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0839 | PVC Protection – Cartmode To Level ( -5.675 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 14 | B1 | 22X To 27 / G To K | FDN | N/A | N/A | 2023-02-01 | 2023-02-02 | 2023-02-01 | 2023-02-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0840 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | 5 To 2X / EY To 10Y | FDN | N/A | N/A | 2023-02-02 | 2023-02-04 | 2023-02-05 | 2023-02-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0841 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 14 | C3 | 37 To 38 / PX To RX | FDN | N/A | N/A | 2023-02-02 | 2023-02-04 | 2023-02-05 | 2023-02-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0842 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-05 | 2023-02-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0843 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-08 | 2023-02-08 | 2023-02-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0844 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-05 | 2023-02-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0845 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QY To RY / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-08 | 2023-02-08 | 2023-02-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0846 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 & B7 | SY To RX / 11 To 18 | FDN | N/A | N/A | 2023-02-04 | 2023-02-06 | 2023-02-07 | 2023-02-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0847 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 7 & 12 | C3 | PX To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-04 | 2023-02-11 | 2023-02-11 | 2023-02-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0848 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 11 | B4 | S To TX / 33 To 35 | FDN | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-05 | 2023-02-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0849 | Reinforced Concrete Slab Formwork Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 46 To 42X / V To Z | G.F | N/A | N/A | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0850 | Reinforced Concrete Corbel Beam Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 38 | L.G | N/A | N/A | 2023-02-05 | 2023-02-11 | 2023-02-11 | 2023-02-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0851 | Reinforced Concrete Walls & Piers Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B8 & B7 | RY To K / 18 To 13X | FDN | N/A | N/A | 2023-02-06 | 2023-02-07 | 2023-02-07 | 2023-02-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0852 | Reinforced Concrete Slab Level & Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | RX To S / 38 | L.G | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-11 | 2023-02-09 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0852 | Reinforced Concrete Slab Level & Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | RX To S / 38 | L.G | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0853 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | Z To ZY / 44 To PX | L.G | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-12 | 2023-02-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0854 | Reinforced Concrete Walls & Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | S To TX / 14 To 16 | FDN | N/A | N/A | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0062 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 35 To 38 / RY To Q | FDN | N/A | N/A | 2023-02-07 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0014 | Electrical Cables Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 & 9 & 10 & 11 | B6 & B4 & B3 & C3 | P To S / 18 To 36 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0855 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 23 To 26 / K To G | FDN | N/A | N/A | 2023-02-08 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0856 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 & B7 | RY To S / 12 To 15 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0857 | Reinforced Concrete Sumpit Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | QX To RY / 10Z To 10Y | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-11 | 2023-02-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0858 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0859 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0860 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0861 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | Q To S / 37 To 38 | FDN | N/A | N/A | 2023-02-08 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0015 | Electrical Cables Sleeves Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 4 | B7 | 12 / N | FDN | N/A | N/A | 2023-02-08 | 2023-02-09 | 2023-02-09 | 2023-02-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0862 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QX / 17 To 24 | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-09 | 2023-02-12 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0863 | Reinforced Concrete Sump pit Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10Y / QX To RY | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-09 | 2023-02-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0864 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 & B5 & B6 | L To RY / 17 To 24 | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-13 | 2023-02-12 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0864 | Plain Concrete Foundation Top Level Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 & B5 & B6 | L To RY / 17 To 24 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0865 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B3 & B6 | QX To RY / 16 To 27 | L.G | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-13 | 2023-02-12 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0865 | Plain Concrete Foundation Top Level Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B3 & B6 | QX To RY / 16 To 27 | L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0866 | Underlayment Layer - Geotextile – Vertical to Level “-4.575” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 9Y To Q / 38 | FDN | N/A | N/A | 2023-02-09 | 2023-02-11 | 2023-02-11 | 2023-02-12 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0867 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | W To V / 46X To 47 | L.G | N/A | N/A | 2023-02-09 | 2023-02-13 | 2023-02-13 | 2023-02-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0016 | Electrical Cables Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 7 | C3 | X To Y / 40 To 41 | FDN | N/A | N/A | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0868 | Waterproofing PVC Layer – Vertical to Level “-4.575” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 9Y To Q / 38 | FDN | N/A | N/A | 2023-02-11 | 2023-02-12 | 2023-02-14 | 2023-02-13 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0869 | Underlayment Layer - Geotextile – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 18 To 10 / J To K | FDN | N/A | N/A | 2023-02-11 | 2023-02-12 | 2023-02-12 | 2023-02-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0870 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | YY / 42 | L.G | N/A | N/A | 2023-02-12 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0871 | Waterproofing PVC Layer – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 18 To 10 / J To K | FDN | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-12 | 2023-02-14 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0872 | Reinforced Concrete Walls & Columns Reinforcement to Level 74.50 | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 11 To 13 / TX To SY | S.B To L.G | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-12 | 2023-02-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0873 | Reinforced Concrete Walls Reinforcement to Level 74.05 | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10 / S To RY | S.B To L.G | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-12 | 2023-02-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0063 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 15 | B1 | 28X To 32X / H To M | FDN | N/A | N/A | 2023-02-12 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0874 | Reinforced Concrete Walls Openings Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10X / SX To RY | L.G | N/A | N/A | 2023-02-12 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0875 | Reinforced Concrete Walls Openings Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | TX To T / 11 | L.G | N/A | N/A | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0876 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | S / 15 | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0877 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 13 To 16 / RY To TX | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0878 | Reinforced Concrete Columns and Grade Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 12 To 13X / RY To T | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0064 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 27 / G To H | FDN | N/A | N/A | 2023-02-13 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0879 | PVC Protection – Cartmode – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 18 To 10 / J To K | FDN | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0880 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 41 To 44 / YY To Z | L.G | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0881 | Construction Joint injectable Hose installation for Sub_basement Walls | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | 11 To 14 / SX To TX | S.B | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0882 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 33 / SY To SX | L.G | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-16 | 2023-02-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0065 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 32X To 33 / H To J | L.G | N/A | N/A | 2023-02-13 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0883 | Reinforced Concrete Column Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 42 / YY | L.G To G.F | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0884 | Reinforced Concrete Walls Reinforcement to Level -1.62 | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / QZ To RX | L.G To G.F | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0885 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 33 To 31X / L To RY | L.G | N/A | N/A | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0066 | Installation of Drainage Pipes as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 35 To 38 / RY To Q | FDN | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0067 | Installation of Drainage Pipes Network as per highlighted / Gravity Test | 00 | MEP | Mech | Pluming | Drainage | Zone 9 & 10 & 11 | B4 & B6 | 18 To 33 / RY To S | FDN | N/A | N/A | 2023-02-14 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0886 | PVC Protection – Cartmode – Vertical to Level “-4.575” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 9Y To Q / 38 | FDN | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0887 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | SX To S / 10 To 10Z | S.B To L.G | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-15 | 2023-02-16 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0888 | Reinforced Concrete Oil Intercptor pit Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 34 / RY To S | FDN | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-14 | 2023-02-16 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0068 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C3 & B3 | 33 To 34 / M To RY | L.G | N/A | N/A | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0069 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23 To 28 / J To H | FDN | N/A | N/A | 2023-02-15 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0070 | Installation for Drainage Network as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C3 & B3 | 33 To 34 / M To RY | L.G | N/A | N/A | 2023-02-15 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0889 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S To RX / 38 | L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0890 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | S To RX / 38 | L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0891 | Reinforced Concrete Core Walls and Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | M To L / 11 To 12 | FDN To L.G | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0892 | Reinforced Concrete Piers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | K To RY / 16 To 13 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0893 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-16 | 2023-02-17 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0893 | Soil Replacement Layer ( 3 ) level & Coordinates | 01 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0894 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-02-15 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0071 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | K /11 | FDN | N/A | N/A | 2023-02-15 | 2023-02-16 | 2023-02-15 | 2023-02-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0072 | Installation Sleeves Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | K /11 | FDN | N/A | N/A | 2023-02-16 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0073 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | M To P / 13X To 16 | FDN | N/A | N/A | 2023-02-16 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0074 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 & B4 | RX To QZ / 30 To 33 | FDN | N/A | N/A | 2023-02-16 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0075 | Gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | 35 To 38 / RY To Q | FDN | N/A | N/A | 2023-02-16 | 2023-02-18 | 2023-02-18 | 2023-02-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0076 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 6 | B1 | K / 43 | FDN | N/A | N/A | 2023-02-16 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0895 | Reinforced Concrete Piers and Walls Formwork to Level “-4.775” | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | K To RY / 16 To 13 | FDN | N/A | N/A | 2023-02-16 | 2023-02-18 | 2023-02-18 | 2023-02-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0896 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 46 To 45 / 32 To 34 | FDN | N/A | N/A | 2023-02-16 | 2023-02-20 | 2023-02-20 | 2023-02-21 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0017 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | 14 To 16 / N To L | L.G | N/A | N/A | 2023-02-16 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0897 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 5 | B5 & B2 | L To QX / 17 To 24 | FDN | N/A | N/A | 2023-02-18 | 2023-02-19 | 2023-02-19 | 2023-02-20 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0018 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 5 | B5 | 18 To 23 / L To QX | L.G | N/A | N/A | 2023-02-18 | 2023-02-19 | 2023-03-05 | 2023-02-20 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0898 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 32 To 32X / G | FDN | N/A | N/A | 2023-02-18 | 2023-02-19 | 2023-02-18 | 2023-02-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0077 | Gravity test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C3 & B3 | 33 To 34 / M To RY | L.G | N/A | N/A | 2023-02-18 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0899 | Reinforced Concrete Corbel Beam Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 38 | L.G | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-19 | 2023-02-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0900 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 38 / QX To RX | L.G | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-19 | 2023-02-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0901 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-20 | 2023-02-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0902 | Reinforced Concrete Foundation Manholes Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 27 To 32 / RY To S | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-21 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0902 | Reinforced Concrete Foundation Manholes Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 27 To 32 / RY To S | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0078 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 & C2 | 44 To 47 / X To Z | FDN | N/A | N/A | 2023-02-19 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0078 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 8 | C1 & C2 | 44 To 47 / X To Z | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L
1176-FSL-CP01-CN-AT-CIR-ME-0079 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10 / R | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-20 | 2023-02-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0080 | Installation Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10 / R | FDN | N/A | N/A | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0903 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 24 To 27 / X To RX | FDN | N/A | N/A | 2023-02-20 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0904 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 42 / YY | L.G | N/A | N/A | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0905 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | A3 | 10 To 11 / L To M | FDN | N/A | N/A | 2023-02-20 | 2023-02-21 | 2023-02-21 | 2023-02-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0906 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | A3 | 10 To 11 / L To M | FDN | N/A | N/A | 2023-02-20 | 2023-02-21 | 2023-02-21 | 2023-02-22 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0907 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0908 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0909 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0910 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0911 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0912 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0913 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | QZ To RX / 37 To 38 | FDN | N/A | N/A | 2023-02-21 | 2023-02-22 | 2023-02-22 | 2023-02-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0019 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 12 | C3 | 36 To 38 / RX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-03-05 | 2023-02-24 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0914 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 30 To 33 / M To RY | L.G | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0915 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 45 To 47X / VX To Z | G.F | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-25 | 2023-02-24 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0915 | Reinforced Concrete Ground Slab Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 45 To 47X / VX To Z | G.F | N/A | N/A | 2023-02-26 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0916 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 13 To 18 / T To RY | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-22 | 2023-02-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0917 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0918 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0919 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0920 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-22 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0921 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 35 To 33 / 47X | FDN | N/A | N/A | 2023-02-22 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0921 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 35 To 33 / 47X | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-08 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0922 | Reinforced Concrete Duct Bank Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 39 To 41 / X To YY | -4.825 | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0081 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | Q To RY / 10X To 11 | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-26 | 2023-02-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0923 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0924 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0925 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-02-23 | 2023-02-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0926 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-02-22 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0020 | Installation of Duct Bank Conduits as Highlighted | 00 | MEP | Elec | Elec | Duct Bank | Zone 12 | C3 | 34 To 36 / P To RX | FDN | N/A | N/A | 2023-02-22 | 2023-02-23 | 2023-03-01 | 2023-02-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0021 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 12 | C4 | 38 / S To RX & V / 40X | L.G | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-03-05 | 2023-02-26 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ME-0082 | Installation Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10X To 11 / RY To Q | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-26 | 2023-02-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0927 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0928 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0929 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0930 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / Q To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0931 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 39 To 42 / Z To V | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0932 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 39 To 42 / Z To V | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0933 | PVC Protection – Cartmode – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | A3 | 10 To 11 / L To M | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-26 | 2023-02-26 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0934 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 24 / L To Q | L.G | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0935 | Backfilling Layer ( 2 ) level & Coordinates & Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 & 12 | C3 | 35 To 37 / RX To QZ | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0936 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | A To C / 9Y To 9 | FDN To L.G | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0937 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 39X To 42 / V To Z | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-23 | 2023-02-26 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0083 | Installation for Water Supply as per Highlighted | 00 | MEP | Mech | Pluming | Water Supply | Zone 5 | B5 | N To Q / 18 To 21 | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 |  | 2023-02-26 | -225 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0084 | Installation for Water Supply as per Highlighted | 00 | MEP | Mech | Pluming | Water Supply | Zone 6 | B2 | 30 To 32 / N To Q | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 |  | 2023-02-26 | -225 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0085 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 15 | B2 | L To N / 26 To 32 | FDN | N/A | N/A | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2023-02-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0938 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | V To Y / 47 | L.G To G.F | N/A | N/A | 2023-02-23 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0939 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | C1 & B1 | 32 To 35 / G | FDN | N/A | N/A | 2023-02-25 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0939 | Reinforced Concrete Foundation Coordinates | 01 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | C1 & B1 | 32 To 35 / G | FDN | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0940 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 32X To 34 / 45 To 47X | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0941 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | SX To CX / 10Z To 10 | FDN To L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-25 | 2023-02-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0942 | Reinforced Concrete Walls & Columns Reinforcement to Level "-4.775" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 13 / RY To S | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-25 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0943 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 46 / 32 To 34 | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0086 | Water Supply Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 5 & 6 | B2 & B5 | 18 To 32 / R To N | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-28 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0944 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 30 To 33 / M To RY | L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0945 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 32X To 28 / Q To RY | L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0946 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 11 / Q To RY | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0947 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 & B3 | 22X To 28 / K To RY | L.G | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0948 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 15 To 18 / T To RY | FDN | N/A | N/A | 2023-02-25 | 2023-02-26 | 2023-02-26 | 2023-02-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0949 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4 | SX To TX / 11 To 14 | FDN To L.G | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0950 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 4 | A3 | 10Y To 10X / M To L | FDN | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0951 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 45 To 44X / 37 To 38 | L.G | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0952 | Duct Bank Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | YY To WY / 39 To 40 | L.G | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0953 | Reinforced Concrete Lower Ground Slab Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B2 & B3 | 28 To 33 / M To RY | FDN | N/A | N/A | 2023-02-26 | 2023-02-27 | 2023-02-27 | 2023-02-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0954 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 | B5 & B6 | RY To Q / 23 To 18 | S.O.G LG | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0955 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 12 To 18 / L To RY | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-27 | 2023-03-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0956 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 33 To 30 / G ToH | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0956 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 33 To 30 / G ToH | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0957 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9Y To 11 / QZ To S | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0958 | Underlayment Layer - Geotextile - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 38 To 35 / TX | L.G | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0959 | Waterproofing PVC Layer - Wall | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | 38 To 35 / TX | L.G | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-0960 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0961 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0962 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0963 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0964 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | 37 To 38 / QZ To Q | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0965 | Reinforced Concrete Foundation ( Trenches ) Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Y To B/ Q To RY | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0966 | Construction Joint injectable Hose installation at A4-B2 Raft | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 | A4 | S To QZ / 10X To 11 | FDN | N/A | N/A | 2023-02-27 | 2023-02-28 | 2023-02-28 | 2023-03-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0087 | Sleeves Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 | C2 | 44 / WY To YY | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0088 | Test for drainage pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A4 | 10Z To 11 / RY To Q | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0967 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0968 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0969 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0970 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0971 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0972 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0973 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0974 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0975 | Plain Concrete Foundation Top Level Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 34 To 36 / QX To RX | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0976 | Reinforced Concrete Core Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 11 To 12 / M To L | FDN | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-02 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0977 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2 & B3 | 34 To 27 / L To RY | L.G | N/A | N/A | 2023-02-28 | 2023-03-01 | 2023-03-01 | 2023-03-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0978 | Reinforced Concrete Lower Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | B5 & B6 | 10Y To B/ K To RY | L.G | N/A | N/A | 2023-02-28 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0089 | Test for drainage pipes after Concrete Pouring as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 5 & 9 & 10 | B5 & B6 & B7 & B8 | 13 To 28 / RY To L | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0022 | Electrical Cables for Earth work as per Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 5 | B5 | L / 22X | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-05 | 2023-03-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0979 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / RX To TX | -4.60 | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-04 | 2023-03-03 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0979 | Reinforced Concrete Columns and Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / RX To TX | -4.60 | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0980 | Reinforced Concrete Reinforcement (Duct Bank) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | RY To S / 22 To 33 | FDN | N/A | N/A | 2023-03-01 | 2023-03-02 | 2023-03-02 | 2023-03-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0981 | Reinforced Concrete Walls & Columns Formwork to Level "-4.775" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 13X / RY To S | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-06 | 2023-03-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0982 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 12 To 18 / L To RY | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-06 | 2023-03-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0983 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | B To EY / 5 To 8 | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-02 | 2023-03-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0090 | Installation of Drainage Pipes as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 27 / G To H | L.G | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-07 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0091 | Installation of Drainage Pipes as per highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 32 / H To J | L.G | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-07 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0023 | Electrical Cables Sleeves & Manhole Ineer Walls Points Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 12 | C3 | 34 To 35 / QY To RY | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-05 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0024 | Installation of Duct Bank Conduits as Highlighted | 00 | MEP | Elec | Elec | Power | Zone 12 | C3 | 34 To 35 / QY To RY | FDN | N/A | N/A | 2023-03-02 | 2023-03-04 | 2023-03-05 | 2023-03-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0984 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 To 23 / RX To L | L.G | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0092 | Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 15 | B2 | L To N / 26 To 32 | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0985 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0986 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-03-04 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0987 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / S To TX | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-EL-0025 | Electrical Cables for Earth work as per Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 7 & 12 | C3 & C4 | 37 To 38 / Q To RY | FDN | N/A | N/A | 2023-03-04 | 2023-03-05 | 2023-03-05 | 2023-03-06 | DONE | C |  |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-EL-0025 | Electrical Cables for Earth work as per Highlighted | 01 | MEP | Elec | Elec | Earthing | Zone 7 & 12 | C3 & C4 | 37 To 38 / Q To RY | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | B | L |  |  | OTAK
1176-FSL-CP01-CN-AT-CIR-ST-0988 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 15 | B1 | 31 To 34 / G To M | FDN | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-07 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0988 | Plain Concrete Foundation Top Level Coordinates and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 6 & 15 | B1 | 31 To 34 / G To M | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0989 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4 | 21 To 23 / T | L.G | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0990 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 44X / Z | L.G To G.F | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0991 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B5-A2 | 20 To 23 / RX To L | L.G | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-0992 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 22X To 28 / K To RY | L.G | N/A | N/A | 2023-03-05 | 2023-03-06 | 2023-03-06 | 2023-03-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-0993 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Y / R To RY | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0994 | Concrete Repair Work | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | W / 47 | L.G To G.F | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0995 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 10 & 11 | B4 | 23 To 33 / RY To S | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0996 | Excavation for Bottom Level & Coordinate | 00 | Civil | Civil | Earthwork | Excavation | Zone 1 & 2 | A1 & A2 | A To C / 1 To 4X | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-07 | 2023-03-08 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-0997 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | B1 | 45 To 47X / 34 To 32X | FDN | N/A | N/A | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0998 | Reinforced Concrete Columns Reinforcement from Lower Ground Level to Ground | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | B3-A & B4-A | 28 To 30 / Q To RY | L.G To G | N/A | N/A | 2023-03-07 | 2023-03-08 | 2023-03-07 | 2023-03-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0093 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 24 To 25 / H To G | FDN | N/A | N/A | 2023-03-07 | 2023-03-08 | 2023-03-08 | 2023-03-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-0999 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / 47 | L.G | N/A | N/A | 2023-03-07 | 2023-03-08 | 2023-03-08 | 2023-03-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1000 | Reinforced Concrete Piers & Grade Beam Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 33 To 34 / 46X | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1001 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 | B2 & B5 & B6 | 28 To 21 / K To RY | L.G | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-11 | 2023-03-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1002 | Reinforced Concrete Lower Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 42 To RX / 32 To 38 | L.G | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-09 | 2023-03-10 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1002 | Reinforced Concrete Lower Slab Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 42 To RX / 32 To 38 | L.G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1003 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1004 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1005 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1006 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1007 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-09 | 2023-03-08 | 2023-03-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1008 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-08 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1009 | Reinforced Concrete Lower Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | C2 | RY To L / 32X To 38 | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-13 | 2023-03-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1010 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | 23 To 32X / RY To S | L.G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1011 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1012 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1013 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1014 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-13 | 2023-03-11 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1015 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-09 | 2023-03-13 | 2023-03-11 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1016 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 & A3 | C To E / 5 To 6 | FDN | N/A | N/A | 2023-03-09 | 2023-03-13 | 2023-03-11 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1017 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 28X To 33 / M To PX | L.G To G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1018 | Reinforced Concrete Lower Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 42 To RX / 32 To 38 | L.G | N/A | N/A | 2023-03-09 | 2023-03-11 | 2023-03-11 | 2023-03-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1019 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 & 3 | A1 & A3 | A To EY / 3 To 8 | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1020 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / WY To Y | L.G To G.F | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-12 | 2023-03-13 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1020 | Reinforced Concrete Walls Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 44 / WY To Y | L.G To G.F | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-15 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1021 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-11 | 2023-03-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1022 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-11 | 2023-03-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1023 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-14 | 2023-03-13 | 2023-03-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1024 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 2 | A2 | 4X To 6 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-14 | 2023-03-13 | 2023-03-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1025 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-11 | 2023-03-12 | 2023-03-12 | 2023-03-13 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1026 | Reinforced Concrete Walls Formwork to Level "-1.62" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | RX To QZ / 38 | L.G To G.F | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1027 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 2 To 5 / B To E | FDN | N/A | N/A | 2023-03-12 | 2023-03-15 | 2023-03-13 | 2023-03-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1028 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 3 To 5 / EY | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1029 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3-B & A3-A | 9Y To 10Y / 6 To 8 | S.B To L.G | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1030 | Reinforced Concrete Piers Formwork & Grade Beams | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47X To 46X / 33 To 34 | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1031 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 28 To 33 / M To QY | L.G To G | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-15 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1032 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | B To E / 3X To 6 | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1033 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A4 | B To EY / Q To S | S.B | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1034 | Reinforced Concrete Walls Formwork to Level "-3.555" | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 44X To 47 / Z | L.G | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1035 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-12 | 2023-03-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1036 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-12 | 2023-03-15 | 2023-03-16 | 2023-03-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1037 | Underlayment Layer - Geotextile – Vertical to Level “73.225” | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 11 To 13 / M To K | FDN | N/A | N/A | 2023-03-12 | 2023-03-13 | 2023-03-13 | 2023-03-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1038 | Reinforced Concrete Duct Bank Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B6 | 23 To 18 / RY | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-13 | 2023-03-15 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1039 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 28 To 33 / M To QY | L.G To G | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1040 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-15 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1041 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 & 2 | A1 & A2 | 3X To 4 / B To D | FDN | N/A | N/A | 2023-03-13 | 2023-03-16 | 2023-03-16 | 2023-03-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1042 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | EY / 3 To 5 | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-14 | 2023-03-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1043 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | M To RY / 31X To 38 | L.G | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1044 | Waterproofing PVC Layer – Vertical to Level “73.225” | 00 | Civil | Civil | Waterproofing | PVC | Zone 4 | B7 | 11 To 14 / M To J | FDN | N/A | N/A | 2023-03-13 | 2023-03-14 | 2023-03-14 | 2023-03-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1045 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A & B5-A | 20 To 22X / N To R | L.G To G | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1046 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | WY To YY / 44 | L.G | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1047 | Reinforced Concrete Foundation Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Z To 11 / RY To S | FDN | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1048 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To E / 3 To 4 | FDN | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-15 | 2023-03-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1049 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | B To E / 3X To 4X | FDN | N/A | N/A | 2023-03-14 | 2023-03-15 | 2023-03-14 | 2023-03-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1050 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C4 | 34 To 35 / RY To TX | L.G | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-16 | 2023-03-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1051 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3-A | 39 To 42 / V To ZY | L.G | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-16 | 2023-03-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1052 | Soil Replacement Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1 To 3 / D To EY | FDN | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-15 | 2023-03-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1053 | Soil Replacement Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1 To 3 / D To EY | FDN | N/A | N/A | 2023-03-15 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1054 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1X To 3 / D To EY | FDN | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-15 | 2023-03-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1055 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1-B | 1X To 2X / C To E | FDN | N/A | N/A | 2023-03-15 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1056 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C3 | WX To YY / 40X To 40 | L.G To G | N/A | N/A | 2023-03-15 | 2023-03-16 | 2023-03-18 | 2023-03-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1057 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2-B | B To D / 2X To 4X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1058 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | B To E / 3 To 4X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-20 | 2023-03-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1059 | PVC Protection – Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | B To E / 3 To 4X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-20 | 2023-03-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1060 | Soil Replacement Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1061 | Soil Replacement Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-16 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1062 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1 To 3 / C To D | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-16 | 2023-03-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1063 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1 To 3 / C To D | FDN | N/A | N/A | 2023-03-16 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1064 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 11 To 16 / L To SY | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1065 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To E / 1X To 3X | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-16 | 2023-03-19 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1066 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C4 | 34 To 35 / RY To TX | FDN To L.G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1067 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B5 & B4 | 22X To 20 / L To RX | L.G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1068 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 & C1 | M To PX / V To WY | L.G To G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1069 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 44 / Y To WY | L.G To G.F | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-18 | 2023-03-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1070 | Reinforced Concrete Walls Reinforcement to Level “72.75” | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | A / 9 To 9X | S.B To L.G | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-19 | 2023-03-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0094 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / H To G | FDN | N/A | N/A | 2023-03-16 | 2023-03-18 | 2023-03-22 | 2023-03-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1071 | Backfilling Layer ( 1 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 13X / RY To J | FDN | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-18 | 2023-03-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1072 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4-B & B2-B | 31 To 23 / RY To SY | FDN | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1073 | Soil Replacement Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1074 | Soil Replacement Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-18 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1075 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | ZY To 37 / 40 To 39 | L.G To G.F | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1076 | Reinforced Concrete Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | VX To ZY / 47 To 47X | G.F | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1077 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 22X / RX To L | L.G To G | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1078 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B4-A | 22X / RX To L | L.G To G | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-19 | 2023-03-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1079 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B4-A | 23 To 26 / L To R | L.G To G | N/A | N/A | 2023-03-18 | 2023-03-19 | 2023-03-21 | 2023-03-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1080 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 24 / H | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1081 | Soil Replacement Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1082 | Soil Replacement Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Soil Replacment | Zone 1 | A1 | 1X To 3X / D To EY | FDN | N/A | N/A | 2023-03-19 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1083 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1X To 3X / 9Y To 10 | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1084 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 33 To 37 / RX To PX | L.G | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-19 | 2023-03-21 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1085 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 22X / L | L.G To G | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1086 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 47 To 47X / ZY To V | G.F | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-22 | 2023-03-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1087 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C3 | 33 To 36 / RY | L.G | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1088 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 33 To 30 / G To H | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1089 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 29 To 33 / G To H | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1090 | Plain Concrete Foundation Top Level Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B4 & B6 | 20 To 24 / RY To S | FDN | N/A | N/A | 2023-03-19 | 2023-03-20 | 2023-03-20 | 2023-03-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1091 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 13X / RY To J | FDN | N/A | N/A | 2023-03-19 | 2023-03-22 | 2023-03-25 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1092 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-20 | 2023-03-23 | 2023-03-25 | 2023-03-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1093 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-21 | 2023-03-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1094 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 16 / RY To J | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-25 | 2023-03-22 | DONE | C |  |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1094 | Backfilling Layer ( 2 ) Level & Coordinates | 01 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 18 To 16 / RY To J | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1095 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | 11 To 16 / RY To T | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-20 | 2023-03-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1096 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-20 | 2023-03-23 | 2023-03-25 | 2023-03-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1097 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | RX / 37 To 35 | L.G To G | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-20 | 2023-03-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0095 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | 22X To 28X / M To G | FDN | N/A | N/A | 2023-03-20 | 2023-03-22 | 2023-03-22 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1098 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | EY To A / 2X To 6 | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-21 | 2023-03-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1099 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | D To C / 3X To 2 | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-21 | 2023-03-22 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1100 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | D To C / 3X To 2 | FDN | N/A | N/A | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-22 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1101 | Backfilling Layer ( 1 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1102 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-25 | 2023-03-28 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1103 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1104 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-21 | 2023-03-25 | 2023-03-25 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1105 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3 To 2 / D To E | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1106 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | C3 | 33 To 36 / RY | L.G | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-21 | 2023-03-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1107 | PVC Protection - Surface Preparation Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3X To 2 / C To D | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1108 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | X To Y / 39 | L.G | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1109 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3 To 2 / D To EY | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-22 | 2023-03-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0096 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28X / J To G | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-22 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0097 | Walls Opening Sleeves Locations as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | RY / 28 To 32X | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-25 | 2023-03-23 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0097 | Walls Opening Sleeves Locations as per Highlighted ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | RY / 28 To 32X | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1110 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | RX / 37 To 35 | L.G To G | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1111 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B4-A | 23 To 26 / L To R | L.G To G.F | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1112 | Ground Slab Openings Coordinates Locations | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 43 To 47 / U To Z | FDN | N/A | N/A | 2023-03-21 | 2023-03-22 | 2023-03-25 | 2023-03-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1113 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 11 / R To RY | S.B | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-25 | 2023-03-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1114 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1 | 3 To 2 / D To EY | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1115 | Reinforced Concrete Columns Reinforcement to L.G | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A3 & A4 | 9Y To 10 / P To QZ | L.G | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1116 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | Q To RY / 38 | L.G To G.F | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1117 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | B To E / 4X To 6 | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1118 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 35 To 33 / 47X | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-26 | 2023-03-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1119 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C3 | QZ / WX | L.G To G.F | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1120 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | 39 / 34 To 35 | L.G To G.F | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-23 | 2023-03-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0098 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / K To H | FDN | N/A | N/A | 2023-03-22 | 2023-03-23 | 2023-03-29 | 2023-03-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1121 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-25 | 2023-03-25 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1122 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-27 | 2023-03-28 | 2023-03-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1123 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-25 | 2023-03-25 | 2023-03-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1124 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-03-23 | 2023-03-27 | 2023-03-28 | 2023-03-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1125 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 32X To 33 / RY To R | L.G To G | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1126 | Reinforced Concrete Walls Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | 34 To 28 / RY | L.G To G | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1127 | Reinforced Concrete Columns Reinforcement From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 24 To 26 / M To N | L.G To G | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1128 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 4 / B To EY | FDN | N/A | N/A | 2023-03-25 | 2023-03-26 | 2023-03-26 | 2023-03-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1129 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C2 | WY To YY / QX | L.G To G.F | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0099 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28X / J To G | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-04-06 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1130 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 12 To 11 / L To RY | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1131 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | SX To TX / 34 To 35 | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1132 | Reinforced Concrete Columns & Walls Piers Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | G To H / 30 To 32X | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0026 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 9 & 10 | B6 & B8 | 11 To 20 / RY To S | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-29 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1133 | Reinforced Concrete Columns Formwork up to L.G Level ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 | 6 To 8 / CY To B | S.B To L.G | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-26 | 2023-03-28 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0100 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23 To 28 / J To H | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-27 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0101 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / J To G | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-27 | 2023-03-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0102 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23X To 28 / G To H | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-03-27 | 2023-03-28 | DONE | B |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0102 | Test for Drainage Pipes | 01 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23X To 28 / G To H | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0102 | Test for Drainage Pipes | 02 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 23X To 28 / G To H | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0103 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-03-26 | 2023-03-27 | 2023-04-06 | 2023-03-28 | DONE | B |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0103 | Test for Drainage Pipes | 01 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0103 | Test for Drainage Pipes | 02 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1134 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-28 | 2023-03-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1135 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1136 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-28 | 2023-03-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1137 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-03-27 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1138 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-28 | 2023-03-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1139 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 36 To 38 / S To RX | FDN | N/A | N/A | 2023-03-27 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1140 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 11 | N/A | 24 To 26 / M To N & 32X / RX | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-27 | 2023-03-29 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1141 | Reinforced Concrete Columns Formwork From L.G To G | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | QZ / WX | FDN | N/A | N/A | 2023-03-27 | 2023-03-28 | 2023-03-27 | 2023-03-29 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0027 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 15 | B1 | 27 To 31 / 45 To 47 | L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-10 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0028 | Installation and Fixation Duct Bank Conduits ( First Fix ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 5 | B5 | 9Y / 18 To 20 | L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-05-10 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1142 | Reinforced Concrete Piers and Walls Reinforcement to ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32X / G To H | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-30 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1143 | Reinforced Concrete Piers and Walls Formwork to ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | 26 To 32X / G To H | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1144 | Reinforced Concrete Walls Reinforcement to L.G Level ( -4.575 ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Y To 11 / QX To S | S.B To L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1145 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 23 To 21 / RY To T | L.G | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-28 | 2023-03-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1146 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX | L.G To G.F | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-03-29 | 2023-03-30 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1146 | Reinforced Concrete Walls Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / TX | L.G To G.F | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-08 | 2023-04-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0104 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 26 To 28 / H To N | FDN | N/A | N/A | 2023-03-28 | 2023-03-29 | 2023-04-05 | 2023-03-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1147 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 23 To 28 / N To TY | L.G To G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-29 | 2023-03-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1148 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1149 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1150 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1151 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1152 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 9X To 8 / A | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1153 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1154 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1155 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1156 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1157 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 14 / K To H | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-01 | 2023-03-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1158 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 14 / K To H | FDN | N/A | N/A | 2023-03-29 | 2023-04-01 | 2023-04-03 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1159 | Reinforced Concrete Walls Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B3 | 24 To 26 / R | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-29 | 2023-03-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1160 | Reinforced Concrete Walls Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B2 | 25 To 26 / N To P | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0029 | Electrical Cables SLeeves locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 3 | A4 | 11 / RY To S | FDN | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-04-03 | 2023-03-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1161 | Ground Slab Formwork Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 42 To 45 / U To Z | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-30 | 2023-03-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1162 | Reinforced Concrete Ground Slab formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 45 To 43 / Z TO V | G.F | N/A | N/A | 2023-03-29 | 2023-03-30 | 2023-03-30 | 2023-03-31 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1162 | Reinforced Concrete Ground Slab formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 45 To 43 / Z TO V | G.F | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-01 | 2023-04-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1163 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-A | 23 To 26 / QX To RX | L.G To G.F | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-03-30 | 2023-04-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1164 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1165 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-03 | 2023-04-03 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1166 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1167 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 16 / SY To RY | FDN | N/A | N/A | 2023-03-30 | 2023-04-03 | 2023-04-03 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1168 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 9Y To 9 / A | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1169 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 14 | B1 | 24 To H | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1170 | Reinforced Concrete Slab Bottom Layer and Beams Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 47 To 45 / VX To ZY | L.G | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0105 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | 25 To 28 / J To G | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0106 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 14 & 15 | B1 | 22X To 28 / G To J | FDN | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-12 | 2023-04-02 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1171 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | RX To Q / 38 | L.G To G.F | N/A | N/A | 2023-03-30 | 2023-04-01 | 2023-04-01 | 2023-04-02 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1172 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 20 To 28 / RY To SY | L.G | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1173 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | 4X To 6 / A To EY | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1174 | PVC Protection – Cartmode – Vertical | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 9Y To 9 / A | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1175 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | N/A | 11 To 14 / TX | S.B To L.G | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1176 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | 4X To 6 / A To EY | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-04 | 2023-04-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0107 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 15 To 16 / L To PX | FDN | N/A | N/A | 2023-04-01 | 2023-04-02 | 2023-04-06 | 2023-04-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1177 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1178 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-05 | 2023-04-06 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1179 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1180 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-02 | 2023-04-05 | 2023-04-06 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1181 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 22 To 28 / RY To T | L.G | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | B | L |  |  | Wafaa Adly & Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1182 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Y To 12 / SX To QX | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-05 | 2023-04-04 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1182 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Y To 12 / SX To QX | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0108 | Installation and Test for Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 14 To 16 / L To Q | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-05 | 2023-04-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1183 | Construction Joint injectable Hose installation at A2 Raft | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / E To A | FDN | N/A | N/A | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-04 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1184 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-04 | 2023-04-04 | 2023-04-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1185 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-07 | 2023-04-06 | 2023-04-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1186 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-04 | 2023-04-04 | 2023-04-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1187 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-03 | 2023-04-07 | 2023-04-06 | 2023-04-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1188 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1189 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1190 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1191 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1192 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1193 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1194 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1195 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1196 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 45 To 43 / V To Y | G.F | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-05 | 2023-04-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1197 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1198 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1199 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1200 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1201 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1202 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1203 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-04 | 2023-04-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1204 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To T | FDN | N/A | N/A | 2023-04-04 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1205 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-B | 20 To 28 / RY To SY | L.G | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1206 | Reinforced Concrete Walls Formwork to Level "-0.85" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 28 To 33 / RY | L.G To G | N/A | N/A | 2023-04-04 | 2023-04-05 | 2023-04-08 | 2023-04-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1207 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1208 | Reinforced Concrete Walls Formwork to Level "-0.875" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B3-A | 32X To 33 / RY To R | L.G | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1209 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-B | 10Y To 11 /QX | L.G | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1210 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 25 To 26 / PX To N | L.G | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1211 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 2 To 4X / B To EY | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1212 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 15 / RY To S | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1213 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1214 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-08 | 2023-04-16 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1215 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-06 | 2023-04-06 | 2023-04-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1216 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-05 | 2023-04-08 | 2023-04-16 | 2023-04-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1217 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | N/A | PX TO QZ / 38 | L.G | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-09 | 2023-04-09 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1218 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A2 | EY / 2X To 2 | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1219 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | G To H / 26 To 28 | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-09 | 2023-04-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1220 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 9 To 9X / 9Y | S.B To L.G | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-06 | 2023-04-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1221 | Reinforced Concrete Columns & Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10 / RY | S.B To L.G | N/A | N/A | 2023-04-08 | 2023-04-12 | 2023-04-12 | 2023-04-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0109 | Installation for Drainage Pipe as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / H To J | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-12 | 2023-04-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0110 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 33 To 35 / RX To TX | FDN | N/A | N/A | 2023-04-06 | 2023-04-08 | 2023-04-08 | 2023-04-09 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1222 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-08 | 2023-04-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1223 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-08 | 2023-04-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1224 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3 | 10X / RY | L.G | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-08 | 2023-04-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1225 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1226 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1227 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 36 To 38 / 45 To 43 | G.F | N/A | N/A | 2023-04-08 | 2023-04-09 | 2023-04-09 | 2023-04-10 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1227 | Reinforced Concrete Slab Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 7 | C1 | 36 To 38 / 45 To 43 | G.F | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-11 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1228 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1229 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 16 To 18 / RY To L | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1230 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1231 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-10 | 2023-04-11 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1232 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To E / 1X To 4 | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-09 | 2023-04-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0111 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 27 To 28 / H To J | FDN | N/A | N/A | 2023-04-09 | 2023-04-10 | 2023-04-12 | 2023-04-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1233 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1234 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 10Y To 12 / K To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1235 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1236 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1237 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 16 To 18 / RY To L | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1238 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1239 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-10 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0112 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B3 | 33 To 35 / TX To RY | FDN | N/A | N/A | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0113 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B8 | 13 To 21 / RY To S | FDN | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0114 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | N/A | N/A | Zone 12 | C2 | 34 To 38 / RY To RX | L.G | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-12 | 2023-04-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1240 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 41 To 42 / 38 | FDN | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-11 | 2023-04-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1241 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | 11 To 14 / TX | FDN | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-04-11 | 2023-04-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-EL-0030 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 15 | B1 | 23 To 27 / 46X | L.G | N/A | N/A | 2023-04-11 | 2023-04-12 | 2023-05-10 | 2023-04-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1242 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-12 | 2023-04-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1243 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-15 | 2023-04-18 | 2023-04-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1244 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1245 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 | B1 | 22X To 25 / H To J | FDN | N/A | N/A | 2023-04-12 | 2023-04-15 | 2023-04-18 | 2023-04-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1246 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 4 to 2X / A To C | FDN | N/A | N/A | 2023-04-12 | 2023-04-12 | 2023-04-12 | 2023-04-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1247 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 31 To 33 / RY To SY | L.G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1248 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 28 To 33 / RY To SY | L.G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0115 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B6 & B8 | 16 To 18 / S To RY | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-15 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1249 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 28 To 33 / RY To SY | L.G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1250 | Slab ( Boundaries - Levels & Offset For Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | J To P / 33 To 38 | G.F | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-18 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0116 | Ground Slab Openings Pointes Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 8 | C1 | J To P / 33 To 38 | G.F | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1251 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1252 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1253 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-16 | 2023-04-14 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1254 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 15 / K | FDN | N/A | N/A | 2023-04-12 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1255 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B8 & B7 | 16 To 18 / RY To L | FDN | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1256 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | V To VX / 47 | L.G To G | N/A | N/A | 2023-04-12 | 2023-04-13 | 2023-04-13 | 2023-04-14 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1257 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X / RY | S.B To L.G | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1258 | PVC Protection – Cartmode to Level ( -4.775 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 3 & 9 | A4-B | 10 / 13X | S.B To L.G | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1259 | RC Walls Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 3 | A4 | SX To Q / 10Y To 11 | FDN | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1260 | Reinforced Concrete Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 43 To 47 / V To ZY | G.F | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-15 | 2023-04-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1261 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1X To 4X / 1Z To EY | FDN | N/A | N/A | 2023-04-13 | 2023-04-15 | 2023-04-13 | 2023-04-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1262 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-B | CY To EY / 2 To 4X | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-15 | 2023-04-17 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1263 | Construction Joint injectable Hose installation at A1 Raft | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 2 | A1 | 4X To 5 / E To A | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-15 | 2023-04-17 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1264 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 22X To 28X / G To L | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1265 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 14 & 15 | B1 | 22X To 28X / G To L | FDN | N/A | N/A | 2023-04-15 | 2023-04-18 | 2023-04-18 | 2023-04-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1266 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | B1 | 22X To 28X / G To L | FDN | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1267 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10 / RY | S.B To L.G | N/A | N/A | 2023-04-15 | 2023-04-16 | 2023-04-16 | 2023-04-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1268 | Plain Concrete Foundation Top Level & Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B1 | 23 To 25 / H To J | FDN | N/A | N/A | 2023-04-16 | 2023-04-17 | 2023-04-16 | 2023-04-18 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1269 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 & B8 | 15 To 21 / RY To T | FDN | N/A | N/A | 2023-04-16 | 2023-04-17 | 2023-04-16 | 2023-04-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1270 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | SY To TX / 13X To 14 | FDN | N/A | N/A | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1271 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 15 To 18 / RY To SY | FDN | N/A | N/A | 2023-04-16 | 2023-04-18 | 2023-04-18 | 2023-04-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1272 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 28 To 33 / SY To RY | L.G | N/A | N/A | 2023-04-17 | 2023-04-18 | 2023-04-18 | 2023-04-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1273 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | B1 | 33 To 35 / 47 To 46X | FDN | N/A | N/A | 2023-04-29 | 2023-04-30 | 2023-04-29 | 2023-05-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1274 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-04-29 | 2023-04-30 | 2023-04-29 | 2023-05-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1275 | RC Stair Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 12 To 13X / M To N | FDN | N/A | N/A | 2023-04-29 | 2023-04-30 | 2023-04-30 | 2023-05-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1276 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 8 | B1 | 32X To 35 / 45 To 47 | FDN | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-02 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1277 | PVC Protection – Cartmode – Vertical to Level “-4.155” | 00 | Civil | Civil | Waterproofing | PVC | Zone 7 | C3 | 41 To 42 / 38 | FDN | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-02 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1278 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-04-30 | 2023-05-01 | 2023-05-01 | 2023-05-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1279 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-01 | 2023-05-04 | 2023-05-04 | 2023-05-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1280 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5-B & B4-B | RY To SY / 16 To 22 | L.G | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1281 | RC Walls Waterproofing Bitumen to "-4.775" | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 9 | B8 | SY To RY / 11 To 13 | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1282 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 33 To 38 / G To P | G.F | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1283 | Reinforced Concrete Walls Reinforcement to Level "-0.075" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 34 To 38 / RY To RX | L.G To G | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1284 | RC Foundation Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 4 & 9 | B7 & B8 | 11 To 12 / K To RY | FDN | N/A | N/A | 2023-05-01 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1285 | Reinforced Concrete Stair Pedestal Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 12 To 13 / M | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1286 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | B To EY / 1 To 5 | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1287 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | B7 & A3 | 10 To 11 / M To K | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-01 | 2023-05-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1288 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 4 | B7 & A3 | 10 To 11 / M To K | FDN | N/A | N/A | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-03 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1289 | RC Manholes Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B2-B & B4-B | 22 To 32X / RY To S | L.G | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1290 | Reinforced Concrete Walls & Columns Reinforcement to Level "-5.825" | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / A To B | FDN | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1291 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1292 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-06 | 2023-05-08 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1293 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1294 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-02 | 2023-05-06 | 2023-05-08 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1295 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 23 To 28 / RX To QZ | L.G To G.F | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-06 | 2023-05-04 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1296 | RC Lower Ground Slab Reinforcement Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RX To RY | L.G | N/A | N/A | 2023-05-02 | 2023-05-03 | 2023-05-03 | 2023-05-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1297 | Reinforced Concrete Columns Formwork to L.G Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X / RY | S.B To L.G | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-05-04 | 2023-05-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1298 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-05 | 2023-05-03 | 2023-05-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1299 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1300 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-05-03 | 2023-05-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1301 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-03 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1302 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 | N/A | 16 To 18 / K To RY | L.G | N/A | N/A | 2023-05-03 | 2023-05-07 | 2023-05-08 | 2023-05-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1303 | Reinforced Concrete Stair Pedestal Formwork to Level "-4.775" | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 12 To 13 / M | FDN To L.G | N/A | N/A | 2023-05-03 | 2023-05-04 | 2023-05-04 | 2023-05-05 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1304 | Reinforced Concrete Columns Reinforcement to Level "-6.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | B To E / 5 | L.G | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-06 | 2023-05-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1305 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | Y To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-08 | 2023-05-07 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1305 | Reinforced Concrete Walls Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | Y To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1306 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1X To 3 / 10X To 10 | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1307 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1308 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1309 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-04 | 2023-05-06 | 2023-05-04 | 2023-05-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1310 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-07 | 2023-05-09 | 2023-05-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1311 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-04 | 2023-05-07 | 2023-05-09 | 2023-05-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1312 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-06 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1313 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-06 | 2023-05-10 | 2023-05-09 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1314 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-06 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1315 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2 | B To E / 5 | FDN | N/A | N/A | 2023-05-06 | 2023-05-07 | 2023-05-06 | 2023-05-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1316 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 34 To 35 / SX To TX | FDN | N/A | N/A | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1317 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 7 | C3 | 37 To 38 / P To Q | FDN | N/A | N/A | 2023-05-06 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1318 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & A4 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-07 | 2023-05-10 | 2023-05-09 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1319 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1320 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-07 | 2023-05-10 | 2023-05-09 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0117 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C2-A | 35 To 37 / RY To S | L.G | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-08 | 2023-05-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0031 | Installation and Fixation Conduits for Earthing System (First Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 15 | B1 | 27 To 28 | L.G | N/A | N/A | 2023-05-07 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0032 | Installation and Fixation UPVC FOR Duct Bank Conduits ( First Fix ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 9 | B8 | 16 TO 18 / SX To TX | L.G | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-11 | 2023-05-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0033 | Installation and Fixating Earthion Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 14 | B1 | 22X To 23 / G To H | L.G | N/A | N/A | 2023-05-07 | 2023-05-08 | 2023-05-10 | 2023-05-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1321 | Reinforced Concrete Stair Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10X To 10Z / SY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1322 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1323 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-08 | 2023-05-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1324 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | E To EY / 2 To 4X | FDN To L.G | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1325 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1326 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1327 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-09 | 2023-05-10 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1328 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-08 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0118 | Water Supply Pipes Locations ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 14 | B1 | 22X To 25 / H To G | FDN | N/A | N/A | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1329 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1330 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1331 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | V To Z / 43 To 47 | G.F To 1st | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-13 | 2023-05-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1332 | Reinforced Concrete Walls & Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | S To SY / 23 To 32X | L.G To G | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1333 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1334 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1335 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3 | 6 To 7 / C To D | S.B To L.G | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-13 | 2023-05-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1336 | Reinforced Concrete Stair Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Z To 10X / RY To S | S.B | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1337 | Reinforced Concrete Stair Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10Z To 10X / RY To S | S.B | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1338 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1339 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-09 | 2023-05-13 | 2023-05-11 | 2023-05-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1340 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / G To H | FDN | N/A | N/A | 2023-05-09 | 2023-05-10 | 2023-05-10 | 2023-05-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0034 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 9 | B6 | 16 To 18 / RY To S | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0035 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 11 | A1-A & A1-B | 1 To 6 / A & EY | L.G | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0036 | Installation and Fixation Earthing Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 8 | C1 & C2 | U To Z / 43 & 47 | G To MEZZ | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0037 | Installation and Fixation Conduits and Boxes for Access Control System (Second Fix) | 00 | MEP | Elec | Elec | Access Control | Zone 2 & 10 & 12 | A3 & B4 & C4 | (10X To 11 / RY To QX) (27 To 28 / RX) (T To QX / 38) | L.G | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1341 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | 13X To 14 / SY To TX | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-11 | 2023-05-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1342 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1343 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-10 | 2023-05-14 | 2023-05-11 | 2023-05-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1344 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 34 To 38 / RX To RY | L.G | N/A | N/A | 2023-05-10 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1345 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 | A4 | 13X To 14 / SY To TX | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-13 | 2023-05-12 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1346 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1347 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-14 | 2023-05-13 | 2023-05-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1348 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-11 | 2023-05-10 | 2023-05-12 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1349 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-10 | 2023-05-14 | 2023-05-13 | 2023-05-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1350 | Reinforced Concrete Lower Ground Slab Axis and Boundaries Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Z / 9 To 9X | L.G | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1351 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 | N/A | L To RY / 18 To 16 | L.G | N/A | N/A | 2023-05-11 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1352 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | E To EY / 2 To 4X | FDN To L.G | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1353 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 | A1-B | E To EY / 4 To 5 | FDN | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-13 | 2023-05-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0119 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 3 | A3-B | 10 To 10Y / Q To RY | L.G | N/A | N/A | 2023-05-11 | 2023-05-13 | 2023-05-15 | 2023-05-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1354 | Reinforced Concrete Duct Bank Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6 | 20 To 16 / RY | FDN | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-13 | 2023-05-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1355 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | Q To QZ / 37 To 38 | L.G To G.F | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1356 | Reinforced Concrete Columns Formwork to L.G Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | S To 23 / 32X | L.G To G | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1357 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 3 | A4 & A1 | E To EY / 4 To 5 | FDN | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1358 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9 To 9X / A To C | L.G | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-14 | 2023-05-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1359 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 14 & 15 | N/A | 23 To 28 / G To K | L.G | N/A | N/A | 2023-05-13 | 2023-05-14 | 2023-05-16 | 2023-05-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1360 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 1 & 3 | A4 & A1 | E To EY / 4 To 5 | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1361 | Reinforced Concrete Walls Reinforcement to Level "-1.80 | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5 | 16 To 18 / SY To TX | L.G To G.F | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1362 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A3 | C To EY / 2 To 4X | S.B To L.G | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-15 | 2023-05-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1363 | Underlayment Layer - Geotextile to Level ( -7.86 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / A | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-14 | 2023-05-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1364 | Waterproofing PVC Layer to Level ( -7.86 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / A | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-16 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1365 | PVC Protection – Cartmode to Level ( -7.86 ) | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | 5 To 6 / A | FDN | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-17 | 2023-05-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1366 | Reinforced Concrete Lower Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 | B5-A | K To RY / 16 To 21 | L.G | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-15 | 2023-05-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1367 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 23 To 16 / RY To SY | L.G | N/A | N/A | 2023-05-14 | 2023-05-15 | 2023-05-15 | 2023-05-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1368 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1369 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1370 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1371 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1372 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-15 | 2023-05-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1373 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1374 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-16 | 2023-05-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1375 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-15 | 2023-05-18 | 2023-05-17 | 2023-05-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0120 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 1 & 2 | A1 | 2X To 4X / B | FDN | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0121 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 1 & 2 | A1 | 2X To 4X / B | FDN | N/A | N/A | 2023-05-15 | 2023-05-22 | 2023-05-23 | 2023-05-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0122 | Reinforced Concrete Walls Openings Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | T To TX / 38 | L.G | N/A | N/A | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1376 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B3 | 23 To 25 / G To H | L.G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1377 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-05-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1378 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-16 | 2023-05-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1379 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3 | RX To QX / 10 To 10Y | L.G To G.F | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1380 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1381 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1382 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1383 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1384 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | S To RX / 33 To 35 | L.G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1385 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | RY To S / 35 To 38 | L.G To G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1386 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-17 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1387 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-16 | 2023-05-20 | 2023-05-17 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0123 | Water Supply Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 4 & 5 | B5-A | 16 To 18 / RY To P | L.G | N/A | N/A | 2023-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1388 | Reinforced Concrete Foundation ( Starter Bar ) Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | A To E / CZ To 5 | FDN | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-05-20 | 2023-05-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1389 | Reinforced Concrete Walls & Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | TX To RY / 38 | L.G To G | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-05-18 | 2023-05-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0038 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 2 | A1 | A To B / 3X To 4 | FDN | N/A | N/A | 2023-05-17 | 2023-05-18 | 2023-05-18 | 2023-05-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1390 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1-A | CZ To 4X / E To A | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1391 | Reinforced Concrete Lower Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5-B | SY To RY / 16 To 22 | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1392 | Ground Slab Formwork Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 35 To 38 / RY To M | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-18 | 2023-05-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1393 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5-B | RY To SY / 23 To 16 | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-18 | 2023-05-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1394 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1395 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1396 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-20 | 2023-05-21 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1397 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | SY To TX / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-22 | 2023-05-20 | 2023-05-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1398 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-22 | 2023-05-20 | 2023-05-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1399 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-18 | 2023-05-22 | 2023-05-20 | 2023-05-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1400 | Reinforced Concrete Slab Reinforcement ( Shrinkage Strep ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 27 To 28 / M To RY | L.G | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-22 | 2023-05-21 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1400 | Reinforced Concrete Slab Reinforcement ( Shrinkage Strep ) | 01 | Civil | Civil | Concrete | Cast in place | Zone 6 | B2-A | 27 To 28 / M To RY | L.G | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-30 | 2023-05-31 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0124 | Ground Slab Opening Locations as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 7 & 12 | C2 | 34 To 38 / RY To K | G.F | N/A | N/A | 2023-05-18 | 2023-05-20 | 2023-05-18 | 2023-05-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1401 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | Y To W / 45 To 46 | G.F | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-21 | 2023-05-22 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1402 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-21 | 2023-05-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1403 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1404 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-21 | 2023-05-22 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1405 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-20 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1406 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10Y / RX To QX | S.B To L.G | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-23 | 2023-05-22 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1406 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10Z To 10Y / RX To QX | S.B To L.G | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0125 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 1 | A1 | A To E / 1 To 4 | FDN | N/A | N/A | 2023-05-20 | 2023-05-21 | 2023-05-23 | 2023-05-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0126 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 1 | A1 | A To E / 1 To 4 | FDN | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1407 | Reinforced Concrete Foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1-A | CZ To 4 / E To A | FDN | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1408 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B5-A & B5-B | 16 To 22 / J To T | L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-21 | 2023-05-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1409 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 & 2 | A1 & A2 | 2X To 4X / 1 To CY | FDN | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-21 | 2023-05-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1410 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A | 23 To 28 / G To K | L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-27 | 2023-05-23 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1410 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 14 & 15 | N/A | 23 To 28 / G To K | L.G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1411 | Reinforced Concrete Walls Reinforcement to Level "-0.85" | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | 23 To 33 / T To SY | L.G To G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1412 | Underlayment Layer - Geotextile for Wall and Corbel | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN To L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1413 | Waterproofing PVC Layer for Wall and Corbel | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX To RY / 38 | FDN To L.G | N/A | N/A | 2023-05-21 | 2023-05-22 | 2023-05-22 | 2023-05-23 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1414 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | 41 / Z | L.G To G.F | N/A | N/A | 2023-05-22 | 2023-05-23 | 2023-05-22 | 2023-05-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1415 | Reinforced Concrete Walls & Columns Formwork to Level "-1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 28 To 33 / T To TX | L.G To G.F | N/A | N/A | 2023-05-22 | 2023-05-23 | 2023-05-23 | 2023-05-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0127 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0128 | Drainage Pipes Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 33 To 35 / SX To TX | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0129 | Water Supply Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Water Supply | Zone 11 | B4 | 34 To 35 / SY To TX | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0130 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-27 | 2023-05-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1416 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1417 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1418 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1419 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1420 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1421 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1422 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1423 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1424 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1425 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1426 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1427 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-05-23 | 2023-05-27 | 2023-05-29 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1428 | Reinforced Concrete Walls Formwork Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1429 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | YY To Z / 47 | FDN To G.F | N/A | N/A | 2023-05-23 | 2023-05-24 | 2023-05-24 | 2023-05-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1430 | Reinforced Concrete Lower Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 14 & 15 | N/A | 23 To 28 / M To G | FDN | N/A | N/A | 2023-05-24 | 2023-05-25 | 2023-05-27 | 2023-05-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1431 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 | 43 To 47 / V To ZY | G.F To 1st | N/A | N/A | 2023-05-24 | 2023-05-25 | 2023-05-25 | 2023-05-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0131 | Installation and Gravity Test for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 11 | B4 | 32X To 35 / RY To TY | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0039 | Electrical Cables Pipes locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Elec | Elec | Power | Zone 11 & 12 | B4 | 33 To 34 / S To TX | FDN | N/A | N/A | 2023-05-24 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1432 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 43 To 39 / Z To X | G.F | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-25 | 2023-05-28 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1433 | Reinforced Concrete Lower Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1434 | Reinforced Concrete Lower Ground Slab Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9 To 9X / 9Y To 10X | L.G | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1435 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1436 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1437 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1438 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-25 | 2023-05-29 | 2023-05-29 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1439 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-25 | 2023-05-27 | 2023-05-27 | 2023-05-28 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1440 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-25 | 2023-05-29 | 2023-05-27 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1441 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-27 | 2023-05-30 | 2023-05-29 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1442 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-27 | 2023-05-30 | 2023-05-29 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1443 | Reinforced Concrete Piers & Walls Coordintes | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 1 To 4 /A To E | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1444 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | N/A | 22 To 18 / M To S | L.G To G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-27 | 2023-05-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1445 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1446 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 15 | B1 | 30 To 32X / G To H | FDN | N/A | N/A | 2023-05-27 | 2023-05-30 | 2023-05-29 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1447 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1448 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1449 | Construction joint fuko hose Injection | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 & 3 | A3-A & A3-B | 49 To 11 & 5 To 9X | FDN To L.G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | C | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1450 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 15 | B1 | H To G / 29 To 32 | L.G | N/A | N/A | 2023-05-27 | 2023-05-28 | 2023-05-28 | 2023-05-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1451 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-29 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1452 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-06-01 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1453 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 35 To 38 / L To RY | G.F | N/A | N/A | 2023-05-28 | 2023-05-29 | 2023-05-31 | 2023-05-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1454 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-29 | 2023-05-31 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1455 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-30 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1456 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-29 | 2023-05-31 | 2023-05-30 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1457 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | B4 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-29 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1458 | Reinforced Concrete Lower Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / SX To TX | L.G | N/A | N/A | 2023-05-28 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1459 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1460 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1461 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1462 | Backfilling Layer ( 14 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1463 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1464 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1465 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1466 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1467 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9X To 9 / A To C | L.G | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-30 | 2023-05-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1468 | Reinforced Concrete Ground Slab Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 | N/A | 30 To 35 / K To RX | G.F | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1469 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2 | 33 To 35 / RY To S | FDN | N/A | N/A | 2023-05-29 | 2023-06-12 | 2023-06-15 | 2023-06-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1470 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-05-31 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1471 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-05-29 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1472 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1473 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1474 | Ground Slab Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | N/A | 30 To YY / 43 To S | G.F | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1475 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1476 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1477 | Reinforced Concrete Ground Slab Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4 | 10 To 11 / TX To SX | L.G | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1478 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 31 To 36 / J To S | G.F | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-01 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1479 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1480 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 11 To 13 / L To RY | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1481 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1482 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-05-30 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1483 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1484 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-05-30 | 2023-05-31 | 2023-05-31 | 2023-06-01 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1485 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-05-31 | 2023-06-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1486 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 2 & 4 | A2 & A3 & B7 | H To M / 10Z To 11 | FDN | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-01 | 2023-06-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1487 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RY To TX | L.G To G.F | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1487 | Reinforced Concrete Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 38 / RY To TX | L.G To G.F | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-03 | 2023-06-04 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1488 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 | N/A | M To RY / 18 | L.G To G.F | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1489 | Reinforced Concrete Walls Formwork to Level (-108) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 16 To 18 / SY To TX | FDN To L.G | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-01 | 2023-06-02 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1490 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-B | T To SY / 23 To 28 | L.G | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-05 | 2023-06-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1491 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-31 | 2023-06-01 | 2023-06-04 | 2023-06-02 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1492 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-06 | 2023-06-05 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1493 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | B1 | 47X To 44X / 32X To 35 | FDN | N/A | N/A | 2023-05-31 | 2023-06-04 | 2023-06-06 | 2023-06-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1494 | Wall Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4 | 25 To 28 / RY | FDN | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-01 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1495 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 11 To 16 / RY To S | FDN | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-04 | 2023-06-04 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1496 | Reinforced Concrete Walls Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4 | 23 To 24 / RY | L.G To G.F | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-04 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1497 | Reinforced Concrete Columns Location | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 36 To 32 / TX To T | L.G To G.F | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-04 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0132 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 9 | B7 & B8 & A4 | 10Y To 14 / PX To RY | FDN | N/A | N/A | 2023-06-01 | 2023-06-03 | 2023-06-08 | 2023-06-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1498 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-06-01 | 2023-06-05 | 2023-06-06 | 2023-06-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1499 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-06-01 | 2023-06-12 | 2023-06-13 | 2023-06-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1500 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 11 / SX To RY | L.G | N/A | N/A | 2023-06-03 | 2023-06-04 | 2023-06-04 | 2023-06-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1501 | Reinforced Concrete Lower Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Z To 11 / SX To RY | L.G | N/A | N/A | 2023-06-03 | 2023-06-04 | 2023-06-04 | 2023-06-05 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1502 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | TX To RY / 38 | L.G To G.F | N/A | N/A | 2023-06-03 | 2023-06-04 | 2023-06-04 | 2023-06-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0133 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 9 | B7 & B8 & A4 | 10Y To 14 / PX To RY | FDN | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-08 | 2023-06-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1503 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-04 | 2023-06-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1504 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-04 | 2023-06-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1505 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-07 | 2023-06-06 | 2023-06-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1506 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-04 | 2023-06-07 | 2023-06-06 | 2023-06-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1507 | Reinforced Concrete Walls and Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | SY To RY / 23 To 16 | L.G To G.F | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-05 | 2023-06-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1508 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | S To RY / 38 | FDN To L.G | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-05 | 2023-06-06 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1509 | Reinforced Concrete Piers Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | D To A / 1X To 3X | FDN To L.G | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-07 | 2023-06-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1510 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | D To A / 1X To 3X | FDN To L.G | N/A | N/A | 2023-06-04 | 2023-06-05 | 2023-06-07 | 2023-06-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0134 | Drainage Pipes Locations & Levels as per Highlighted ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-06-04 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0135 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-10 | 2023-06-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0136 | Wall Opening Coordinates | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B5-B | 16 To 18 / RY To SY | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1511 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B5-B | RX To PX / 18 | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-06-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1512 | Ground Slab Openings Points Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | C2 | 37 To 38 / L To QX | G.F | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1513 | Reinforced Concrete Ground Slab ( Boundaries - Levels & Offset For Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 35 To 38 / L To QX | G.F | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1514 | Reinforced Concrete Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | 35 To 38 / L To QX | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1515 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-06-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1516 | Backfilling Layer ( 15 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1517 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-06-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1518 | Backfilling Layer ( 16 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-05 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1519 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9 To 9X / A To C | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-08 | 2023-06-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1520 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-06-05 | 2023-06-06 | 2023-06-06 | 2023-06-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1521 | Reinforced Concrete Duct Bank Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B7 & B8 | 11 To 16 / RY To S | FDN | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-06-06 | 2023-06-08 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1522 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9 To 9X / A To C | L.G | N/A | N/A | 2023-06-06 | 2023-06-07 | 2023-06-07 | 2023-06-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0137 | Test After Concrete Pouring for the Drainage Network | 00 | MEP | Mech | Pluming | Drainage | Zone 14 | B1 | 22X To 28 / G To H | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0138 | Puddle Flange Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A2 & A3 | A To EY / 5 To QY | FDN | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-11 | 2023-06-09 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0138 | Puddle Flange Locations & Levels ( Survey Inspection ) | 01 | MEP | Mech | Pluming | Drainage | Zone 2 & 3 | A2 & A3 | A To EY / 5 To QY | FDN | N/A | N/A | 2023-06-19 | 2023-06-21 | 2023-06-20 | 2023-06-22 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1523 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | N/A | G To L / 24 To 27 | L.G To G | N/A | N/A | 2023-06-07 | 2023-06-08 | 2023-06-07 | 2023-06-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1524 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1525 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1526 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1527 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-08 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1528 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 23 / L | L.G | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1529 | Plan Concrete Duct Bank Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B8 | 15 To 16 / RY To S | FDN | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1530 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 14 | B3 | 22X To 28 / G To M | L.G | N/A | N/A | 2023-06-08 | 2023-06-10 | 2023-06-11 | 2023-06-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1531 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 22 To 18 / QX To S | L.G To G | N/A | N/A | 2023-06-10 | 2023-06-11 | 2023-06-11 | 2023-06-12 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1532 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 37 To S / 36 To S | FDN | N/A | N/A | 2023-06-10 | 2023-06-11 | 2023-06-13 | 2023-06-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0139 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B8 | 11 To 16 / RY To T | FDN | N/A | N/A | 2023-06-10 | 2023-06-11 | 2023-06-11 | 2023-06-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0140 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-06-11 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0141 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 9 | B8 | 11 To 16 / RY To T | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-20 | 2023-06-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1533 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1534 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1535 | Reinforced Concrete Oil Interceptor pit ( Slab & Walls ) Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 34 To 35 / SX To SY | FDN | N/A | N/A | 2023-06-11 | 2023-06-12 | 2023-06-12 | 2023-06-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0142 | Test for Drainage Pipes | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 9 | B7 & B8 & A4 | 10Y To 14 / PX To RY | FDN | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-20 | 2023-06-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1536 | Reinforced Concrete Columns & Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 18 To 23 / RY | L.G To G.F | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1537 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | N/A | 30 To 36 / N To G | L.G | N/A | N/A | 2023-06-12 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1538 | Reinforced Concrete Oil Interceptor pit Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 33 To 34 / RY To S | FDN | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1539 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10Z To 11 / RY To SX | L.G | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-13 | 2023-06-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1540 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-12 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1541 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | S To RY / 38 | FDN | N/A | N/A | 2023-06-12 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1542 | Reinforced Concrete Columns & Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | C2 | M To RY / 35 To 38 | G.F | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1543 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 47 / Z | L.G | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1544 | Wall Openings Location & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | B2-B | RY To TX / 35 | L.G | N/A | N/A | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-14 | DONE | B |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1544 | Wall Openings Location & Level | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | B2-B | RY To TX / 35 | L.G | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1545 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 / L | FDN | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-17 | 2023-06-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1546 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 24 To 26 / G To L | L.G To G.F | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1547 | Backfilling Layer ( 17 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1548 | Backfilling Layer ( 18 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-13 | 2023-06-14 | 2023-06-14 | 2023-06-15 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1549 | Backfilling Layer ( 17 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-15 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1550 | Backfilling Layer ( 18 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 15 / RY To SY | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-15 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1551 | Plain Concrete Foundation Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 11 To 17 / RY To SY | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-14 | 2023-06-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1552 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1553 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | RY To RX / 38 | FDN To L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-14 | 2023-06-16 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1554 | Reinforced Concrete Lower Ground Slab Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 10Y / SX To RY | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1555 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 11 / RY To SX | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1556 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 36 To 37 / RY To S | L.G To G.F | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-14 | 2023-06-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1557 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1558 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1559 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1560 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1561 | Reinforced Concrete Walls & Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 23 To 28 / RY | L.G To G.F | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-17 | 2023-06-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1562 | Reinforced Concrete Lower Ground Slab Reinforcement ( Shrinkage Strip ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B2-A | 27 To 28 / RY To SY | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1563 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-15 | 2023-06-16 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1564 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-06-14 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1565 | Reinforced Concrete Walls Openings Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 11 / TX To T | L.G | N/A | N/A | 2023-06-14 | 2023-06-15 | 2023-06-18 | 2023-06-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1566 | Construction Joint injectable Hose installation for Sub_basement Walls | 00 | Civil | Civil | Waterproofing | PVC | Zone 2 | A2 | A / 4X To 6 | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-17 | 2023-06-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1567 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2-A | A / 4X To 6 | FDN To LG | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-17 | 2023-06-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1568 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 11 / RY To S | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1569 | Reinforced Concrete Slab Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | 10Z To 10Y / RY To S | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-15 | 2023-06-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0040 | Duct Bank Pipes locations & Levels ( Survey Inspection ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 9 & 10 & 11 | B4 | 11 To 35 / RX To S | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-15 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0041 | Installation of Electrical Cables Conduits | 00 | MEP | Elec | Elec | Power | Zone 2 | A1 | A To B / 3X To 4 | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0042 | Installation of Electrical Cables Conduits | 00 | MEP | Elec | Elec | Power | Zone 11 & 12 | B4 | 33 To 34 / S To TX | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | D | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0043 | Installation of Duct Bank Conduits | 00 | MEP | Elec | Elec | Duct Bank | Zone 9 & 10 & 11 | B4 | 11 To 35 / RX To S | FDN | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0044 | Installation and Fixating Earthion Conduits and Cables for Earthing System (First & Second Fix) | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | L / 11 | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0045 | Installation of Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | N / 12 | L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0046 | Installation and Fixation Conduits for Access Control System | 00 | MEP | Elec | Elec | Access Control | Zone 12 | C4 | T To S / 35 To 36 | S.B To L.G | N/A | N/A | 2023-06-15 | 2023-06-17 | 2023-06-18 | 2023-06-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1570 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C3 | RY To RX / 38 | FDN To L.G | N/A | N/A | 2023-06-17 | 2023-06-18 | 2023-06-18 | 2023-06-19 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1571 | Reinforced Concrete Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 10X To 11 / TX To SX | L.G | N/A | N/A | 2023-06-17 | 2023-06-18 | 2023-06-20 | 2023-06-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0047 | Duct Bank Manhole Location & Level ( Survey Inspection ) | 00 | MEP | Elec | Elec | Duct Bank | Zone 11 & 12 | B3 | 34 To 35 / RY To S | L.G | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-18 | 2023-06-20 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1572 | Reinforced Concrete Slab Bottom Layer Reinforcement & Beams | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 36 To 31 / RY To K | G.F | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-21 | 2023-06-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1573 | Reinforced Concrete Columns Reinforcement to Level "-1.11" | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5 | 18 / K | L.G To G.F | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-18 | 2023-06-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1574 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9Y To 10Z / 9X To 9 | L.G | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1575 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1576 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0143 | Test After Concrete Pouring for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 33 / H To G | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0144 | Test After Concrete Pouring for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 15 | B1 | 30 To 32 / H To G | FDN | N/A | N/A | 2023-06-18 | 2023-06-19 | 2023-06-19 | 2023-06-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1577 | Backfilling Layer ( 13 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-19 | 2023-06-22 | 2023-06-21 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1578 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-19 | 2023-06-22 | 2023-06-21 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1579 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 26 To 28 / QY To RY | L.G To G.F | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-19 | 2023-06-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1580 | Reinforced Concrete Duct Bank Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B4 | 33 To 35 / S To RX | FDN | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-20 | 2023-06-21 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1581 | Reinforced Concrete Walls Reinforcement from "74.95" To "76.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9Y To 10X / T To TX | L.G To G.F | N/A | N/A | 2023-06-19 | 2023-06-20 | 2023-06-24 | 2023-06-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1582 | Reinforced Concrete Columns Reinforcement to Level "-1.11" | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 16 / K To J | L.G To G.F | N/A | N/A | 2023-06-20 | 2023-06-21 | 2023-06-20 | 2023-06-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1583 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | N/A | 3 / C To D | FDN | N/A | N/A | 2023-06-20 | 2023-06-21 | 2023-06-20 | 2023-06-22 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0048 | Wall & Slab Openings Location & Level ( Survey Inspection ) | 00 | MEP | Elec | Elec | Light Current | Zone 8 | B1-A | 47 To 47X / U To V | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0145 | Installation for Puddle Flange as per Highlighted | 00 | MEP | Mech | Tanks | N/A | Zone 2 & 3 | A2 & A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-25 | 2023-06-23 | DONE | D |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0145 | Installation for Puddle Flange as per Highlighted | 01 | MEP | Mech | Tanks | N/A | Zone 2 & 3 | A2 & A3 | 6 To 9 / A To C | FDN | N/A | N/A | 2023-07-30 | 2023-07-31 | 2023-07-31 | 2023-08-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0146 | Test After Concrete Pouring for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 8 & 15 | B1 & C1 | 28 To 37 / G To N | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-24 | 2023-06-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1584 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 36 / S | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-25 | 2023-06-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1585 | Reinforced Concrete Walls Formwork ( Duct Bank Manholes ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4 | RY To S / 27 To 32X | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1586 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1587 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1588 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | B1-A | 30 To 36 / N To G | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-23 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1589 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 18 To 11 / RY To SY | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1590 | Reinforced Concrete Wall Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B3 | 22X To 23 / J To H | L.G | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1591 | Reinforced Concrete Duct Bank Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 11 / RY To S | FDN | N/A | N/A | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1592 | Backfilling Layer ( 14 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-06-22 | 2023-06-26 | 2023-06-23 | 2023-06-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1593 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-06-22 | 2023-06-26 | 2023-06-23 | 2023-06-27 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1594 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | B1-A | 30 To 34 / G To M | L.G | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-23 | 2023-06-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1595 | Reinforced Concrete Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 31 To 36 / J To RY | G.F | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-23 | 2023-06-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1596 | Reinforced Concrete Column Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 18 / L | L.G | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-23 | 2023-06-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1597 | Reinforced Concrete Slab ( Boundaries - Levels & Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 & 12 | B3-A | 30 To 36 / RY To K | L.G | N/A | N/A | 2023-06-22 | 2023-06-24 | 2023-06-25 | 2023-06-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1598 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 11 To 20 / RY To T | L.G | N/A | N/A | 2023-06-23 | 2023-07-05 | 2023-07-05 | 2023-07-06 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1599 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 18 To 11 / RY To SY | L.G | N/A | N/A | 2023-06-23 | 2023-06-24 | 2023-06-24 | 2023-06-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1600 | Reinforced Concrete Lower Ground Slab ( Boundaries - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 18 To 11 / RY To SY | L.G | N/A | N/A | 2023-06-23 | 2023-06-24 | 2023-06-24 | 2023-06-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1601 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | B1-A | N To G / 30 To 36 | L.G | N/A | N/A | 2023-06-24 | 2023-06-25 | 2023-06-25 | 2023-06-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1602 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A & A4-B | TX To RY / 10X To 11 | L.G To G.F | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-08 | 2023-07-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1603 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 11 | B3-A | RY To K / 32 To 36 | G.F | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-08 | 2023-07-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1604 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-06 | 2023-07-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1605 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-05 | 2023-07-06 | 2023-07-06 | 2023-07-07 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1606 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | 25 To 28 / RY To QY | L.G | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-08 | 2023-07-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1607 | Backfilling Layer ( 15 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-06 | 2023-07-10 | 2023-07-13 | 2023-07-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1608 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-06 | 2023-07-10 | 2023-07-13 | 2023-07-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1609 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 36 To 37 / S | S.B To L.G | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-06 | 2023-07-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1610 | Reinforced Concrete Grease Interceptor pit Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 34 To 35 / SX To TX | FDN | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-08 | 2023-07-09 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1610 | Reinforced Concrete Grease Interceptor pit Walls Formwork | 01 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 34 To 35 / SX To TX | FDN | N/A | N/A | 2023-07-08 | 2023-07-09 | 2023-07-09 | 2023-07-10 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1611 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-07-06 | 2023-07-08 | 2023-07-10 | 2023-07-09 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1612 | Backfilling Layer ( 3 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 13X To 14 / T To TX | FDN | N/A | N/A | 2023-07-06 | 2023-07-10 | 2023-07-12 | 2023-07-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1613 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | N/A | 32 To 34 / G To M | L.G To G.F | N/A | N/A | 2023-07-08 | 2023-07-09 | 2023-07-12 | 2023-07-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1614 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 12 | N/A | 35 To 38 / RX To S | FDN | N/A | N/A | 2023-07-09 | 2023-07-10 | 2023-07-12 | 2023-07-11 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1615 | Reinforced Concrete Columns formwork ( Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 / K | L.G To G.F | N/A | N/A | 2023-07-09 | 2023-07-10 | 2023-07-10 | 2023-07-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1616 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 18 / K | L.G To G.F | N/A | N/A | 2023-07-09 | 2023-07-10 | 2023-07-10 | 2023-07-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1617 | Reinforced Concrete Walls Reinforcement to Level "-5.825" | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / A To B | FDN To G.F | N/A | N/A | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-12 | DONE | C |  |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1617 | Reinforced Concrete Walls Reinforcement to Level "-5.825" | 01 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / A To B | FDN To G.F | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-19 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1618 | Reinforced Concrete Walls Reinforcement to Level "-1.585" | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 35 / RY To TX | L.G To G.F | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | B |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1618 | Reinforced Concrete Walls Reinforcement to Level "-1.585" | 01 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 35 To 36 / RY To TX | L.G To G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1619 | Reinforced Concrete Wall Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B5-A | QX To R / 18 | L.G | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1620 | Reinforced Concrete Ground Slab ( Boundaries - Levels & Opening Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | B5-A | 16 To 23 / S To J | L.G | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1621 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1622 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2023-07-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1623 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | B5-A | 22X To 18 / L To RY | G.F | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-07-15 | 2023-07-14 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1624 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-07-13 | 2023-07-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1625 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-12 | 2023-07-13 | 2023-07-13 | 2023-07-14 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1626 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 13 / Q To RY | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1627 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 13 / Q To RY | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1628 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1629 | Backfilling Layer ( 16 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-07-13 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0147 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 1 | A1 | A To D / 1X To 2X | FDN | N/A | N/A | 2023-07-13 | 2023-07-15 | 2023-07-17 | 2023-07-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1630 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 13 To 16 / SX To S | L.G To G.F | N/A | N/A | 2023-07-13 | 2023-07-15 | 2023-07-15 | 2023-07-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1631 | Reinforced Concrete Ground Slab ( Boundaries - Axis - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 17 To 20 / J To M | G.F | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-15 | 2023-07-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1632 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 13 To 16 / S | L.G | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-16 | 2023-07-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1633 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 17 To 20 / J To M | G.F | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1634 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 8 & 15 | N/A | 32 To 34 / G To M | L.G To G.F | N/A | N/A | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1635 | Reinforced Concrete Walls and Columns Reinforcement to Level " -1.90" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B6-B | 13 To 18 | L.G To G.F | N/A | N/A | 2023-07-16 | 2023-07-17 | 2023-07-19 | 2023-07-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1636 | Reinforced Concrete Lower Ground Slab Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | B2-B | 33 To 35 / RY To TX | L.G | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-20 | 2023-07-19 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1637 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | B1-A | 32 To 34 / G To J | L.G | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-17 | 2023-07-19 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1638 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-18 | 2023-07-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1639 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-19 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ME-0148 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 11 To 15 / PX To N | FDN | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-22 | 2023-07-20 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1640 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | 35 To 32 / 46 To 42X | L.G To G.F | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-18 | 2023-07-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1641 | Backfilling Layer ( 4 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1642 | Backfilling Layer ( 5 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1643 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-19 | 2023-07-20 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1644 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C3 | 35 To 36 / RX To S | FDN | N/A | N/A | 2023-07-18 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1645 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 | N/A | 32 To 38 / L To QY | G.F To 1st | N/A | N/A | 2023-07-18 | 2023-07-19 | 2023-07-19 | 2023-07-20 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1646 | Reinforced Concrete Walls and Column Reinforcement to Level " -1.10" | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | B3 | 23 To 26 / J To H | L.G | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-22 | 2023-07-21 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1647 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 13 To 16 / PX To RY | L.G | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-20 | 2023-07-21 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1648 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 & 9 | B7 & B8 | 13 To 16 / PX To RY | L.G | N/A | N/A | 2023-07-19 | 2023-07-23 | 2023-07-22 | 2023-07-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1649 | Plane Concrete Lower Ground Slab Level & Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B7 & B8 | 13 To 16 / PX To RY | L.G | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-23 | 2023-07-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0149 | Installation for Drainage Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | 11 To 15 / PX To N | FDN | N/A | N/A | 2023-07-19 | 2023-07-20 | 2023-07-22 | 2023-07-21 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1650 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 35 / TX To R | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-20 | 2023-07-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1651 | Backfilling Layer ( 2 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 13X To 16 / K To PX | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-24 | 2023-07-23 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1652 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 13X To 16 / K To PX | L.G | N/A | N/A | 2023-07-20 | 2023-07-24 | 2023-07-22 | 2023-07-25 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1653 | Plane Concrete Lower Ground Slab Level & Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B7 | 13X To 16 / K To PX | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-20 | 2023-07-23 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1654 | Reinforced Concrete Lower Ground Slab Boundaries Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 35 / TX To RX | L.G | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-20 | 2023-07-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1655 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 35 / TX To RX | L.G | N/A | N/A | 2023-07-20 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1656 | Reinforced Concrete Piers Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 1 | A1 | 2 / A To D | FDN | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1657 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | 35 To 32 / 46 To 42X | L.G To G.F | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-23 | 2023-07-23 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1658 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | A4-B | 11 To 14 / SY To TX | L.G To G.F | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-23 | 2023-07-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1659 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B5-A | 23 To 18 / K To RX | G.F | N/A | N/A | 2023-07-20 | 2023-07-22 | 2023-07-22 | 2023-07-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1660 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2-A | 6 To 4 / A | FDN To L.G | N/A | N/A | 2023-07-22 | 2023-07-23 | 2023-07-22 | 2023-07-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1661 | Backfilling Layer ( 11 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1662 | Backfilling Layer ( 11 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-25 | 2023-07-24 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1663 | Backfilling Layer ( 12 ) Level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-24 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1664 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 9 | B8 | 11 To 14 / RY To SY | FDN | N/A | N/A | 2023-07-22 | 2023-07-25 | 2023-07-24 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1665 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 32 To 38 / N To RX | G.F To 1ST | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1666 | Reinforced Concrete Walls Formwork from "74.95" To "76.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | 9Y To 10X / T To TX | L.G To G.F | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1667 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 23 To 15 / T To SY | L.G To G.F | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-26 | 2023-07-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1668 | Lower Ground Slab Plain Concrete Top Level & Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 10Y To 15 / RY To Q | FDN | N/A | N/A | 2023-07-23 | 2023-07-24 | 2023-07-24 | 2023-07-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0049 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 7 & 8 & 11 & 12 | N/A | N/A | N/A | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-25 | 2023-07-26 | DONE | C | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0050 | Horizontal Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 10 | B6-B | N/A | G.F | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-31 | 2023-07-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0150 | Test After Concrete Pouring for Drainage Pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 6 & 7 & 8 & 11 & 12 & 15 | B1 & B2 & B3 & C1 & C2 & C3 | 28 To 38 / G To TX | FDN | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-27 | 2023-07-26 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1669 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 | N/A | L To QY / 32X To 35 | G.F To 1ST | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-26 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1670 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1671 | Backfilling Layer ( 6 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-08-01 | 2023-08-01 | 2023-08-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1672 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-26 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1673 | Backfilling Layer ( 7 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-07-24 | 2023-08-01 | 2023-08-01 | 2023-08-02 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1674 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 32X To 36 / RY To TX | L.G | N/A | N/A | 2023-07-24 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1675 | Reinforced Concrete Doors & FHC Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | 45 To 46X / ZY To Y | G.F | N/A | N/A | 2023-07-24 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1676 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | S / 36 To 37 | L.G To G.F | N/A | N/A | 2023-07-24 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1677 | Reinforced Concrete Ground Slab ( Boundaries, Opening, Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 10 & 11 | B4-A | 31 To 27 / S To L | G.F | N/A | N/A | 2023-07-24 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0051 | Vertical Earthing Conduits in Columns Coordinates | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 7 & 8 & 11 & 12 | N/A | N/A | N/A | N/A | N/A | 2023-07-25 | 2023-07-26 | 2023-07-29 | 2023-07-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1678 | Reinforced Concrete Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | B5 -A | 23 To 18 / QY To RY | G.F | N/A | N/A | 2023-07-25 | 2023-07-26 | 2023-07-26 | 2023-07-27 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1679 | Reinforced Concrete Wall Opening Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 22X To 26 / J To G | L.G | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0052 | Horizontal Earthing Conduits Level | 00 | MEP | Elec | Elec | Earthing | Zone 10 | B6 | N/A | G.F | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-31 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0053 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 6 & 8 & 12 | C1 & C2 & C4 | N/A | G.F To 1ST & G.F To MEZZ | N/A | N/A | 2023-07-26 | 2023-07-27 | 2023-07-27 | 2023-07-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1680 | Reinforced Concrete Stair Core Reinforcement to Level " +3.00" | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 45 To 46X / Y To ZY | G.F To MEZZ | N/A | N/A | 2023-07-27 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1681 | Reinforced Concrete Water Tank Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | A2 & A3 | 6 To 9 / A To B | FDN To L.G | N/A | N/A | 2023-07-27 | 2023-07-29 | 2023-07-30 | 2023-07-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1682 | Reinforced Concrete Walls Reinforcement to Level " -1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 32X To 35 / T To TX | L.G To G.F | N/A | N/A | 2023-07-27 | 2023-07-29 | 2023-07-29 | 2023-07-30 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1683 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 11 | N/A | 26 To 31 / L To RY | G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-30 | 2023-07-31 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1684 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 | N/A | 32X To 34 / RY | L.G To G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-29 | 2023-07-31 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1685 | Reinforced Concrete Ground Slab ( Boundaries, Levels, Sleeves, Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 & 10 | B5-A | 16 To 23 / J To S | G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-07-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1686 | Reinforced Concrete Ground Slab Top Layer Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 5 & 9 & 10 | B5-A | 16 To 23 / J To S | G.F | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-08-01 | 2023-07-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1687 | Reinforced Concrete Wall Opening Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 11 To 14 / SY To T | L.G | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-07-31 | 2023-07-31 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1688 | Reinforced Concrete Water Tank Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3 | 7 To 9 / A To B | S.B To L.G | N/A | N/A | 2023-07-29 | 2023-07-30 | 2023-08-01 | 2023-07-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1689 | Reinforced Concrete Walls Reinforcement to Level " -1.1" | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 22X To 27 / G To J | L.G To G.F | N/A | N/A | 2023-07-30 | 2023-07-31 | 2023-07-31 | 2023-08-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1690 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 39X To 40 / 32X To 37 | L.G To G.F | N/A | N/A | 2023-07-30 | 2023-07-31 | 2023-07-31 | 2023-08-01 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0151 | Test for Drainage Pipes After Concrete Pouring | 00 | MEP | Mech | Pluming | Drainage | Zone 4 & 9 | B7 & B8 | 11 To 14 / P To RY | FDN | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-02 | 2023-08-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1691 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 11 To 18 / K To RY | L.G | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1692 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-02 | 2023-08-03 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1693 | Backfilling Layer ( 12 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 4 | B7 | 11 To 13 / L To PX | FDN | N/A | N/A | 2023-08-01 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1694 | Plane Concrete Lower Ground Slab Level & Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-A | 11 To 13 / L To PX | L.G | N/A | N/A | 2023-08-01 | 2023-08-02 | 2023-08-02 | 2023-08-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1695 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 9 & 10 | B5-A | 16 To 23 / S To J | G.F | N/A | N/A | 2023-08-02 | 2023-08-03 | 2023-08-05 | 2023-08-04 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1696 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | S / 36 | L.G To G.F | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-03 | 2023-08-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1697 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | T To SY / 30 To 32X | G.F | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-03 | 2023-08-06 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1698 | Backfilling Layer ( 17 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1699 | Backfilling Layer ( 17 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-07 | 2023-08-08 | 2023-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1700 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1701 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | FDN | N/A | N/A | 2023-08-03 | 2023-08-07 | 2023-08-08 | 2023-08-08 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1702 | Reinforced Concrete Beam Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | 11 To 12 / T To TX | L.G | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1703 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | B2-B | 33 To 34 / S | L.G To G.F | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-06 | 2023-08-06 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1704 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 34 To 37 / WY To YY | G.F To 1ST | N/A | N/A | 2023-08-03 | 2023-08-05 | 2023-08-05 | 2023-08-06 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1705 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | T To SY / 30 To 32X | L.G To G.F | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-06 | 2023-08-07 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1706 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 37 To ZY / 46X To 45 | G.F To MEZZ | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-06 | 2023-08-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1707 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 & 7 & 12 | N/A | 32X To 37 / RX To QZ | G.F To 1ST & MEZZ | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-06 | 2023-08-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1708 | Reinforced Concrete Ground Slab ( Boundaries, Opening, Drop panls, Beams, Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 | B4-A | L To S / 22X To 28 | G.F | N/A | N/A | 2023-08-05 | 2023-08-06 | 2023-08-08 | 2023-08-07 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1709 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | N/A | 5 To 8 / B To EY | FDN To L.G | N/A | N/A | 2023-08-06 | 2023-08-07 | 2023-08-06 | 2023-08-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1710 | Reinforced Concrete Beam Reinforcement & Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 11 To 12 / SY To TX | L.G | N/A | N/A | 2023-08-06 | 2023-08-07 | 2023-08-06 | 2023-08-08 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1711 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 27 To 30 | L.G To G.F | N/A | N/A | 2023-08-06 | 2023-08-07 | 2023-08-06 | 2023-08-08 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1712 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 11 To 15 / Q To K | L.G | N/A | N/A | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-09 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1713 | Reinforced Concrete Ground Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | B4-A | 22X To 28 / L To RY | G.F | N/A | N/A | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-09 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1714 | R.C Stair Case Formwork Coordinates & Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | B4-A | 24 To 28 / QX To RY | L.G | N/A | N/A | 2023-08-07 | 2023-08-08 | 2023-08-08 | 2023-08-09 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1715 | PVC Protection – Cartmode | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | B4 | T To SY / 30 To 32X | L.G To G.F | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-08 | 2023-08-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1716 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 39 To 44 / WY To YY | G.F To 1ST | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1717 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | 39X To 40 / VX To Z | G.F To 1ST | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0152 | Test After Concrete Pouring for Sanitary Drainage Pipes as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 3 & 4 & 5 & 9 & 10 & 14 | B1 & B5 & B6 & B7 & B8 | 10 To 27 / G To RY | FDN | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1718 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-08 | 2023-08-09 | 2023-08-09 | 2023-08-10 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1719 | Backfilling Layer ( 8 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-08 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1720 | Waterproofing PVC Layer to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 27 To 30 | G.F | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1721 | PVC Protection – Cartmode to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 27 To 30 | G.F | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0153 | Installation and Test for Drainage Pipes as per attached | 00 | MEP | Mech | Pluming | Drainage | Zone 10 | B4 | 24 To 26 / RY To R | FDN | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0054 | Vertical Earthing Conduits in Columns Beteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 | B5 | 18 To L | G.F | N/A | N/A | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-08-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0055 | Vertical Earthing Conduits in Columns Beteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 10 | B4 & B5 | N/A | 1ST | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-29 | 2023-08-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1722 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | N/A | 22X To 20 / K To CX | G.F To 1ST | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1723 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1724 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To SY / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-16 | 2023-08-16 | 2023-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1725 | Backfilling Layer ( 18 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-10 | 2023-08-10 | 2023-08-11 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1726 | Backfilling Layer ( 18 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C4 | TX To Q / 38 | L.G | N/A | N/A | 2023-08-09 | 2023-08-16 | 2023-08-16 | 2023-08-17 | DONE | A | L |  |  | Al-Abrar
1176-FSL-CP01-CN-AT-CIR-ST-1727 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | T To TX / 11 To 16 | L.G To G.F | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-10 | 2023-08-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1728 | Reinforced Concrete Lower Ground Slab ( Boundaries, Drops Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 11 To 17 / K To S | L.G | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1729 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 11 To 18 / L To RY | L.G | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1730 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 33 To 37 / S | G.F | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-12 | 2023-08-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ME-0154 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 4 | B7 | Q To QX / 10Y To 11 | FDN | N/A | N/A | 2023-08-10 | 2023-08-12 | 2023-08-10 | 2023-08-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0056 | Vertical Earthing Conduits in ColumnsBeteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 12 | B5 & C3 | N/A | 1ST | N/A | N/A | 2023-08-12 | 2023-08-13 | 2023-08-29 | 2023-08-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1731 | Reinforced Concrete Columns & Shear Wall Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | C1 & C2 | 42X To 45 / VX To WY | G.F To MEZZ | N/A | N/A | 2023-08-12 | 2023-08-13 | 2023-08-14 | 2023-08-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1732 | Reinforced Concrete Columns & Wall Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 12 To 16 / K To RY | L.G | N/A | N/A | 2023-08-13 | 2023-08-15 | 2023-08-14 | 2023-08-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1733 | Reinforced Concrete Columns & Shear Wall Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 & 11 | N/A | 32X To 36 / 45 To QY | G.F To MEZZ | N/A | N/A | 2023-08-13 | 2023-08-15 | 2023-08-14 | 2023-08-16 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1734 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | T To SY / 27 To 24 | L.G | N/A | N/A | 2023-08-13 | 2023-08-14 | 2023-08-14 | 2023-08-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1735 | Underlayment Layer - Geotextile to Level "74.9" | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | TX / 36 To 38 | L.G | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-14 | 2023-08-16 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1736 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | Q To RX / 18 To 22X | G.F To 1ST | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-17 | 2023-08-16 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1737 | Plain Concrete Foundation Top Level & Coordinates and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 38 / TX To RX | L.G | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2023-08-16 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0057 | Vertical Earthing Conduits in Columns ( Level & Location ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 12 | N/A | N/A | 1st | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2023-08-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0058 | Vertical Earthing Conduits in Columns ( Level & Location ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 10 | N/A | N/A | 1st | N/A | N/A | 2023-08-14 | 2023-08-15 | 2023-08-15 | 2023-08-16 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1738 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | QZ To PX / 38 | G.F To 1ST | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-08-15 | 2023-08-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1739 | Reinforced Concrete Ground Slab ( Boundaries, Drops, Beams Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | N/A | 22X To 31 / SY To RY | G.F | N/A | N/A | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1740 | Reinforced Concrete Lower Ground Slab Boundaries, Drops, Openings & Beams ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / RY To Q | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1741 | Waterproofing PVC Layer to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | T To SY / 27 To 24 | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1742 | PVC Protection – Cartmode to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | T To SY / 27 To 24 | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1743 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 & 15 | N/A | 23 To 37 / G To J | L.G To G.F | N/A | N/A | 2023-08-16 | 2023-08-20 | 2023-08-21 | 2023-08-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1744 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | X To W / 47 | G.F To 1ST | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-19 | 2023-08-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1745 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | RY To Q / B To EY | L.G | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1746 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 To 23 / K To RY | G.F To 1ST | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1747 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 & 11 | B4-B | 23 To 31 / SY To RY | G.F | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-17 | 2023-08-18 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1748 | Reinforced Concrete Walls Openings Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 13 To 16 / T To SY | L.G To G.F | N/A | N/A | 2023-08-16 | 2023-08-17 | 2023-08-19 | 2023-08-18 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1749 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1750 | Backfilling Layer ( 9 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-21 | 2023-08-19 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1751 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1752 | Backfilling Layer ( 10 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | C2-A | 37 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-21 | 2023-08-19 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1753 | Plain Concrete Slab Top Level & Coordinates and Formwork | 00 | Civil | Civil | Earthwork | Backfilling | Zone 12 | N/A | 36 To 38 / S To RX | L.G | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1754 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 16 To 12 / L To R | L.G To G.F | N/A | N/A | 2023-08-17 | 2023-08-19 | 2023-08-19 | 2023-08-20 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1755 | Reinforced Concrete Columns formwork ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 16 / K | L.G To G.F | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-20 | 2023-08-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1756 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 10 | N/A | 18 To 22X / M To R | G.F To 1ST | N/A | N/A | 2023-08-19 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1757 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 12 To 16 / K To QX | L.G To G.F | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-21 | 2023-08-21 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1758 | Reinforced Concrete Wall Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 37 To 38 / S To RY | L.G To G.F | N/A | N/A | 2023-08-19 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0059 | Vertical Earthing Conduits in Columns ( L.G To G.F ) | 00 | MEP | Elec | Elec | Earthing | Zone 4 | B7 | N / 14 To 16 | L.G | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-29 | 2023-08-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0060 | Vertical Earthing Conduits in Columns Beteen ( G.F & Upeer Floor ) | 00 | MEP | Elec | Elec | Earthing | Zone 7 | C2 | ( Z / 45 ) ( 38 / RZ ) | G.F | N/A | N/A | 2023-08-19 | 2023-08-20 | 2023-08-29 | 2023-08-21 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1759 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-20 | 2023-08-21 | 2023-08-21 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1760 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-20 | 2023-08-21 | 2023-08-21 | 2023-08-22 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1761 | Underlayment Layer - Geotextile | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-08-20 | 2023-08-21 | 2023-08-21 | 2023-08-22 | DONE | C |  |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1761 | Underlayment Layer - Geotextile | 01 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-06 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1762 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 45 To 46X / ZY To Y | G.F | N/A | N/A | 2023-08-21 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1763 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | N/A | 12 To 14 / L To R | L.G To G.F | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-21 | 2023-08-23 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1764 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-21 | 2023-08-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1765 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-21 | 2023-08-22 | 2023-08-21 | 2023-08-23 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1766 | Reinforced Concrete Depressed Slab formwork ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1767 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1768 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1769 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-23 | 2023-08-24 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1770 | Reinforced Concrete Walls Reinforcement to Level "-0.85" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 12 To 21 / RY | L.G To G.F | N/A | N/A | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-24 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1771 | Reinforced Concrete Depressed Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1772 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | N/A | 23 To 31 / S To L | G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1773 | Underlayment Layer - Geotextile from Level "-3.05"to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 24 To 30 | L.G To G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1774 | Waterproofing PVC Layer from Level "-3.05"to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 24 To 30 | L.G To G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1775 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-23 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1776 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-23 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1777 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-23 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1778 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | 45 To 46X / ZY To Y | G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-27 | 2023-08-25 | DONE | C | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1779 | Reinforced Concrete Walls Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 11 & 12 | N/A | 32X To 36 / TX To T | L.G | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1780 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 & 9 | B6-A | 12 / N To RX | L.G To G.F | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1781 | Reinforced Concrete Columns Location and Level | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | W To X / 47 | G.F To 1ST | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-27 | 2023-08-25 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1782 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1783 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-26 | 2023-08-25 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1784 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | C4 | TX / 37 To 38 | L.G | N/A | N/A | 2023-08-23 | 2023-08-24 | 2023-08-24 | 2023-08-25 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1785 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / TX To RY | L.G | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-28 | 2023-08-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1786 | Reinforced Concrete Stair Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | R To RY / 27 To 28 | L.G To G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-27 | 2023-08-27 | DONE | C |  |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1786 | Reinforced Concrete Stair Bottom Layer Reinforcement | 01 | Civil | Civil | Concrete | Cast in place | Zone 10 | N/A | R To RY / 27 To 28 | L.G To G.F | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1787 | Reinforced Concrete Walls Openings ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | RY To SX / 35 To 36 | L.G To G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1788 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1789 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-28 | 2023-08-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1790 | Reinforced Concrete Slab formwork Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 18 To 22X / TX To RY | G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-27 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1791 | Surface Preparation for Tank Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 & 3 | N/A | 6 To 9 / B To C | FDN To L.G | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-27 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1792 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1793 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1794 | PVC Protection – Cartmode from Level "-3.05"to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 & 11 | B4 | T To SY / 24 To 30 | L.G To G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-26 | 2023-08-27 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1795 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | N/A | W To X / 47 | G.F | N/A | N/A | 2023-08-24 | 2023-08-26 | 2023-08-30 | 2023-08-27 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1796 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | N/A | 24 To 21 / T To SY | FDN | N/A | N/A | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-28 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1797 | Reinforced Concrete Walls Openings ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 11 To 12 / RY | L.G To G.F | N/A | N/A | 2023-08-26 | 2023-08-27 | 2023-08-28 | 2023-08-28 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0155 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | N/A | 37 To 38 / RY To RX | FDN | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-30 | 2023-08-29 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1798 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-28 | 2023-08-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1799 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-28 | 2023-08-29 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1800 | Reinforced Concrete Depressed Slab Bottom, Top Layers and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | A To C / 8 To 9 | L.G | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-28 | 2023-08-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1801 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 18 To 23 / RX To TX | G.F | N/A | N/A | 2023-08-27 | 2023-08-28 | 2023-08-30 | 2023-08-29 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1802 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-B | L To M / 12 | L.G To G.F | N/A | N/A | 2023-08-27 | 2023-09-02 | 2023-09-02 | 2023-09-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1803 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 11 To 18 / RY | L.G | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1804 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 13X To 14 / L | L.G To G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1805 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9Y To 11 / TX To RY | L.G To G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1806 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9 To 9X / A | L.G | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-28 | 2023-08-30 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1807 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1808 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1809 | Reinforced Concrete Slab formwork Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | B5-A | 17 To 21 / T To TX | G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-30 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0061 | Installation Earthing Conduits and Cables for Earthing System | 00 | MEP | Elec | Elec | Earthing | Zone 4 & 5 & 10 & 11 | B2 & B3 & B5 & B6 | N/A | G.F | N/A | N/A | 2023-08-28 | 2023-08-29 | 2023-08-29 | 2023-08-30 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0156 | Installation for Pluming Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | RX To RY / 37 To 38 | L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-08-31 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0157 | Drainage Pipes Location & Level ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C4 | T To TX / 38 | L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-09-02 | 2023-08-31 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1810 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A2-A | 5 To 7 / CX To 10Y | S.B To L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-09-02 | 2023-08-31 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1811 | Waterproofing PVC Layer to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | N/A | 24 To 21 / T To SY | FDN To L.G | N/A | N/A | 2023-08-29 | 2023-08-30 | 2023-08-30 | 2023-08-31 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ME-0158 | Gravity Test for Pluming Network as per Highlighted | 00 | MEP | Mech | Pluming | Drainage | Zone 12 | C3 | RX To RY / 37 To 38 | L.G | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-31 | 2023-09-01 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1812 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | B5-A | 18 / N | G.F To 1ST | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-30 | 2023-09-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1813 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-A | 2 To 16 / N | L.G To G.F | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-30 | 2023-09-01 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1814 | Reinforced Concrete Stair Landing Coordinates & Levels | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 35 To 36 / S To T | L.G | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-30 | 2023-09-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1815 | PVC Protection – Cartmode to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 9 & 10 | N/A | 24 To 21 / T To SY | FDN To L.G | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-08-31 | 2023-09-01 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1816 | Reinforced Concrete Ground Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | N/A | 22X To 31 / S To L | G.F | N/A | N/A | 2023-08-30 | 2023-09-04 | 2023-09-05 | 2023-09-05 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1817 | Reinforced Concrete Walls Openings ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | R To QX / 16 | L.G To G.F | N/A | N/A | 2023-08-30 | 2023-08-31 | 2023-09-02 | 2023-09-01 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1818 | Reinforced Concrete Walls Reinforcement to Level "-1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 16 / QX To RX | L.G To G.F | N/A | N/A | 2023-08-31 | 2023-09-02 | 2023-09-03 | 2023-09-03 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1819 | Reinforced Concrete Ground Slab ( Boundaries, Levels, Sleeves, Starter bar Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | N/A | 22X To 31 / L To S | G.F | N/A | N/A | 2023-08-31 | 2023-09-02 | 2023-09-05 | 2023-09-03 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1820 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | G.F To 1st | QX To N / 18 To 22X | G.F | N/A | N/A | 2023-09-02 | 2023-09-03 | 2023-09-03 | 2023-09-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1821 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | B6-A | 18 / L | L.G | N/A | N/A | 2023-09-02 | 2023-09-03 | 2023-09-05 | 2023-09-04 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1822 | Reinforced Concrete Columns Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 12 | N/A | QZ To RX / 38 | G.F To 1ST | N/A | N/A | 2023-09-02 | 2023-09-03 | 2023-09-03 | 2023-09-04 | DONE | A | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1823 | Reinforced Concrete Depressed Slab ( Boundaries, Drops, Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-09-03 | 2023-09-04 | 2023-09-04 | 2023-09-05 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1824 | Reinforced Concrete Columns Formwork ( Location ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | 16 / L | L.G To G.F | N/A | N/A | 2023-09-03 | 2023-09-04 | 2023-09-05 | 2023-09-05 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1825 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 4 & 9 | N/A | 9Y To 12 / RY To QZ | L.G | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-04 | 2023-09-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1826 | Reinforced Concrete Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 23 / RX To TX | G.F | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-05 | 2023-09-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1827 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 8 To 9 / A To C | L.G | N/A | N/A | 2023-09-04 | 2023-09-05 | 2023-09-05 | 2023-09-06 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1828 | Surface Preparation for Tank Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9 / A To C | FDN To L.G | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-06 | 2023-09-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1829 | Reinforced Concrete Lower Ground Slab Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 36 To 38 / S To RX | L.G | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-05 | 2023-09-07 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1830 | Reinforced Concrete Beams Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 18 To 21 / A To C | G.F | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1831 | Reinforced Concrete Beams Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 18 To 21 / A To C | G.F | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-06 | 2023-09-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1832 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 | N/A | 18 / L | G.F To 1ST | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-05 | 2023-09-07 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ME-0159 | Puddle Flange Locations & Levels ( Survey Inspection ) | 00 | MEP | Mech | Pluming | Drainage | Zone 2 | A3 | K To QX / B To EY | FDN | N/A | N/A | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-07 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1833 | Surface Preparation for Tank Walls | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | N/A | 6 / A To C | FDN To L.G | N/A | N/A | 2023-09-06 | 2023-09-10 | 2023-09-10 | 2023-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1834 | Reinforced Concrete Walls Formwork ( Top Levels on Attachment ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 10X To 11 / TX To RY | L.G To Ramp | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-09 | 2023-09-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1835 | Wall opening ( Knock out ) Coordinates & level | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-C | A / 9X | L.G | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-07 | 2023-09-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1836 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | 9Y To 10X / SX To TX | L.G To G.F | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-09 | 2023-09-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1837 | Reinforced Concrete Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-B | QX To RX / 10 To 10Z | FDN To L.G | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-07 | 2023-09-08 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-EL-0062 | Horizontal Earthing Conduits as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 9 & 10 | B5-B | N/A | G.F | N/A | N/A | 2023-09-06 | 2023-09-07 | 2023-09-12 | 2023-09-08 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0063 | Installation of Earthing Cable and Clamp as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 9 | B5-B | SY To TX / 18 To 20 | G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-12 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ME-0160 | Installation of Puddle Flange in Treated Water Tank | 00 | MEP | Mech | Pluming | Drainage | Zone 2 | A3 | K To QX / B To EY | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-07 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1838 | Waterproofing PVC Layer | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1839 | PVC Protection - Screed | 00 | Civil | Civil | Waterproofing | PVC | Zone 12 | N/A | RY To TX / 38 | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1840 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A4-A | TX To SY / A | L.G | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-07 | 2023-09-10 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1841 | Reinforced Concrete Walls Formwork to Level "-1.05" | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 | N/A | 16 / QX To RX | L.G To G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-10 | 2023-09-10 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1842 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 | N/A | J To QZ / 37 To 38 | G.F To MEZZ | N/A | N/A | 2023-09-07 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1843 | Reinforced Concrete Walls Formwork Coordinates & level to Level "-1.1" | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 23 To 27 / H To G | L.G To G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-11 | 2023-09-10 | DONE | C |  |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1843 | Reinforced Concrete Walls Formwork Coordinates & level to Level "-1.1" | 01 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 23 To 27 / H To G | L.G To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1844 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1845 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 & 11 | N/A | 31 To 25 / SY | FDN | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1846 | Reinforced Concrete Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 & 10 & 11 | B4-A | 23 To 32 / L To S | G.F | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-09 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1847 | Reinforced Concrete Foundation Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 / TX To RY | L.G | N/A | N/A | 2023-09-07 | 2023-09-09 | 2023-09-10 | 2023-09-10 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1848 | RC Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 1 | N/A | 2 To 3 / A To D | FDN | N/A | N/A | 2023-09-09 | 2023-09-10 | 2023-09-10 | 2023-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1849 | RC Raft Foundation Surface Preparation for Waterproofing Bitumen | 00 | Civil | Civil | Waterproofing | Bitumen | Zone 1 | N/A | 1 To 4 / A To D | FDN | N/A | N/A | 2023-09-09 | 2023-09-10 | 2023-09-10 | 2023-09-11 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1850 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1851 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0064 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 6 | B4-A | N/A | G.F To 1st | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0065 | Horizontal Earthing Conduits Level | 00 | MEP | Elec | Elec | Earthing | Zone 9 & 10 | B5-B | N/A | G.F | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0066 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 6 | B4-A | N/A | G.F To 1st | N/A | N/A | 2023-09-10 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0067 | Earthing Cable and Clamp Level as Highlighted | 00 | MEP | Elec | Elec | Earthing | Zone 9 | B5-B | SY To TX / 18 To 20 | G.F | N/A | N/A | 2023-09-10 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1852 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1853 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1854 | Reinforced Concrete Ground Slab ( Boundaries, Starter bar Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 23 / RX To TX | G.F | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-11 | 2023-09-12 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1855 | Reinforced Concrete Lower Ground Slab Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C3 | 35 To 38 / S To RX | L.G | N/A | N/A | 2023-09-10 | 2023-09-11 | 2023-09-12 | 2023-09-12 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1856 | Reinforced Concrete Lower Ground Slab ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 35 To 38 / S To RX | L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1857 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 & 4 & 9 | A4 | 9Y To 12 / RY To QZ | L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1858 | Reinforced Concrete Lower Ground Slab ( Boundaries, Starter bar Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-B | 9Y To 12 / RY To QZ | L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1859 | Backfilling Layer ( 3 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2023-09-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1860 | Backfilling Layer ( 4 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2023-09-13 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1861 | Reinforced Concrete Slab Top Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 9 & 10 | N/A | 16 To 23 / RX To TX | G.F | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1862 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | N/A | QX To QY / 10Z To 10 | S.B To L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | A | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1863 | Reinforced Concrete Mezzanine Slab Formwork ( Boundaries - Levels & Coordinates ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | V To Z / 44 To 46X | MEZZ | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1864 | Underlayment Layer - Geotextile to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | N/A | 32X To 33 / T To TX | FDN To L.G | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1865 | Reinforced Concrete Mezzanine Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 | C1 | VX To ZY / 44 To 45 | MEZZ | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-12 | 2023-09-13 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0068 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 6 | B4-A | N/A | G.F | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0069 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 5 & 6 | B4-A | N/A | G.F | N/A | N/A | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-13 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0070 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B3-A | 28 / QY | G.F | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-17 | 2023-09-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0071 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B3-A | 28 / QY | G.F | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-17 | 2023-09-14 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1866 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | N/A | 26 To 30 / M To QY | G.F To 1st | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1867 | Reinforced Concrete Foundation Bottom Layer Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 to 39/ RY To TX | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1868 | Backfilling Layer ( 5 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1869 | Backfilling Layer ( 6 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | B4 | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1870 | Waterproofing PVC Layer for Wall to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | N/A | 32X To 33 / T To TX | FDN To L.G | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2023-09-14 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1871 | PVC Protection – Cartmode for Wall to Level "-3.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 | N/A | 32X To 33 / T To TX | FDN To L.G | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-13 | 2023-09-14 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1872 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-13 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1873 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-12 | 2023-09-13 | 2023-09-13 | 2023-09-14 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1874 | Backfilling Layer ( 7 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1875 | Backfilling Layer ( 8 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1876 | Reinforced Concrete foundation Top Layer Reinforcement and Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | N/A | 38 To 39 / RY To TX | FDN To L.G | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1877 | Reinforced Concrete Walls Formwork To Level "- 0.875" | 00 | Civil | Civil | Concrete | Cast in place | Zone 4 | N/A | L To M / 12 | L.G To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1878 | Backfilling Layer ( 9 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1879 | Backfilling Layer ( 10 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 10 | N/A | 25 To 22X / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1880 | Backfilling Layer ( 11 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1881 | Backfilling Layer ( 12 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-14 | 2023-09-15 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1882 | Underlayment Layer - Geotextile to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | 24 To 22 / T To SY | FDN To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1883 | Waterproofing PVC Layer to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | 24 To 22 / T To SY | FDN To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | B | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1884 | PVC Protection – Cartmode to Level "-1.05" | 00 | Civil | Civil | Waterproofing | PVC | Zone 10 | B4 | 24 To 22 / T To SY | FDN To G.F | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | A | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1885 | Reinforced Concrete Wall Starter bars Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 / RY To TX | L.G | N/A | N/A | 2023-09-13 | 2023-09-14 | 2023-09-17 | 2023-09-15 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1886 | Reinforced Concrete Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 14 | N/A | 22 To 26 / J To G | L.G To G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1887 | Reinforced Concrete Ground Slab Formwork ( Coordinates & Levels ) | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1888 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 7 & 8 | N/A | J To QZ / 37 To 38 | G.F To MEZZ | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1889 | Reinforced Concrete Columns and Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 3 | A3-B | Q To S / 9Y To 12 | L.G | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1890 | Backfilling Layer ( 13 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-14 | 2023-09-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1891 | Backfilling Layer ( 14 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-14 | 2023-09-17 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1892 | Reinforced Concrete Walls Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | 38 / RY To TX | L.G | N/A | N/A | 2023-09-14 | 2023-09-16 |  | 2023-09-17 | -22 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1893 | Reinforced Concrete Slab Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 12 | C4 | RY To TX / 35 To 38 | G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-EL-0072 | Vertical Earthing Conduits in Columns ( Levels & Location as per attached ) | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B4-A | 23 / QY | G.F | N/A | N/A | 2023-09-14 | 2023-09-16 | 2023-09-17 | 2023-09-17 | DONE | B | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-EL-0073 | Vertical Earthing Conduits in Columns | 00 | MEP | Elec | Elec | Earthing | Zone 11 | B4-A | 23 / QY | G.F | N/A | N/A | 2023-09-16 | 2023-09-17 |  | 2023-09-18 | -21 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1894 | Reinforced Concrete Columns and Walls Formwork | 00 | Civil | Civil | Concrete | Cast in place | Zone 6 | N/A | M To PX / 30 | G.F To 1st | N/A | N/A | 2023-09-16 | 2023-09-17 | 2023-09-17 | 2023-09-18 | DONE | B | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1895 | Backfilling Layer ( 15 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 | 2023-09-17 | 2023-09-19 | DONE | A | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1896 | Backfilling Layer ( 16 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 31 / TX To T | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1897 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 5 & 6 | N/A | 23 To 30 / M To QY | G.F To 1st | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1898 | Reinforced Concrete Columns and Walls Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 8 & 15 | N/A | 32 To 35 / 46X To 47 | L.G To G.F | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Al-khaleej
1176-FSL-CP01-CN-AT-CIR-ST-1899 | Reinforced Concrete Columns Coordinates | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | A3-B | 6 To 7 / B To C | L.G | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1900 | Underlayment Layer - Geotextile to Level "-5.50" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 & 12 | N/A | 33 To 36 / TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1901 | Waterproofing PVC Layer to Level "-5.50" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 & 12 | N/A | 33 To 36 / TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Shield
1176-FSL-CP01-CN-AT-CIR-ST-1902 | Backfilling Layer ( 1 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 31 To 33 / SY To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1903 | Backfilling Layer ( 2 ) level & Coordinates | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 31 To 33 / SY To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1904 | Backfilling Layer ( 1 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 33 / T To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-20 |  | 2023-09-21 | -18 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1905 | Backfilling Layer ( 2 ) Compaction Work | 00 | Civil | Civil | Earthwork | Backfilling | Zone 11 | N/A | 30 To 33 / T To TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-20 |  | 2023-09-21 | -18 | open | L |  |  | Atrium
1176-FSL-CP01-CN-AT-CIR-ST-1906 | Reinforced Concrete Columns Reinforcement | 00 | Civil | Civil | Concrete | Cast in place | Zone 2 | N/A | 6 To 7 / B To C | FDN To L.G | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Wafaa Adly
1176-FSL-CP01-CN-AT-CIR-ST-1907 | PVC Protection – Cartmode to Level "-5.50" | 00 | Civil | Civil | Waterproofing | PVC | Zone 11 & 12 | N/A | 33 To 36 / TX | FDN | N/A | N/A | 2023-09-17 | 2023-09-18 |  | 2023-09-19 | -20 | open | L |  |  | Shield
Formulas:
Inspection Date = [Issued Date]+1
Date limit to issue response = [Inspection Date]+1
Overdue = IF([Actual Response Dates]>0,"DONE",[Date limit to issue response]-TODAY())
Overdue = IF([Actual Response Dates, row above]>0,"DONE",[Date limit to issue response]-TODAY())

## KPI
Project Name: Four Seaons Hotel -Luxor Project Code Num: P0020 | [6 empty] | Owner : | [5 empty] | Key Performance Indicators ( KPI ) | [7 empty] | Project Management : |  |  |  |  | Main Consultant : | [6 empty] | Main Contractor : ATRIUM
Total Of IR's |  |  | CIVIL | [6 empty] | Landscape | [6 empty] | Arch. | [6 empty] | ELEC | [6 empty] | MECH
MONTH | CUMULATIVE | C | A | B | C | D | Cancelled | Open | Total | A | B | C | D | Cancelled | Open | Total | A | B | C | D | Cancelled | Open | Total | A | B | C | D | Cancelled | Open | Total | A | B | C | D | Cancelled | Open | Total | From | TO
2022-01-01 | 7 | 0 | 1 | 6 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-01-01 | 2022-01-31
2022-02-01 | 17 | 0 | 5 | 12 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-02-01 | 2022-02-28
2022-03-01 | 44 | 2 | 17 | 25 | 2 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2022-03-31
2022-04-01 | 15 | 0 | 5 | 10 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-04-01 | 2022-04-30
2022-05-01 | 25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-05-01 | 2022-05-31
2022-06-01 | 54 | 2 | 7 | 41 | 0 | 1 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 5 | 2022-06-01 | 2022-06-30
2022-07-01 | 52 | 3 | 3 | 45 | 2 | 1 | 0 | 0 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 2022-07-01 | 2022-07-31
2022-08-01 | 109 | 1 | 67 | 32 | 1 | 1 | 0 | 1 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 1 | 0 | 0 | 7 | 2022-08-01 | 2022-08-31
2022-09-01 | 101 | 1 | 44 | 44 | 1 | 0 | 0 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 2022-09-01 | 2022-09-30
2022-10-01 | 116 | 3 | 52 | 52 | 1 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | 2 | 0 | 0 | 0 | 10 | 2022-10-01 | 2022-10-31
2022-11-01 | 144 | 6 | 65 | 62 | 4 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 11 | 1 | 0 | 0 | 0 | 12 | 2022-11-01 | 2022-11-30
2022-12-01 | 194 | 9 | 86 | 86 | 5 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 6 | 0 | 9 | 2 | 0 | 0 | 0 | 11 | 2022-12-01 | 2022-12-31
2023-01-01 | 214 | 1 | 112 | 84 | 0 | 0 | 0 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 11 | 1 | 0 | 0 | 0 | 12 | 2023-01-01 | 2023-01-31
2023-02-01 | 183 | 10 | 68 | 69 | 9 | 0 | 0 | 0 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 9 | 1 | 24 | 1 | 0 | 0 | 2 | 28 | 2023-02-01 | 2023-02-28
2023-03-01 | 231 | 9 | 98 | 97 | 7 | 0 | 0 | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 0 | 0 | 9 | 0 | 19 | 1 | 0 | 0 | 0 | 20 | 2023-03-01 | 2023-03-31
2023-04-01 | 122 | 2 | 72 | 37 | 2 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 8 | 0 | 0 | 0 | 0 | 10 | 2023-04-01 | 2023-04-30
2023-05-01 | 248 | 8 | 141 | 73 | 6 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 0 | 0 | 0 | 0 | 10 | 5 | 11 | 2 | 0 | 0 | 0 | 18 | 2023-05-01 | 2023-05-31
2023-06-01 | 136 | 1 | 52 | 57 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 0 | 2 | 0 | 0 | 9 | 3 | 13 | 1 | 1 | 0 | 0 | 18 | 2023-06-01 | 2023-06-30
2023-07-01 | 101 | 5 | 40 | 49 | 2 | 0 | 0 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 5 | 0 | 3 | 2 | 0 | 0 | 0 | 5 | 2023-07-01 | 2023-07-31
2023-08-01 | 147 | 4 | 55 | 72 | 3 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 2 | 6 | 1 | 0 | 0 | 0 | 9 | 2023-08-01 | 2023-08-31
2023-09-01 | 106 | 1 | 31 | 47 | 1 | 0 | 0 | 13 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 1 | 12 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 2023-09-01 | 2023-09-30
2023-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-10-01 | 2023-10-31
2023-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-11-01 | 2023-11-30
2023-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2023-12-01 | 2023-12-31
2024-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-01-01 | 2024-01-31
2024-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-02-01 | 2024-02-28
2024-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-03-01 | 2024-03-31
2024-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-04-01 | 2024-04-30
2024-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-05-01 | 2024-05-31
2024-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-06-01 | 2024-06-30
2024-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-07-01 | 2024-07-31
2024-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-08-01 | 2024-08-31
2024-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-09-01 | 2024-09-30
2024-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-10-01 | 2024-10-31
2024-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-11-01 | 2024-11-30
2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2024-12-01 | 2024-12-31
2025-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-01-01 | 2025-01-31
2025-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-02-01 | 2025-02-28
2025-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-03-01 | 2025-03-31
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-04-01 | 2025-04-30
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-05-01 | 2025-05-31
2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-06-01 | 2025-06-30
2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-07-01 | 2025-07-31
2025-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-08-01 | 2025-08-31
2025-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-09-01 | 2025-09-30
2025-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-10-01 | 2025-10-31
2025-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-11-01 | 2025-11-30
2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2025-12-01 | 2025-12-31
| 2366 | 68 | 1021 | 1025 | 46 | 3 | 0 | 14 | 2109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 63 | 5 | 2 | 0 | 1 | 77 | 16 | 142 | 17 | 2 | 0 | 3 | 180
Formulas:
Total Of IR's = [From]

## Summary Cumulatlve
Project : Four Seasons Hotel - Luxor |  |  | Owner : |  |  | Project Name: Four Seasons Hotel - Luxor Project Code Num: P0020 |  | Project Management : |  | Main Consultant: |  | Main Contractor : ATRIUM
[15 empty] | From | TO | Weekly
Status For Inspection Request | [6 empty] | Status For Inspection Request | [7 empty] | 2022-11-03 | 2022-11-10
CIVIL CUMULATIVE | [6 empty] | Arch. CUMULATIVE
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Code D | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Code D |  | From | TO | Monthly
CIVIL | 2109 | 1021 | 1025 | 46 | 14 | 3 | Arch. | 0 | 0 | 0 | 0 | 0 | 0 |  | 2022-12-01 | 2022-12-31
Civil Weekly | [6 empty] | Arch. Weekly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-11-03 | 2022-11-10 | [5 empty] | 2022-11-03 | 2022-11-10
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D
CIVIL | 26 | 16 | 10 | 0 | 0 | 0 | Arch. | 0 | 0 | 0 | 0 | 0 | 0
CIVIL Monthly | [6 empty] | Arch. Monthly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-12-01 | 2022-12-31 | [5 empty] | 2022-12-01 | 2022-12-31
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D
CIVIL | 177 | 86 | 86 | 5 | 0 | 0 | Arch. | 0 | 0 | 0 | 0 | 0 | 0
Status For Inspection Request | [6 empty] | Status For Inspection Request
ELEC. CUMULATIVE | [6 empty] | MECH. CUMULATIVE
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Code D |  | A | B | C | ON PROGRESS
ELEC. | 77 | 6 | 63 | 5 | 1 | 0 | MECH. | 180 | 16 | 142 | 17 | 3 | 2 |  | 22 | 205 | 22 | 4
ELEC. Weekly | [6 empty] | MECH. Weekly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-11-03 | 2022-11-10 | [5 empty] | 2022-11-03 | 2022-11-10
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D |  | A | B | C | ON PROGRESS
ELEC. | 0 | 0 | 0 | 0 | 0 | 0 | MECH. | 4 | 0 | 4 | 0 | 0 | 0 |  | 0 | 4 | 0 | 0
ELEC. Monthly | [6 empty] | MECH. Monthly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-12-01 | 2022-12-31 | [5 empty] | 2022-12-01 | 2022-12-31
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D | Code D
ELEC. | 6 | 0 | 4 | 2 | 0 | 0 | MECH. | 11 | 0 | 9 | 2 | 0 | 0 | 0
Status For Inspection Request | [6 empty] | Status For Inspection Request
Survey. CUMULATIVE | [6 empty] | CUMULATIVE ( CIVIL & Arch. & Elec. & Mech. )
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Code D | Code D
Survey | 0 | 0 | 0 | 0 | 0 | 0 | ALL | 2366 | 1043 | 1230 | 68 | 18 | 7 | 7
Survey. Weekly | [6 empty] | Weekly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-11-03 | 2022-11-10 | [5 empty] | 2022-11-03 | 2022-11-10
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D
Survey | 0 | 0 | 0 | 0 | 0 | 0 | ALL | 30 | 16 | 14 | 0 | 0 | 0
Survey. Monthly | [6 empty] | Monthly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-12-01 | 2022-12-31 | [5 empty] | 2022-12-01 | 2022-12-31
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Code D
Survey | 0 | 0 | 0 | 0 | 0 | 0 | ALL | 194 | 86 | 99 | 9 | 0 | 0

## Root Cause
Project : Four Seasons Hotel - Luxor | [5 empty] | Owner : | [5 empty] | Project Name: Four Seasons Hotel - Luxor Project Code Num: P0020 | [6 empty] | Project Management : |  |  |  | Main Consultant: |  |  |  | Main Contractor : Atrium
ALL REJECTED SIR's - ROOT CAUSE ANALYSIS FROM BEGINNING PROJECT TILL 28/02/2022
CIVIL | Root Cause Analysis | Lack of supervision |  |  |  | Poor workmanship |  |  |  | Work is not ready | Not Released from MEP |  | Survey Mistake |  |  | Not Following Project Specs |  |  | Not Following Project procedures |  |  |  | Lack of Coordination |  |  |  | Using unapproved Material |  | Others | Total
| Root Cause Subtitle | Lack of Construction Supervision | QC Supervision | Subcontractor Supervision | Survey Supervision | Poor Subcontractor Workmanship | Bad Quality of Material | Bad Quality of Tools | Product Cleaning | Work is not ready | Mech. Release | Elec. Release | Reference level not correct | Reference coordinates not correct | Item Location not correct | Not following approved SD | Using Improper Material | Required tests not implemented | Relevant MS,ITP,etc not submitted for approval | Not following approved MS | Not following approved ITP | Unapproved subcontractor | Lack of communication | Safe access not ready | Inspection tools not available | involved inspection parties not attend | Material approval delay | MIR not approved | Consultant request extra documents and materials
| No. of Rejected WIRs | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6
| % | 0% | 0% | 0% | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 16.67% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67%
ARCH | Root Cause Analysis | Lack of supervision |  |  |  | Poor workmanship |  |  |  | Work is not ready | Not Released from MEP |  | Survey Mistake |  |  | Not Following Project Specs |  |  | Not Following Project procedures |  |  |  | Lack of Coordination |  |  |  | Using unapproved Material |  | Others | Total
| Root Cause Subtitle | Lack of Construction Supervision | QC Supervision | Subcontractor Supervision | Survey Supervision | Poor Subcontractor Workmanship | Bad Quality of Material | Bad Quality of Tools | Product Cleaning | Work is not ready | Mech. Release | Elec. Release | Reference level not correct | Reference coordinates not correct | Item Location not correct | Not following approved SD | Using Improper Material | Required tests not implemented | Relevant MS,ITP,etc not submitted for approval | Not following approved MS | Not following approved ITP | Unapproved subcontractor | Lack of communication | Safe access not ready | Inspection tools not available | involved inspection parties not attend | Material approval delay | MIR not approved | Consultant request extra documents and materials
| No. of Rejected WIRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
MECH. | Root Cause Analysis | Lack of supervision |  |  |  | Poor workmanship |  |  |  | Work is not ready | Not Released from MEP |  | Survey Mistake |  |  | Not Following Project Specs |  |  | Not Following Project procedures |  |  |  | Lack of Coordination |  |  |  | Using unapproved Material |  | Others | Total
| Root Cause Subtitle | Lack of Construction Supervision | QC Supervision | Subcontractor Supervision | Survey Supervision | Poor Subcontractor Workmanship | Bad Quality of Material | Bad Quality of Tools | Product Cleaning | Work is not ready | Mech. Release | Elec. Release | Reference level not correct | Reference coordinates not correct | Item Location not correct | Not following approved SD | Using Improper Material | Required tests not implemented | Relevant MS,ITP,etc not submitted for approval | Not following approved MS | Not following approved ITP | Unapproved subcontractor | Lack of communication | Safe access not ready | Inspection tools not available | involved inspection parties not attend | Material approval delay | MIR not approved | Consultant request extra documents and materials
| No. of Rejected WIRs | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
| % | 66.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ELEC. | Root Cause Analysis | Lack of supervision |  |  |  | Poor workmanship |  |  |  | Work is not ready | Not Released from MEP |  | Survey Mistake |  |  | Not Following Project Specs |  |  | Not Following Project procedures |  |  |  | Lack of Coordination |  |  |  | Using unapproved Material |  | Others | Total
| Root Cause Subtitle | Lack of Construction Supervision | QC Supervision | Subcontractor Supervision | Survey Supervision | Poor Subcontractor Workmanship | Bad Quality of Material | Bad Quality of Tools | Product Cleaning | Work is not ready | Mech. Release | Elec. Release | Reference level not correct | Reference coordinates not correct | Item Location not correct | Not following approved SD | Using Improper Material | Required tests not implemented | Relevant MS,ITP,etc not submitted for approval | Not following approved MS | Not following approved ITP | Unapproved subcontractor | Lack of communication | Safe access not ready | Inspection tools not available | involved inspection parties not attend | Material approval delay | MIR not approved | Consultant request extra documents and materials
| No. of Rejected WIRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Survey | Root Cause Analysis | Lack of supervision |  |  |  | Poor workmanship |  |  |  | Work is not ready | Not Released from MEP |  | Survey Mistake |  |  | Not Following Project Specs |  |  | Not Following Project procedures |  |  |  | Lack of Coordination |  |  |  | Using unapproved Material |  | Others | Total
| Root Cause Subtitle | Lack of Construction Supervision | QC Supervision | Subcontractor Supervision | Survey Supervision | Poor Subcontractor Workmanship | Bad Quality of Material | Bad Quality of Tools | Product Cleaning | Work is not ready | Mech. Release | Elec. Release | Reference level not correct | Reference coordinates not correct | Item Location not correct | Not following approved SD | Using Improper Material | Required tests not implemented | Relevant MS,ITP,etc not submitted for approval | Not following approved MS | Not following approved ITP | Unapproved subcontractor | Lack of communication | Safe access not ready | Inspection tools not available | involved inspection parties not attend | Material approval delay | MIR not approved | Consultant request extra documents and materials
| No. of Rejected WIRs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| % | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
All Discipline | Root Cause Analysis | Lack of supervision |  |  |  | Poor workmanship |  |  |  | Work is not ready | Not Released from MEP |  | Survey Mistake |  |  | Not Following Project Specs |  |  | Not Following Project procedures |  |  |  | Lack of Coordination |  |  |  | Using unapproved Material |  | Others | Total
| Root Cause Subtitle | Lack of Construction Supervision | QC Supervision | Subcontractor Supervision | Survey Supervision | Poor Subcontractor Workmanship | Bad Quality of Material | Bad Quality of Tools | Product Cleaning | Work is not ready | Mech. Release | Elec. Release | Reference level not correct | Reference coordinates not correct | Item Location not correct | Not following approved SD | Using Improper Material | Required tests not implemented | Relevant MS,ITP,etc not submitted for approval | Not following approved MS | Not following approved ITP | Unapproved subcontractor | Lack of communication | Safe access not ready | Inspection tools not available | involved inspection parties not attend | Material approval delay | MIR not approved | Consultant request extra documents and materials
| No. of Rejected WIRs | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9
| % | 22.22% | 0% | 0% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 11.11% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11%

## Summary Last Rev.
Project :Four Seasons Hotel - Luxor |  | Owner : |  | Project Management : |  | Project Name : Four Seasons Luxor Project Code Num : P0020 |  | Main Consultant : |  |  |  | Main Contractor : Atrium
[14 empty] | From | TO | Weekly
Status For Inspection Request | [6 empty] | Status For Inspection Request | [6 empty] | 2022-06-01 | 2022-06-23
CIVIL CUMULATIVE | [6 empty] | Arch. CUMULATIVE
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | From | TO | Monthly
CIVIL | 2063 | 1021 | 1023 | 2 | 15 | 0 | Arch. | 0 | 0 | 0 | 0 | 0 | 0 | 2022-06-01 | 2022-06-23
Civil Weekly | [6 empty] | Arch. Weekly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-06-01 | 2022-06-23 | [5 empty] | 2022-06-01 | 2022-06-23
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled
CIVIL | 39 | 6 | 32 | 0 | 1 | 0 | Arch. | 0 | 0 | 0 | 0 | 0 | 0
CIVIL Monthly | [6 empty] | Arch. Monthly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-06-01 | 2022-06-23 | [5 empty] | 2022-06-01 | 2022-06-23
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled
CIVIL | 39 | 6 | 32 | 0 | 1 | 0 | Arch. | 0 | 0 | 0 | 0 | 0 | 0
Status For Inspection Request | [6 empty] | Status For Inspection Request
ELEC. CUMULATIVE | [6 empty] | MECH. CUMULATIVE
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | A | B | C | ON PROGRESS
ELEC. | 71 | 6 | 63 | 1 | 1 | 0 | MECH. | 162 | 16 | 140 | 3 | 3 | 0 | 22 | 203 | 4 | 4
ELEC. Weekly | [6 empty] | MECH. Weekly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-06-01 | 2022-06-23 | [5 empty] | 2022-06-01 | 2022-06-23
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | A | B | C | ON PROGRESS
ELEC. | 0 | 0 | 0 | 0 | 0 | 0 | MECH. | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 0 | 1
ELEC. Monthly | [6 empty] | MECH. Monthly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-06-01 | 2022-06-23 | [5 empty] | 2022-06-01 | 2022-06-23
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled
ELEC. | 0 | 0 | 0 | 0 | 0 | 0 | MECH. | 3 | 0 | 2 | 0 | 1 | 0
Status For Inspection Request | [6 empty] | Status For Inspection Request
Survey. CUMULATIVE | [6 empty] | CUMULATIVE ( CIVIL & Arch. & Elec. & Mech. )
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS | Cancelled
ELEC. | 0 | 0 | 0 | 0 | 0 | 0 | ALL | 2297 | 1043 | 1225 | 6 | 18 | 0
Survey. Weekly | [6 empty] | Weekly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-06-01 | 2022-06-23 | [5 empty] | 2022-06-01 | 2022-06-23
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled
ELEC. | 0 | 0 | 0 | 0 | 0 | 0 | ALL | 40 | 6 | 33 | 0 | 1 | 0
Survey. Monthly | [6 empty] | Monthly
[5 empty] | From | TO | [5 empty] | From | TO
[5 empty] | 2022-06-01 | 2022-06-23 | [5 empty] | 2022-06-01 | 2022-06-23
Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled | Discipline | Total Issued | CODE A | CODE B | CODE C | ON PROGRESS WITH Consultant | Cancelled
ELEC. | 0 | 0 | 0 | 0 | 0 | 0 | ALL | 40 | 6 | 33 | 0 | 1 | 0

## Sheet1
Cut Date | From | TO
| 2021-05-20 | 2021-05-27
CIVIL | Last Rev. This Week | Old Rev. This Week | Last Rev. Cumulative | Old Rev. Cumulative
| 0 | 0 | 2 | 0
Code C This Week BEFORE UPGRADING | 0 | Code C Cumulative BEFORE UPGRADING | 2
Code C This Week AFTER UPGRADING | 0 | Code C Cumulative AFTER UPGRADING | 2
2
Arch. | Last Rev. This Week | Old Rev. This Week | Last Rev. Cumulative | Old Rev. Cumulative
| 0 | 0 | 0 | 0
Code C This Week BEFORE UPGRADING | 0 | Code C Cumulative BEFORE UPGRADING | 0
Code C This Week AFTER UPGRADING | 0 | Code C Cumulative AFTER UPGRADING | 0
0
ELEC | Last Rev. This Week | Old Rev. This Week | Last Rev. Cumulative | Old Rev. Cumulative
| 0 | 0 | 1 | 0
Code C This Week BEFORE UPGRADING | 0 | Code C Cumulative BEFORE UPGRADING | 1
Code C This Week AFTER UPGRADING | 0 | Code C Cumulative AFTER UPGRADING | 1
1
MECH | Last Rev. This Week | Old Rev. This Week | Last Rev. Cumulative | Old Rev. Cumulative
| 0 | 0 | 3 | 0
Code C This Week BEFORE UPGRADING | 0 | Code C Cumulative BEFORE UPGRADING | 3
Code C This Week AFTER UPGRADING | 0 | Code C Cumulative AFTER UPGRADING | 3
3
Survey | Last Rev. This Week | Old Rev. This Week | Last Rev. Cumulative | Old Rev. Cumulative
| 0 | 0 | 0 | 0
Code C This Week BEFORE UPGRADING | 0 | Code C Cumulative BEFORE UPGRADING | 0
Code C This Week AFTER UPGRADING | 0 | Code C Cumulative AFTER UPGRADING | 0
0

## KPI-1 (hidden)
Total Of IR'S |  | CIVIL |  |  |  |  | ARCH |  |  |  |  | ELEC |  |  |  |  | MECH
MONTH | CUMULATIVE | A | AN | R&R | Open | Total | A | AN | R&R | Open | Total | A | AN | R&R | Open | Total | A | AN | R&R | Open | Total
2018-04-01 | 0 | 0 | [19 empty] | 2020-08-01 | 2020-08-31
2018-05-01 | 0 | 0 | [19 empty] | 2020-09-01 | 2020-09-30
2018-06-01 | 0 | [20 empty] | 2020-10-01 | 2020-10-31
2018-07-01 | 0 | [20 empty] | 2020-11-01 | 2020-11-30
2018-08-01 | 0 | [20 empty] | 2020-12-01 | 2020-12-31
2018-09-01 | 0 | [20 empty] | 2021-01-01 | 2021-01-31
2018-10-01 | 0 | [20 empty] | 2021-02-01 | 2021-02-28
2018-11-01 | 0 | [20 empty] | 2021-03-01 | 2021-03-31
2018-12-01 | 0 | [20 empty] | 2021-04-01 | 2021-04-30
2019-01-01 | 0 | [20 empty] | 2021-05-01 | 2021-05-31
2019-02-01 | 0 | [20 empty] | 2021-06-01 | 2021-06-30
2019-03-01 | 0 | [20 empty] | 2021-07-01 | 2021-07-31
2019-04-01 | 0 | [20 empty] | 2021-08-01 | 2021-08-31
2019-05-01 | 0 | [20 empty] | 2021-09-01 | 2021-09-30
2019-06-01 | 0 | [20 empty] | 2021-10-01 | 2021-10-31
2019-07-01 | 0 | [20 empty] | 2021-11-01 | 2021-11-30
2019-08-01 | 0 | [20 empty] | 2021-12-01 | 2021-12-31
2019-09-01 | 0 | [20 empty] | 2022-01-01 | 2022-01-31
2019-10-01 | 0 | [20 empty] | 2022-02-01 | 2022-02-28
2019-11-01 | 0 | [20 empty] | 2022-03-01 | 2022-03-31
2019-12-01 | 0 | [20 empty] | 2022-04-01 | 2022-04-30
2020-01-01 | 0
2020-02-01 | 0
2020-03-01 | 0
2020-04-01 | 0
Total | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
|  | Total Civil |  |  |  | 0 | Total Arch |  |  |  | 0 | Total ELEC |  |  |  | 0 | Total MECH |  |  |  | 0
[11 empty] | 12 | [9 empty] | 2